## Dashboard
Status Date |  |  | Dashboard - A320 FFS SN06
2026-01-30 |  |  | KPIs for Material Supply Chain
Milestone | Date | Status
1
0
0
0
0
0
No. Purchase Orders / No. Lines
OTIF (%) -
On time in full
Backorder Rate - Pending Orders
No. Extended Deadline Orders
No. POs pending to be issued
967
91%
9%
13
0
No. On-going Deliveries
#¡VALOR!

## SAP_Material Status
Item | Material | Material Description | Solped | Solped Line | Date Sol. | Warning Sol | No. PO | PO Line | PO Date | Release PO Date | Warning PO | Delivery Date | Planned Lead Time | Tmpo.tratamiento EM | Status | Ctd. Solicitada | Ctd. pedido | Ctd. Recepcionada | Ctd. por recepcionar | Ctd. Aceptada | Ctd. Rechazada | Received | Valor por entregar | Valor ctd. aceptada | Supplier | OEM | P/N OEM | Concluída | Número modificaciones en fecha entrega | Número modificaciones fecha estadística | Es material RUF(Si='X',No='') | Elemento PEP | Lead Time | Lead Time Impact | Revised Date | OTD | OTD Qty | Late | Late Qty | Extended dealine Orders | OTIF | OTIF (%) | Pending Orders to be received | Pending to be issued | SOLPED BLOQ | PO BLOQ | Month | Backorder Rate | Today | Delivery Date-Today | On-going Deliveries | On-going Deliveries (Qty) | Warning Units (neededvsordered)
1 | 39121435 | Unidad de distribuci&#243;n de potencia | 1101755661 | 1 | 2024-06-14 |  | 4800002570 | 5000 | 2024-06-07 |  |  | 2024-06-15 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1237430 |  | 0 | 0 |  | 7218¦JA2580_1001 | 8 | - | 2026-01-30 | YES | 1900-01-02 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% | 2026-04-23 | -677 | 0
2 | 39121415 | Unidad de distribuci&#243;n de potencia | 1101755661 | 2 | 2024-06-14 |  | 4800002570 | 5010 | 2024-06-07 |  |  | 2024-06-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6520342 |  | 0 | 0 |  | 7218¦JA2580_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -677 | 0
3 | 26121536 | Unidad de distribuci&#243;n de potencia | 1101755661 | 3 | 2024-06-14 |  | 4800002570 | 5020 | 2024-06-07 |  |  | 2024-06-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0479409 |  | 0 | 0 |  | 7218¦JA2580_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -677 | 0
4 | 39121435 | Unidad de distribuci&#243;n de potencia | 1101755661 | 4 | 2024-06-14 |  | 4800002570 | 5030 | 2024-06-07 |  |  | 2024-06-15 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1237433 |  | 0 | 0 |  | 7218¦JA2580_1001 | 8 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -677 | 0
5 | 39121708 | Tira de jumpers Wago serie TOPJOB S, 200 | 1101756080 | 1 | 2024-06-17 |  | 4800002579 | 450 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5076591 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
6 | 39121432 | Conector circular Amphenol Limited Hembr | 1101756080 | 2 | 2024-06-17 |  | 4800002579 | 460 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8751456 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
7 | 39121432 | Conector circular Amphenol Limited Macho | 1101756080 | 3 | 2024-06-17 |  | 4800002579 | 470 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8751462 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
8 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 4 | 2024-06-17 |  | 4800002579 | 480 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620695 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
9 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 5 | 2024-06-17 |  | 4800002579 | 490 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620686 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
10 | 39121413 | Conector circular Amphenol Limited Hembr | 1101756080 | 6 | 2024-06-17 |  | 4800002579 | 500 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1860301 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
11 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 7 | 2024-06-17 |  | 4800002579 | 510 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620664 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
12 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 8 | 2024-06-17 |  | 4800002579 | 520 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620676 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
13 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 9 | 2024-06-17 |  | 4800002579 | 530 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 300 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620673 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
14 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 10 | 2024-06-17 |  | 4800002579 | 540 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 300 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620670 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
15 | 39121432 | Contacto para conector circular Amphenol | 1101756080 | 11 | 2024-06-17 |  | 4800002579 | 550 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620682 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
16 | 39121413 | Conector circular Amphenol Limited Conec | 1101756080 | 12 | 2024-06-17 |  | 4800002579 | 560 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368091 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
17 | 39121413 | Conector circular Amphenol Limited Conec | 1101756080 | 13 | 2024-06-17 |  | 4800002579 | 570 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368157 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
18 | 39121413 | Conector circular Amphenol Limited Conec | 1101756080 | 14 | 2024-06-17 |  | 4800002579 | 580 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368092 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
19 | 39121413 | Conector circular Amphenol Limited Conec | 1101756080 | 15 | 2024-06-17 |  | 4800002579 | 590 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368155 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
20 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756080 | 16 | 2024-06-17 |  | 4800002579 | 600 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804838 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
21 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756080 | 17 | 2024-06-17 |  | 4800002579 | 610 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804913 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
22 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 1 | 2024-06-17 |  | 4800002579 | 800 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804913 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
23 | 39121413 | Conector circular Amphenol Limited Conec | 1101756129 | 2 | 2024-06-17 |  | 4800002579 | 810 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368094 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
24 | 39121413 | Conector circular Amphenol Limited Conec | 1101756129 | 3 | 2024-06-17 |  | 4800002579 | 820 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368158 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
25 | 39121413 | Conector circular Amphenol Limited Conec | 1101756129 | 4 | 2024-06-17 |  | 4800002579 | 830 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368095 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
26 | 39121413 | Conector circular Amphenol Limited Conec | 1101756129 | 5 | 2024-06-17 |  | 4800002579 | 840 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368161 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
27 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 6 | 2024-06-17 |  | 4800002579 | 850 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804840 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
28 | 39121413 | Conector circular Amphenol Limited Conec | 1101756129 | 7 | 2024-06-17 |  | 4800002579 | 860 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368163 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
29 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 8 | 2024-06-17 |  | 4800002579 | 870 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804846 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
30 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 9 | 2024-06-17 |  | 4800002579 | 880 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804918 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
31 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 10 | 2024-06-17 |  | 4800002579 | 890 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 9 | 9 | 9 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804847 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
32 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 11 | 2024-06-17 |  | 4800002579 | 900 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 9 | 9 | 9 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804921 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
33 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 12 | 2024-06-17 |  | 4800002579 | 910 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 29 | 29 | 29 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804849 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 29 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
34 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756129 | 13 | 2024-06-17 |  | 4800002579 | 920 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 29 | 29 | 29 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804920 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 29 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
35 | 32000000 | Conector circular MIL-C-38999 serie III | 1101756211 | 1 | 2024-06-17 |  | 4800002579 | 980 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804923 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
36 | 39121413 | Conector circular Amphenol India Hembra | 1101756211 | 2 | 2024-06-17 |  | 4800002579 | 990 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2475435 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
37 | 39121413 | Conector circular Amphenol India Hembra | 1101756211 | 3 | 2024-06-17 |  | 4800002579 | 1000 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2475437 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
38 | 39121413 | Conector circular Souriau Sunbank by Eat | 1101756211 | 4 | 2024-06-17 |  | 4800002579 | 1010 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7601259 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
39 | 39121415 | Conector D-sub FCT from Molex, Serie 173 | 1101756211 | 5 | 2024-06-17 |  | 4800002579 | 1020 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2075813 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
40 | 39121421 | Carcasa de conector Molex 39-01-4031, Se | 1101756211 | 6 | 2024-06-17 |  | 4800002579 | 1030 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6795842P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
41 | 39121432 | Contacto de crimpado Molex 39-00-0039, M | 1101756211 | 7 | 2024-06-17 |  | 4800002579 | 1040 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1729134P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
42 | 39121421 | Carcasa de conector de crimpado Molex 39 | 1101756211 | 8 | 2024-06-17 |  | 4800002579 | 1050 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 30 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2076789 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
43 | 39121432 | Contacto de crimpado Molex 39-00-0041, M | 1101756211 | 9 | 2024-06-17 |  | 4800002579 | 1060 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1729140P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
44 | 39121432 | Contacto de crimpado hembra Molex serie | 1101756211 | 10 | 2024-06-17 |  | 4800002579 | 1070 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 250 | 250 | 250 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2363050P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
45 | 39121432 | Contacto de crimpado macho Molex serie S | 1101756211 | 11 | 2024-06-17 |  | 4800002579 | 1080 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 250 | 250 | 250 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2363044P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
46 | 39121421 | Carcasa de conector Molex 50-57-9204, Se | 1101756211 | 12 | 2024-06-17 |  | 4800002579 | 1090 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6703887 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
47 | 39121421 | Carcasa de conector Molex 50-57-9404, Se | 1101756211 | 13 | 2024-06-17 |  | 4800002579 | 1100 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6783161 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
48 | 39121432 | Contacto de crimpado hembra Molex serie | 1101756211 | 14 | 2024-06-17 |  | 4800002579 | 1110 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6794742P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
49 | 39121421 | Carcasa de conector Molex 43025-0600, Se | 1101756211 | 15 | 2024-06-17 |  | 4800002579 | 1120 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 125 | 125 | 125 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2332769P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 125 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
50 | 39121421 | Carcasa de conector Molex 43020-0600, Se | 1101756211 | 16 | 2024-06-17 |  | 4800002579 | 1130 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2332826P |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
51 | 39121432 | Contacto de crimpado hembra Molex serie | 1101756211 | 17 | 2024-06-17 |  | 4800002579 | 1140 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2333009 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
52 | 39121432 | Contacto de terminal de crimpado Molex 4 | 1101756211 | 18 | 2024-06-17 |  | 4800002579 | 1150 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2333037 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
53 | 39121432 | Contacto de crimpado hembra Molex serie | 1101756236 | 1 | 2024-06-17 |  | 4800002579 | 1220 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6706293 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
54 | 39121421 | Carcasa de conector Molex 51110-0860, Se | 1101756236 | 2 | 2024-06-17 |  | 4800002579 | 1230 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6703607 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
55 | 39121432 | Puntera hueca de crimpado Schneider Elec | 1101756236 | 3 | 2024-06-17 |  | 4800002579 | 1240 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2546429 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
56 | 31163100 | Tornillo de conector - Bloqueo roscado, | 1101756236 | 4 | 2024-06-17 |  | 4800002579 | 1250 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 400 | 400 | 400 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0453886 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
57 | 11162114 | Cinta de gancho y bucle Velcro de color | 1101756236 | 5 | 2024-06-17 |  | 4800002579 | 1260 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 4239533 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
58 | 39121432 | Terminal redondo aislado de Cobre RS PRO | 1101756236 | 6 | 2024-06-17 |  | 4800002579 | 1270 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2673919 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
59 | 39121432 | Terminal redondo aislado de Cobre RS PRO | 1101756236 | 7 | 2024-06-17 |  | 4800002579 | 1280 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2673880 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
60 | 39121432 | Terminal redondo aislado de Cobre RS PRO | 1101756236 | 8 | 2024-06-17 |  | 4800002579 | 1290 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 500 | 500 | 500 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2673650 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
61 | 39121432 | Terminal redondo aislado de Cobre RS PRO | 1101756236 | 9 | 2024-06-17 |  | 4800002579 | 1300 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2394098 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
62 | 39121432 | Terminal de horquilla RS PRO, Aislado, M | 1101756236 | 10 | 2024-06-17 |  | 4800002579 | 1310 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0534272 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
63 | 39121432 | Puntera hueca de crimpado RS PRO, Pin de | 1101756236 | 11 | 2024-06-17 |  | 4800002579 | 1320 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2114296 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
64 | 39121432 | Puntera hueca de crimpado RS PRO, Pin de | 1101756236 | 12 | 2024-06-17 |  | 4800002579 | 1330 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2114319 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
65 | 39121432 | Puntera hueca de crimpado RS PRO, Pin de | 1101756236 | 13 | 2024-06-17 |  | 4800002579 | 1340 | 2024-06-14 |  |  | 2024-06-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2114325 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -674 | 0
66 | 24112003 | Gaveta RS PRO, Rojo de Cart&#243;n, 100m | 1101773840 | 1 | 2024-08-08 |  | 4800002611 | 3020 | 2024-08-01 |  |  | 2024-08-09 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2281188 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -622 | 0
67 | 24112003 | Gaveta RS PRO, Rojo de Cart&#243;n, 100m | 1101773840 | 2 | 2024-08-08 |  | 4800002611 | 3030 | 2024-08-01 |  |  | 2024-08-09 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2281116 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 8 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -622 | 0
68 | 24112003 | Gaveta RS PRO, Rojo de Cart&#243;n, 100m | 1101773840 | 3 | 2024-08-08 |  | 4800002611 | 3040 | 2024-08-01 |  |  | 2024-08-09 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2281194 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -622 | 0
69 | 24112003 | Gaveta RS PRO, Rojo de Cart&#243;n, 100m | 1101773840 | 4 | 2024-08-08 |  | 4800002611 | 3050 | 2024-08-01 |  |  | 2024-08-09 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2281122 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -622 | 0
70 | 1709800000000 | PEQUEÑO MATERIAL FERRETERIA E INSTALACIO | 1101775736 | 1 | 2024-08-19 |  | 4200576567 | 90 | 2024-09-09 | 2024-09-09 |  | 2024-11-06 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | HILTI ESPAÑOLA, S.A. | OTROS FABRICANTES | 1709800000000 |  | 0 | 0 |  | 7218¦JA2593_1001 | 58 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -533 | 0
71 | 1709800000000 | PEQUEÑO MATERIAL FERRETERIA E INSTALACIO | 1101775736 | 2 | 2024-08-19 |  | 4200576567 | 100 | 2024-09-09 | 2024-09-09 |  | 2024-11-06 | 55 | 8 | Liberado | 1 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | HILTI ESPAÑOLA, S.A. | OTROS FABRICANTES | 1709800000000 |  | 0 | 0 |  | 7218¦JA2593_1001 | 58 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -533 | 0
72 | 1709800000000 | PEQUEÑO MATERIAL FERRETERIA E INSTALACIO | 1101775736 | 3 | 2024-08-19 |  | 4200576567 | 110 | 2024-09-09 | 2024-09-09 |  | 2024-11-06 | 55 | 8 | Liberado | 1 | 24 | 24 | 0 | 0 | 0 | X | 0.00 |  | HILTI ESPAÑOLA, S.A. | OTROS FABRICANTES | 1709800000000 |  | 0 | 0 |  | 7218¦JA2593_1001 | 58 | - |  | YES | 24 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -533 | 0
73 | 1709800000000 | PEQUEÑO MATERIAL FERRETERIA E INSTALACIO | 1101775736 | 4 | 2024-08-19 |  | 4200576567 | 120 | 2024-09-09 | 2024-09-09 |  | 2024-11-06 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | HILTI ESPAÑOLA, S.A. | OTROS FABRICANTES | 1709800000000 |  | 0 | 0 |  | 7218¦JA2593_1001 | 58 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -533 | 0
74 | 1709800000000 | PEQUEÑO MATERIAL FERRETERIA E INSTALACIO | 1101775736 | 5 | 2024-08-19 |  | 4200576567 | 130 | 2024-09-09 | 2024-09-09 |  | 2024-11-06 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | HILTI ESPAÑOLA, S.A. | OTROS FABRICANTES | 1709800000000 |  | 0 | 0 |  | 7218¦JA2593_1001 | 58 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -533 | 0
75 | 9999000322010 | N.R. PANELES SIMULADORES | 1101780013 | 1 | 2024-09-05 |  | 4200578537 | 10 | 2024-09-24 | 2024-09-24 |  | 2025-01-31 | 95 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 1 | 1 |  | 7218¦JA2583_1001 | 129 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -447 | 0
76 | 32121615 | Resistencia RS PRO, de 100? &#177;5%, 0. | 1101786463 | 1 | 2024-09-26 |  | 4800002666 | 1210 | 2024-09-24 |  |  | 2024-09-27 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7077587 |  | 0 | 0 |  | 7218¦JA2593_1001 | 3 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -573 | 0
77 | 32121615 | Resistencia RS PRO, de 100? &#177;5%, 0. | 1101786467 | 1 | 2024-09-26 |  | 4800002666 | 1220 | 2024-09-24 |  |  | 2024-09-27 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7077587 |  | 0 | 0 |  | 7218¦JA2593_1001 | 3 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -573 | 0
78 | 39111803 | Soporte para LED Arcolectric (Bulgin) Lt | 1101790024 | 1 | 2024-10-04 |  | 4800002669 | 4120 | 2024-10-01 |  |  | 2024-10-05 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2370519 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -565 | 0
79 | 32111601 | Fototransistor NPN ams OSRAM de amplio e | 1101790024 | 2 | 2024-10-04 |  | 4800002669 | 4130 | 2024-10-01 |  |  | 2024-10-05 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6547808P |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -565 | 0
80 | 40183009 | Tubo termorretr&#225;ctil RS PRO de Poli | 1101790024 | 3 | 2024-10-04 |  | 4800002669 | 4140 | 2024-10-01 |  |  | 2024-10-05 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7004646 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -565 | 0
81 | 31163100 | Tornillo de conector - Bloqueo roscado, | 1101791120 | 1 | 2024-10-08 |  | 4800002684 | 630 | 2024-10-07 |  |  | 2024-10-09 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0453886 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -561 | 0
82 | 39121432 | Conector circular Amphenol Limited Macho | 1101791120 | 2 | 2024-10-08 |  | 4800002684 | 640 | 2024-10-07 |  |  | 2024-10-09 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8751462 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -561 | 0
83 | 39121432 | Puntera hueca de crimpado RS PRO, Pin de | 1101791120 | 3 | 2024-10-08 |  | 4800002684 | 650 | 2024-10-07 |  |  | 2024-10-09 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2114280 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -561 | 0
84 | 26121522 | Cable para Entornos Hostiles TE Connecti | 1101791858 | 1 | 2024-10-10 |  | 4800002684 | 2430 | 2024-10-07 |  |  | 2024-10-11 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2291472 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -559 | 0
85 | 32000000 | Cabezal de pulsador Schneider Electric s | 1101792080 | 1 | 2024-10-10 |  | 4800002684 | 3030 | 2024-10-07 |  |  | 2024-10-11 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2762926 |  | 0 | 0 |  | 7218¦JA2594_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -559 | 0
86 | 39121432 | Contacto para conector circular Amphenol | 1101792134 | 1 | 2024-10-10 |  | 4800002684 | 3240 | 2024-10-07 |  |  | 2024-10-11 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7620670 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -559 | 0
87 | 39112102 | LED Kingbright, Azul, 465 nm, Vf= 3.3 V, | 1101792163 | 1 | 2024-10-10 |  | 4800002684 | 3270 | 2024-10-07 |  |  | 2024-10-11 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 4663548 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -559 | 0
88 | 32111503 | LED Nichia, Blanco, Vf= 3,2 V, 65 &#176; | 1101792163 | 2 | 2024-10-10 |  | 4800002684 | 3280 | 2024-10-07 |  |  | 2024-10-11 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7133974 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -559 | 0
89 |  | MONTAJE SIMULADOR A320 | 1101792892 | 1 | 2024-10-14 |  | 4300334654 | 10 | 2024-11-04 | 2024-11-04 |  | 2024-11-06 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -533 | 0
90 | 32121609 | Resistencia TE Connectivity, de 2k? &#17 | 1101794250 | 1 | 2024-10-16 |  | 4800002692 | 3500 | 2024-10-11 |  |  | 2024-10-17 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1251200 |  | 0 | 0 |  | 7218¦JA2593_1001 | 6 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -553 | 0
91 | 39121534 | Luz piloto, Universal LED, di&#225;metro | 1101794252 | 1 | 2024-10-16 |  | 4800002692 | 3510 | 2024-10-11 |  |  | 2024-10-17 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6095846 |  | 0 | 0 |  | 7218¦JA2593_1001 | 6 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -553 | 0
92 | 39122221 | Bloque de luces Eaton 216557 M22-LED-W, | 1101794252 | 2 | 2024-10-16 |  | 4800002692 | 3520 | 2024-10-11 |  |  | 2024-10-17 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3993630 |  | 0 | 0 |  | 7218¦JA2593_1001 | 6 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -553 | 0
93 | 32111601 | Fototransistor NPN Vishay sensible a IR, | 1101794570 | 1 | 2024-10-17 |  | 4800002695 | 200 | 2024-10-18 |  |  | 2024-10-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7000760P |  | 0 | 0 |  | 7218¦JA2593_1001 | 0 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -552 | 0
94 | 27112147 | Herramienta de crimpado Molex, serie 207 | 1101795754 | 1 | 2024-10-21 |  | 4800002700 | 470 | 2024-10-24 |  | BORR | 2024-10-22 | 0 | 0 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 272.54 |  | AMIDATA, S.A. |  | 1754238 |  | 0 | 0 |  | 7218¦JA2593_1001 | -2 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -548 | 0
95 | 27112147 | Herramienta de crimpado Molex, serie 207 | 1101795754 | 1 | 2024-10-21 |  | 4800002701 | 470 | 2024-10-24 |  |  | 2024-10-22 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1754238 |  | 0 | 0 |  | 7218¦JA2593_1001 | -2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -548 | 0
96 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101796017 | 1 | 2024-10-22 |  | 4200582780 | 10 | 2024-10-24 | 2024-10-25 |  | 2024-12-16 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 53 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -493 | 0
97 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101797682 | 1 | 2024-10-25 |  | 4200583598 | 10 | 2024-10-30 | 2024-10-31 |  | 2024-12-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 48 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -492 | 0
98 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101797682 | 2 | 2024-10-25 |  | 4200583598 | 20 | 2024-10-30 | 2024-10-31 |  | 2024-12-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 48 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -492 | 0
99 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101797682 | 3 | 2024-10-25 |  | 4200583598 | 30 | 2024-10-30 | 2024-10-31 |  | 2024-12-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 48 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -492 | 0
100 | 32111601 | Fototransistor NPN Vishay sensible a IR, | 1101797739 | 1 | 2024-10-25 |  | 4800002701 | 4040 | 2024-10-24 |  |  | 2024-10-26 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7000760P |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -544 | 0
101 | 9999000322010 | N.R. PANELES SIMULADORES | 1101797741 | 1 | 2024-10-25 |  | 4200583162 | 10 | 2024-10-28 | 2024-10-29 |  | 2024-12-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 0 | 0 |  | 7218¦JA2588_1001 | 64 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -478 | 0
102 | 9999000322010 | N.R. PANELES SIMULADORES | 1101797741 | 2 | 2024-10-25 |  | 4200583162 | 20 | 2024-10-28 | 2024-10-29 |  | 2024-12-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 0 | 0 |  | 7218¦JA2588_1001 | 64 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -478 | 0
103 | 9999000322010 | N.R. PANELES SIMULADORES | 1101797741 | 3 | 2024-10-25 |  | 4200583162 | 30 | 2024-10-28 | 2024-10-29 |  | 2024-12-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 0 | 0 |  | 7218¦JA2588_1001 | 64 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -478 | 0
104 | 9999000322010 | N.R. PANELES SIMULADORES | 1101797741 | 4 | 2024-10-25 |  | 4200583162 | 40 | 2024-10-28 | 2024-10-29 |  | 2024-12-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 0 | 0 |  | 7218¦JA2588_1001 | 64 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -478 | 0
105 | 9999000322010 | N.R. PANELES SIMULADORES | 1101797741 | 5 | 2024-10-25 |  | 4200583162 | 50 | 2024-10-28 | 2024-10-29 |  | 2024-12-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 0 | 0 |  | 7218¦JA2588_1001 | 64 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -478 | 0
106 | 39121432 | Terminal de leng&#252;eta hembra TE Conn | 1101798256 | 1 | 2024-10-28 |  | 4800002706 | 580 | 2024-10-29 |  |  | 2024-10-29 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7197145 |  | 0 | 0 |  | 7218¦JA2581_1001 | 0 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -541 | 0
107 | 27112147 | Herramienta de crimpado Molex, serie 207 | 1101798585 | 1 | 2024-10-29 |  | 4800002706 | 750 | 2024-10-29 |  |  | 2024-10-30 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1754238 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -540 | 0
108 | 27112836 | Juego de puntas de atornillar MTI de 32 | 1101798585 | 2 | 2024-10-29 |  | 4800002706 | 760 | 2024-10-29 |  |  | 2024-10-30 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3966111 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -540 | 0
109 | 32121609 | Resistencia TE Connectivity, de 2k? &#17 | 1101799195 | 1 | 2024-10-30 |  | 4800002706 | 1470 | 2024-10-29 |  |  | 2024-10-31 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1251200 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -539 | 0
110 | 26121639 | Cable de datos apantallado TE Connectivi | 1101799202 | 1 | 2024-10-30 |  | 4800002706 | 1480 | 2024-10-29 |  |  | 2024-10-31 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0362572 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -539 | 0
111 |  | MONTAJE EQUIPO CABINA SIMULADOR A320 | 1101800301 | 1 | 2024-11-04 |  | 4300335153 | 10 | 2024-11-12 | 2024-11-13 |  | 2024-11-27 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -512 | 0
112 | 32111502 | Vishay 1.7 (Dia.) x 3.9mm Simple BZX55C6 | 1101802159 | 1 | 2024-11-07 |  | 4800002712 | 4420 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 250 | 250 | 250 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6997806 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
113 | 32101629 | Amplificador operacional LF347N 3MHZ PDI | 1101802159 | 2 | 2024-11-07 |  | 4800002712 | 4430 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6610473P |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
114 | 32121615 | Resistencia TE Connectivity, de 1k? &#17 | 1101802159 | 3 | 2024-11-07 |  | 4800002712 | 4440 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1251150P |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
115 | 32111511 | Diodo de conmutaci&#243;n, 1N4148, 300mA | 1101802159 | 4 | 2024-11-07 |  | 4800002712 | 4450 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 2000 | 2000 | 2000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8428002 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 2000 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
116 | 32111504 | Diodo, GI754-E3/54, 6A, 400V Conexi&#243 | 1101802159 | 5 | 2024-11-07 |  | 4800002712 | 4460 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 40 | 40 | 40 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7088016P |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
117 | 32121505 | Condensador electrol&#237;tico Panasonic | 1101802159 | 6 | 2024-11-07 |  | 4800002712 | 4470 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 40 | 40 | 40 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3150619P |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
118 | 15121905 | Pasta t&#233;rmica con &#243;xido met&#2 | 1101802185 | 1 | 2024-11-07 |  | 4800002712 | 4490 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0554311 |  | 0 | 0 |  | 7218¦JA2593_1001 | 4 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
119 | 55121612 | PK20 ETQ LSR 210X297 METAL APLI 10071 | 1101802192 | 1 | 2024-11-07 |  | 4800002711 | 860 | 2024-11-04 |  |  | 2024-11-08 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 3048879 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 4 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -531 | 0
120 | 43223306 | Bandeja en rack con ventilaci&#243;n 1U | 1101802534 | 1 | 2024-11-08 |  | 4800002712 | 4770 | 2024-11-04 |  |  | 2024-11-09 | 0 | 0 |  | 8 | 8 | 8 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1863002 |  | 0 | 0 |  | 7218¦JA2583_1001 | 5 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -530 | 0
121 | 32121609 | Resistencia TE Connectivity, de 2k? &#17 | 1101802542 | 1 | 2024-11-08 |  | 4800002712 | 4780 | 2024-11-04 |  |  | 2024-11-09 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1251200 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -530 | 0
122 | 24141501 | Pel&#237;cula para protecci&#243;n contr | 1101802755 | 1 | 2024-11-08 |  | 4800002712 | 5040 | 2024-11-04 |  |  | 2024-11-09 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8157012 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -530 | 0
123 | 39121723 | Tubo termorretr&#225;ctil TE Connectivit | 1101803073 | 1 | 2024-11-11 |  | 4800002726 | 60 | 2024-11-10 |  |  | 2024-11-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2777960 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -527 | 0
124 | 39121723 | Tubo termorretr&#225;ctil TE Connectivit | 1101803073 | 2 | 2024-11-11 |  | 4800002726 | 70 | 2024-11-10 |  |  | 2024-11-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2777960 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -527 | 0
125 | 39121412 | Carcasa de conector circular Amphenol Li | 1101803108 | 1 | 2024-11-11 |  | 4800002726 | 100 | 2024-11-10 |  |  | 2024-11-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067532 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -527 | 0
126 | 39121723 | Tubo termorretr&#225;ctil TE Connectivit | 1101803543 | 1 | 2024-11-12 |  | 4800002726 | 1360 | 2024-11-10 |  |  | 2024-11-13 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2885241 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -526 | 0
127 | 39121412 | Carcasa de conector circular Amphenol Li | 1101803543 | 2 | 2024-11-12 |  | 4800002726 | 1370 | 2024-11-10 |  |  | 2024-11-13 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067523 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -526 | 0
128 | 39121412 | Carcasa de conector circular Amphenol Li | 1101803543 | 3 | 2024-11-12 |  | 4800002726 | 1380 | 2024-11-10 |  |  | 2024-11-13 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067532 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -526 | 0
129 | 39121412 | Carcasa de conector circular Amphenol M8 | 1101803543 | 4 | 2024-11-12 |  | 4800002726 | 1390 | 2024-11-10 |  |  | 2024-11-13 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067519 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -526 | 0
130 | 39121432 | Puntera hueca de crimpado RS PRO, Aislad | 1101804761 | 1 | 2024-11-14 |  | 4800002726 | 3420 | 2024-11-10 |  |  | 2024-11-15 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1787320 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -524 | 0
131 | 43211609 | Cable USB 2.0 StarTech.com, con A. USB C | 1101804766 | 1 | 2024-11-14 |  | 4800002726 | 3440 | 2024-11-10 |  |  | 2024-11-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1863229 |  | 0 | 0 |  | 7218¦JA2588_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -524 | 0
132 | 43202222 | Cable VGA StarTech.com de color Negro, c | 1101804766 | 2 | 2024-11-14 |  | 4800002726 | 3450 | 2024-11-10 |  |  | 2024-11-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1861667 |  | 0 | 0 |  | 7218¦JA2588_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -524 | 0
133 | 43211617 | Cable USB 2.0 StarTech.com, con A. USB A | 1101804766 | 3 | 2024-11-14 |  | 4800002726 | 3460 | 2024-11-10 |  |  | 2024-11-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1863178 |  | 0 | 0 |  | 7218¦JA2588_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -524 | 0
134 | 43211617 | Cable USB 2.0 StarTech.com, con A. USB A | 1101804766 | 4 | 2024-11-14 |  | 4800002726 | 3470 | 2024-11-10 |  |  | 2024-11-15 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1863187 |  | 0 | 0 |  | 7218¦JA2588_1001 | 5 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -524 | 0
135 | 26121639 | Cable de datos apantallado TE Connectivi | 1101805339 | 1 | 2024-11-15 |  | 4800002726 | 4800 | 2024-11-10 |  |  | 2024-11-16 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0362572 |  | 0 | 0 |  | 7218¦JA2593_1001 | 6 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -523 | 0
136 | 39121432 | Contacto de crimpado hembra Molex serie | 1101805339 | 2 | 2024-11-15 |  | 4800002726 | 4810 | 2024-11-10 |  |  | 2024-11-16 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6706293 |  | 0 | 0 |  | 7218¦JA2593_1001 | 6 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -523 | 0
137 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101805413 | 1 | 2024-11-15 |  | 4200586752 | 30 | 2024-11-21 | 2024-11-21 |  | 2024-12-20 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 29 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -489 | 0
138 | 31161807 | Arandelas Galvanizado brillante, Acero, | 1101806430 | 1 | 2024-11-19 |  | 4800002733 | 1340 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0560338 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
139 | 31161801 | Arandela a prueba de vibraciones Galvani | 1101806430 | 2 | 2024-11-19 |  | 4800002733 | 1350 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0526574 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
140 | 31161727 | Tuerca hexagonal M3 RS PRO de acero Galv | 1101806430 | 3 | 2024-11-19 |  | 4800002733 | 1360 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0560293 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
141 | 32121508 | Condensador de t&#225;ntalo Vishay 489D4 | 1101806430 | 4 | 2024-11-19 |  | 4800002733 | 1370 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 30 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6844389 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
142 | 32121701 | Diodo, 1N4004-E3/54, 1A, 400V Conexi&#24 | 1101806430 | 5 | 2024-11-19 |  | 4800002733 | 1380 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6289029 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
143 | 32121615 | Resistencia RS PRO, de 5.1k? &#177;5%, 0 | 1101806430 | 6 | 2024-11-19 |  | 4800002733 | 1390 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 5000 | 5000 | 5000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7397512 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 5000 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
144 | 32121607 | Matriz de resistencias Bourns, 4.7k?, &# | 1101806430 | 7 | 2024-11-19 |  | 4800002733 | 1400 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 25 | 25 | 25 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5224015 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
145 | 32121615 | Resistencia RS PRO, de 27k? &#177;5%, 0. | 1101806430 | 8 | 2024-11-19 |  | 4800002733 | 1410 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 5000 | 5000 | 5000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7397575 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 5000 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
146 | 32121618 | Resistencia TE Connectivity, de 13k? &#1 | 1101806430 | 9 | 2024-11-19 |  | 4800002733 | 1420 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7550870 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
147 | 32121616 | Potenci&#243;metro para PCB Bourns serie | 1101806430 | 10 | 2024-11-19 |  | 4800002733 | 1430 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 6 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5219287 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
148 | 32121615 | Resistencia RS PRO, de 33k? &#177;5%, 0. | 1101806430 | 11 | 2024-11-19 |  | 4800002733 | 1440 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7077789 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
149 | 32131006 | Z&#243;calo DIL Preci-Dip, paso de 2.54m | 1101806430 | 12 | 2024-11-19 |  | 4800002733 | 1450 | 2024-11-15 |  |  | 2024-11-20 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7020676 |  | 0 | 0 |  | 7218¦JA2593_1001 | 5 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -519 | 0
150 | 1807990092800 | PIEZA RECORTADA ADH GANCHO 25X25MM NEGRO | 1101806908 | 1 | 2024-11-19 |  | 4200594733 | 10 | 2025-01-27 | 2025-01-27 |  | 2025-02-03 | 61 | 8 | Liberado | 6 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | VELCRO | EB51025330118476 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -444 | 0 |  | X
151 | 1807990092800 | PIEZA RECORTADA ADH GANCHO 25X25MM NEGRO | 1101806908 | 1 | 2024-11-19 |  | 4200604976 | 10 | 2025-03-31 | 2025-04-01 |  | 2025-04-04 | 61 | 8 | Liberado | 6 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | VELCRO | EB51025330118476 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 4 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -384 | 0 |  | X
152 | 1232525308000 | CINT ADH ESPUM ACR VHB 4930P 30MM 33M BL | 1101806908 | 2 | 2024-11-19 |  | 4200594733 | 20 | 2025-01-27 | 2025-01-27 |  | 2025-02-03 | 40 | 8 | Liberado | 165 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | 3M | 4930P/30MM |  | 0 | 0 |  | 7218¦S24B05_P10253 | 7 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -444 | 0 |  | X
153 | 1805710000000 | IMPRIMACION 94 AMBAR APROX 6% SOLIDOS | 1101806908 | 3 | 2024-11-19 |  | 4200594733 | 30 | 2025-01-27 | 2025-01-27 |  | 2025-02-03 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | 3M | 70-0160-5477-0 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 7 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -444 | 0
154 | 7854800130000 | BROCHA PEQ PINTURA PLANA 25MM | 1101806908 | 4 | 2024-11-19 |  | 4200592492 | 20 | 2025-01-09 | 2025-01-10 |  | 2025-02-14 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | FERRETERIA FERAYU SL | HENKEL CORP. | 799 299 003 |  | 1 | 1 |  | 7218¦S24B05_P10253 | 36 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -433 | 0
155 | 1802500600000 | MASILLA UNIVERSAL RELLENO DUAL | 1101806908 | 5 | 2024-11-19 |  | 4200594733 | 40 | 2025-01-27 | 2025-01-27 |  | 2025-02-03 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | KRAFFT | 14524 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -444 | 0
156 | 1800700500000 | ADH METACRILATO 2C ARALDITE 2021-1 50ML | 1101806908 | 6 | 2024-11-19 |  | 4200594733 | 50 | 2025-01-27 | 2025-01-27 |  | 2025-02-03 | 30 | 8 | Liberado | 1 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | HUNTSMAN | 4746608 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 7 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -444 | 0
157 | 1800600900000 | ADHESIVO CONTACTO TEROKAL 2444 | 1101806908 | 7 | 2024-11-19 |  | 4200594106 | 10 | 2025-01-22 | 2025-01-22 |  | 2025-02-03 | 90 | 8 | Liberado | 2 | 340 | 1020 | 0 | 340 | 680 | X | 0.00 |  | Technipol Suministros, S.L. | HENKEL CORP. | 238403 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 12 | - |  | YES | 1020 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -444 | 0
158 | 1232525506900 | CINTA ADH 50MM 390UM 7.5N/CM BLANC TEJID | 1101806908 | 8 | 2024-11-19 |  | 4200588735 | 10 | 2024-12-05 | 2024-12-10 |  | 2025-01-13 | 30 | 8 | Liberado | 1 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | TESA | 4964 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 39 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -465 | 0
159 | 39121415 | Conector macho para PCB Molex serie SL d | 1101807103 | 1 | 2024-11-20 |  | 4800002736 | 380 | 2024-11-19 |  |  | 2024-11-21 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6700835 |  | 0 | 0 |  | 7218¦JA2583_1001 | 2 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -518 | 0
160 | 39121415 | Conector macho para PCB Molex serie SL d | 1101807103 | 2 | 2024-11-20 |  | 4800002736 | 390 | 2024-11-19 |  |  | 2024-11-21 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6792499 |  | 0 | 0 |  | 7218¦JA2583_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -518 | 0
161 | 39121402 | Punto de toma de tierra para rack para p | 1101807400 | 1 | 2024-11-20 |  | 4800002736 | 700 | 2024-11-19 |  |  | 2024-11-21 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0392141 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -518 | 0
162 | 39121708 | Carril DIN Perforado de Acero Phoenix Co | 1101807400 | 2 | 2024-11-20 |  | 4800002736 | 710 | 2024-11-19 |  |  | 2024-11-21 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6485738 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -518 | 0
163 | 32000000 | Placa de Cierre APC, 483 x 45 x 28mm | 1101807410 | 1 | 2024-11-20 |  | 4800002736 | 720 | 2024-11-19 |  |  | 2024-11-21 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7794070 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -518 | 0
164 | 39121415 | Conector D-sub FCT from Molex, Serie FL, | 1101807607 | 1 | 2024-11-21 |  | 4800002739 | 130 | 2024-11-20 |  |  | 2024-11-22 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8126368 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
165 | 39121402 | Toma Kopp de 2P de color Negro, para Eur | 1101807607 | 2 | 2024-11-21 |  | 4800002739 | 140 | 2024-11-20 |  |  | 2024-11-22 | 0 | 0 |  | 13 | 13 | 13 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425811 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 13 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
166 | 32000000 | Placa de Cierre APC, 483 x 45 x 28mm | 1101807610 | 1 | 2024-11-21 |  | 4800002739 | 160 | 2024-11-20 |  |  | 2024-11-22 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7794070 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
167 |  | MONTAJE SIMULADOR A320 | 1101807791 | 1 | 2024-11-21 |  | 4300335965 | 10 | 2024-11-25 | 2024-11-27 |  | 2024-12-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 19 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -495 | 0
168 | 39121723 | Tubo termorretr&#225;ctil HellermannTyto | 1101807940 | 1 | 2024-11-21 |  | 4800002739 | 490 | 2024-11-20 |  |  | 2024-11-22 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1331782 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
169 | 39121723 | Tubo termorretr&#225;ctil HellermannTyto | 1101807940 | 2 | 2024-11-21 |  | 4800002739 | 500 | 2024-11-20 |  |  | 2024-11-22 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1331780 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
170 | 39121321 | Juego de tornillos Rittal serie EL, para | 1101808178 | 1 | 2024-11-22 |  | 4800002739 | 820 | 2024-11-20 |  |  | 2024-11-23 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8262903 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -516 | 0
171 | 32000000 | Tuerca en jaula nVent SCHROFF 21100-003 | 1101808178 | 2 | 2024-11-22 |  | 4800002739 | 830 | 2024-11-20 |  |  | 2024-11-23 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2457843 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -516 | 0
172 | 39121321 | Earth Bar Rittal 7113000 | 1101808178 | 3 | 2024-11-22 |  | 4800002739 | 840 | 2024-11-20 |  |  | 2024-11-23 | 0 | 0 |  | 8 | 8 | 8 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8262868 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -516 | 0
173 | 39121413 | Protecci&#243;n contra tirones Plateado | 1101808334 | 1 | 2024-11-22 |  | 4800002740 | 350 | 2024-11-22 |  |  | 2024-11-23 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2614993 |  | 0 | 0 |  | 7218¦JA2586_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -516 | 0
174 | 39121413 | Conector circular Amphenol Limited Conec | 1101808337 | 1 | 2024-11-22 |  | 4800002740 | 360 | 2024-11-22 |  |  | 2024-11-23 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368153 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -516 | 0
175 | 39121413 | Protecci&#243;n contra tirones Plateado | 1101808337 | 2 | 2024-11-22 |  | 4800002740 | 370 | 2024-11-22 |  |  | 2024-11-23 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2614964 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -516 | 0
176 |  | ADAPTACIÓN DEL BASEFRAME | 1101809006 | 1 | 2024-11-25 |  | 4300336226 | 10 | 2024-11-28 | 2024-11-29 |  | 2024-12-24 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | TALLERES XUQUER, SL |  |  |  | 0 | 0 |  | 7218¦JA2580_1001 | 26 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -485 | 0
177 |  | PUESTA A PUNTO/EN SERVICIO SIMULACION | 1101810000 | 1 | 2024-11-27 |  | 4300336149 | 10 | 2024-11-27 | 2025-02-14 |  | 2024-12-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2582_1001 | 33 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -479 | 0
178 | 39121412 | Carcasa de conector circular Amphenol Li | 1101810008 | 1 | 2024-11-27 |  | 4800002747 | 450 | 2024-11-26 |  |  | 2024-11-28 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067562 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -511 | 0
179 | 39121412 | Carcasa de conector circular Amphenol M8 | 1101810012 | 1 | 2024-11-27 |  | 4800002747 | 460 | 2024-11-26 |  |  | 2024-11-28 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067519 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -511 | 0
180 | 39121402 | Toma Kopp de 2P de color Negro, para Eur | 1101810025 | 1 | 2024-11-27 |  | 4800002747 | 470 | 2024-11-26 |  |  | 2024-11-28 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425811 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -511 | 0
181 | 39121402 | Toma Kopp de 2P de color Negro, para Eur | 1101810025 | 2 | 2024-11-27 |  | 4800002747 | 480 | 2024-11-26 |  |  | 2024-11-28 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425811 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -511 | 0
182 | 39121413 | Protecci&#243;n contra tirones Plateado | 1101810045 | 1 | 2024-11-27 |  | 4800002747 | 530 | 2024-11-26 |  |  | 2024-11-28 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2614993 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -511 | 0
183 | 39121413 | Protecci&#243;n contra tirones Plateado | 1101810070 | 1 | 2024-11-27 |  | 4800002747 | 590 | 2024-11-26 |  |  | 2024-11-28 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2614993 |  | 0 | 0 |  | 7218¦JA2586_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -511 | 0
184 | 32000000 | Conector circular MIL-C-38999 serie III | 1101810502 | 1 | 2024-11-28 |  | 4800002749 | 190 | 2024-11-27 |  |  | 2024-11-29 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804851 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
185 | 32000000 | Conector circular MIL-C-38999 serie III | 1101810502 | 2 | 2024-11-28 |  | 4800002749 | 200 | 2024-11-27 |  |  | 2024-11-29 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804922 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
186 | 26121629 | Cable de alimentaci&#243;n RS PRO Negro | 1101810502 | 3 | 2024-11-28 |  | 4800002749 | 210 | 2024-11-27 |  |  | 2024-11-29 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0487277 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
187 | 39121415 | Conector macho para PCB Molex serie SL d | 1101810566 | 1 | 2024-11-28 |  | 4800002749 | 240 | 2024-11-27 |  |  | 2024-11-29 | 0 | 0 |  | 15 | 15 | 15 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6700835 |  | 0 | 0 |  | 7218¦JA2583_1001 | 2 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
188 | 39121415 | Conector macho para PCB Molex serie SL d | 1101810566 | 2 | 2024-11-28 |  | 4800002749 | 250 | 2024-11-27 |  |  | 2024-11-29 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6792499 |  | 0 | 0 |  | 7218¦JA2583_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
189 | 39121415 | Conector macho para PCB Molex serie SL d | 1101810754 | 1 | 2024-11-28 |  | 4800002750 | 390 | 2024-11-28 |  |  | 2024-11-29 | 0 | 0 |  | 25 | 25 | 25 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6700835 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
190 | 39121415 | Conector macho para PCB Molex serie SL d | 1101810754 | 2 | 2024-11-28 |  | 4800002750 | 400 | 2024-11-28 |  |  | 2024-11-29 | 0 | 0 |  | 30 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6792499 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
191 | 39121412 | Carcasa de conector circular Amphenol M8 | 1101810754 | 3 | 2024-11-28 |  | 4800002750 | 410 | 2024-11-28 |  |  | 2024-11-29 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067519 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
192 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101812059 | 1 | 2024-12-03 |  | 4200589052 | 60 | 2024-12-09 | 2024-12-10 |  | 2024-12-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -482 | 0
193 | 39121432 | Terminal de leng&#252;eta hembra TE Conn | 1101812703 | 1 | 2024-12-04 |  | 4800002762 | 1060 | 2024-12-03 |  |  | 2024-12-05 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7197145 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -504 | 0
194 | 39121432 | Terminal de leng&#252;eta hembra TE Conn | 1101812709 | 1 | 2024-12-04 |  | 4800002762 | 1080 | 2024-12-03 |  |  | 2024-12-05 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7197145 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -504 | 0
195 | 39121413 | Protecci&#243;n contra tirones Plateado | 1101812778 | 1 | 2024-12-04 |  | 4800002769 | 10 | 2024-12-04 |  |  | 2024-12-05 | 0 | 0 |  | 9 | 9 | 9 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2614993 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -504 | 0
196 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101812930 | 1 | 2024-12-04 |  | 4200589452 | 20 | 2024-12-10 | 2024-12-11 |  | 2024-12-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -486 | 0
197 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101813294 | 1 | 2024-12-05 |  | 4200589622 | 10 | 2024-12-11 | 2024-12-12 |  | 2024-12-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -482 | 0
198 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101813297 | 1 | 2024-12-05 |  | 4200589622 | 20 | 2024-12-11 | 2024-12-12 |  | 2024-12-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -482 | 0
199 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101813301 | 1 | 2024-12-05 |  | 4200589622 | 30 | 2024-12-11 | 2024-12-12 |  | 2024-12-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -482 | 0
200 | 55121612 | PK20 ETQ POLIEST 210X297 BCO APLI 1228 | 1101813317 | 1 | 2024-12-05 |  | 4800002758 | 490 | 2024-12-02 |  |  | 2024-12-06 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 993226 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 4 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -503 | 0
201 | 39121404 | Manguitos de soldadura, TE Connectivity, | 1101813568 | 1 | 2024-12-05 |  | 4800002774 | 90 | 2024-12-05 |  |  | 2024-12-06 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2652726 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -503 | 0
202 | 1251000380100 | MICROFONO PRESION 1/2” 3.5HZ-20KHZ CCP | 1101813963 | 1 | 2024-12-09 |  | 4200590224 | 20 | 2024-12-16 | 2024-12-17 |  | 2025-01-07 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SOUND OF NUMBERS SL | GRAS SOUND & VIBRATI | 46AO |  | 1 | 1 |  | 7218¦S24B05_S1077 | 22 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -471 | 0
203 | 1263011992600 | F.A. CCP 2XAA/3-6VDC 28V 4MA BNC | 1101813963 | 2 | 2024-12-09 |  | 4200590458 | 10 | 2024-12-17 | 2024-12-17 |  | 2025-01-31 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | GRAS SOUND & VIBRATI | 12AL |  | 1 | 0 |  | 7218¦S24B05_S1077 | 45 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -447 | 0
204 | 1229502470000 | CBL EQ EXTENSION CCP BNC-BNC 50R L=3M | 1101813963 | 3 | 2024-12-09 |  | 4200590682 | 30 | 2024-12-18 | 2025-01-20 |  | 2025-01-20 | 70 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | GRAS SOUND & VIBRATI | AA0035 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 33 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -458 | 0
205 | 7279902131200 | CALIBRADOR ACUSTICO 94-114DB 1KHZ | 1101813963 | 4 | 2024-12-09 |  | 4200589922 | 10 | 2024-12-12 | 2024-12-12 |  | 2025-01-15 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | GRAS SOUND & VIBRATI | 42AG |  | 0 | 0 |  | 7218¦S24B05_S1077 | 34 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -463 | 0
206 | 7279902131290 | ACC ADAPT CALIBRADOR/PREAMPLIFICADOR XLR | 1101813963 | 5 | 2024-12-09 |  | 4200589922 | 20 | 2024-12-12 | 2024-12-12 |  | 2025-01-15 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | GRAS SOUND & VIBRATI | AG0003 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 34 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -463 | 0
207 | 1589903549000 | ADAPT P/MICRO 1/2-1/4 CAB GIR P/TRIP 1/4 | 1101813963 | 6 | 2024-12-09 |  | 4200590228 | 20 | 2024-12-16 | 2024-12-17 |  | 2024-12-27 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | GRAS SOUND & VIBRATI | AL0003 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -482 | 0
208 | 1589991012301 | ANCLAJE 16MM HEX M5 1/4" P/13-55MM NE | 1101813963 | 7 | 2024-12-09 |  | 4200590231 | 20 | 2024-12-16 | 2024-12-17 |  | 2024-12-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MANFROTTO | MAN035 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -486 | 0
209 | 1589991012400 | PASADOR CORTO REV M/M 3/8"-1/4" BRONCE | 1101813963 | 8 | 2024-12-09 |  | 4200590231 | 40 | 2024-12-16 | 2024-12-17 |  | 2024-12-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MANFROTTO | MAN037 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -486 | 0
210 | 39121410 | Borne de conexi&#243;n HellermannTyton d | 1101814995 | 1 | 2024-12-11 |  | 4800002778 | 490 | 2024-12-10 |  |  | 2024-12-12 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2517660 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -497 | 0
211 | 39121400 | Conector XLR Macho de 3 pines Neutrik, c | 1101814997 | 1 | 2024-12-11 |  | 4800002778 | 500 | 2024-12-10 |  |  | 2024-12-12 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0405607 |  | 0 | 0 |  | 7218¦JA2584_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -497 | 0
212 | 39121410 | Soporte final RS PRO, para usar con CDK, | 1101814998 | 1 | 2024-12-11 |  | 4800002778 | 510 | 2024-12-10 |  |  | 2024-12-12 | 0 | 0 |  | 30 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8787556 |  | 0 | 0 |  | 7218¦JA2588_1001 | 2 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -497 | 0
213 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101815034 | 1 | 2024-12-11 |  | 4200590773 | 20 | 2024-12-18 | 2024-12-19 |  | 2024-12-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -478 | 0
214 | 39121412 | Carcasa de conector circular Amphenol Li | 1101815999 | 1 | 2024-12-12 |  | 4800002780 | 210 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2259365 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
215 | 39121412 | Carcasa de conector circular Amphenol Li | 1101815999 | 2 | 2024-12-12 |  | 4800002780 | 220 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067529 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
216 | 39121413 | Conector circular Amphenol Limited Conec | 1101815999 | 3 | 2024-12-12 |  | 4800002780 | 230 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368090 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
217 | 39121017 | Unidad de distribuci&#243;n de potencia | 1101816002 | 1 | 2024-12-12 |  | 4800002780 | 240 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1237430 |  | 0 | 0 |  | 7218¦JA2580_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
218 | 31161816 | Separador roscado hexagonal Macho/Hembra | 1101816005 | 1 | 2024-12-12 |  | 4800002780 | 260 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 400 | 400 | 400 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2808985 |  | 0 | 0 |  | 7218¦JA2583_1001 | 2 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
219 | 39121321 | Tuerca en jaula Rittal 2094200 Acero M6 | 1101816005 | 2 | 2024-12-12 |  | 4800002780 | 270 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 150 | 150 | 150 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8262906 |  | 0 | 0 |  | 7218¦JA2583_1001 | 2 | - |  | YES | 150 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
220 | 39121412 | Carcasa de conector circular Amphenol Li | 1101816014 | 1 | 2024-12-12 |  | 4800002780 | 330 | 2024-12-11 |  |  | 2024-12-13 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2259358 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
221 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101816196 | 1 | 2024-12-12 |  | 4200591157 | 40 | 2024-12-19 | 2024-12-19 |  | 2025-01-15 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 27 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -463 | 0
222 | 26121636 | Cable de alimentaci&#243;n RS PRO Negro | 1101816380 | 1 | 2024-12-12 |  | 4800002782 | 220 | 2024-12-12 |  |  | 2024-12-13 | 0 | 0 |  | 15 | 15 | 15 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1789806 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
223 | 39121412 | Carcasa de conector circular Amphenol Li | 1101816438 | 1 | 2024-12-12 |  | 4800002783 | 180 | 2024-12-12 |  |  | 2024-12-13 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067523 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
224 | 39121402 | Toma Kopp de 2P de color Negro, para Eur | 1101816438 | 2 | 2024-12-12 |  | 4800002783 | 190 | 2024-12-12 |  |  | 2024-12-13 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425811 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
225 | 39121432 | Contacto del conector circular Amphenol | 1101816438 | 3 | 2024-12-12 |  | 4800002783 | 200 | 2024-12-12 |  |  | 2024-12-13 | 0 | 0 |  | 400 | 400 | 400 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6918897 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
226 | 39121432 | Terminal de leng&#252;eta hembra TE Conn | 1101816438 | 4 | 2024-12-12 |  | 4800002783 | 210 | 2024-12-12 |  |  | 2024-12-13 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7197145 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -496 | 0
227 | 39121413 | Conector circular Amphenol Limited Conec | 1101816944 | 1 | 2024-12-13 |  | 4800002784 | 450 | 2024-12-12 |  |  | 2024-12-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368158 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -495 | 0
228 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101817454 | 1 | 2024-12-16 |  | 4200591887 | 20 | 2025-01-02 | 2025-01-08 |  | 2025-01-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -461 | 0
229 | 43211609 | USB C to DisplayPort Adapter - 8K/5K/4K | 1101817910 | 1 | 2024-12-17 |  | 4800002788 | 40 | 2024-12-17 |  |  | 2024-12-18 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2133167 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -491 | 0
230 | 26121522 | Cable para Entornos Hostiles TE Connecti | 1101817997 | 1 | 2024-12-17 |  | 4800002788 | 200 | 2024-12-17 |  |  | 2024-12-18 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2291422 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -491 | 0
231 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101818117 | 1 | 2024-12-17 |  | 4200591966 | 10 | 2025-01-03 | 2025-01-10 |  | 2025-01-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -461 | 0
232 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101818117 | 2 | 2024-12-17 |  | 4200591966 | 20 | 2025-01-03 | 2025-01-10 |  | 2025-01-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -461 | 0
233 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101818117 | 3 | 2024-12-17 |  | 4200591966 | 30 | 2025-01-03 | 2025-01-10 |  | 2025-01-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -461 | 0
234 | 39121431 | Tap&#243;n ciego para prensaestopas RS P | 1101818562 | 1 | 2024-12-18 |  | 4800002788 | 770 | 2024-12-17 |  |  | 2024-12-19 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8178855 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
235 | 39121029 | Transformador de montaje en chasis RS PR | 1101818562 | 2 | 2024-12-18 |  | 4800002788 | 780 | 2024-12-17 |  |  | 2024-12-19 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0504313 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
236 | 26121636 | Cable de alimentaci&#243;n RS PRO Negro | 1101818684 | 1 | 2024-12-18 |  | 4800002790 | 10 | 2024-12-18 |  |  | 2024-12-19 | 0 | 0 |  | 15 | 15 | 15 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1789806 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
237 | 27113204 | Herramienta de extracci&#243;n Molex 11- | 1101818694 | 1 | 2024-12-18 |  | 4800002790 | 20 | 2024-12-18 |  |  | 2024-12-19 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2155900 |  | 0 | 0 |  | 7218¦JA2592_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
238 | 39121413 | Conector circular Amphenol Limited Conec | 1101818821 | 1 | 2024-12-18 |  | 4800002790 | 150 | 2024-12-18 |  |  | 2024-12-19 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368090 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
239 | 31161816 | Separador roscado hexagonal Macho/Hembra | 1101818821 | 2 | 2024-12-18 |  | 4800002790 | 160 | 2024-12-18 |  |  | 2024-12-19 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2808985 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
240 | 39121412 | Carcasa de conector circular Amphenol Li | 1101818821 | 3 | 2024-12-18 |  | 4800002790 | 170 | 2024-12-18 |  |  | 2024-12-19 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067529 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -490 | 0
241 | 39121708 | Carril DIN Sin perforar de Acero Phoenix | 1101819705 | 1 | 2024-12-20 |  | 4800002796 | 70 | 2024-12-19 |  |  | 2024-12-21 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8039609 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -488 | 0
242 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101819790 | 1 | 2024-12-20 |  | 4200592399 | 10 | 2025-01-09 | 2025-01-10 |  | 2025-01-24 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -454 | 0
243 |  | AMPLIACIÓN DDP_03-DISEÑO Y SIM.MECÁNICA | 1101821545 | 1 | 2025-01-07 |  | 4300338740 | 10 | 2025-01-16 | 2025-03-28 |  | 2025-08-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 3566.08 |  | RDT INGENIEROS MADRID, S.L. |  |  |  | 1 | 1 |  | 7218¦S24B05_P10261 | 226 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -236 | 0
244 |  | MONTAJE SIMULADOR A320 | 1101821694 | 1 | 2025-01-07 |  | 4300338521 | 20 | 2025-01-13 | 2025-01-16 |  | 2025-01-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 17 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -448 | 0
245 |  | MONTAJE SIMULADOR A320 | 1101821698 | 1 | 2025-01-07 |  | 4300338521 | 30 | 2025-01-13 | 2025-01-16 |  | 2025-01-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 17 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -448 | 0
246 |  | COSLADA MONTAJE SIMULADOR A320 | 1101821730 | 1 | 2025-01-07 |  | 4300338537 | 20 | 2025-01-13 | 2025-01-20 |  | 2025-01-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | ISC Instalaciones y Servicios de |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 17 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -448 | 0
247 |  | MONTAJE SIMULADOR A320 | 1101821760 | 1 | 2025-01-07 |  | 4300338520 | 30 | 2025-01-13 | 2025-01-13 |  | 2025-01-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | TALLERES SANTIAGO DATO, S.L.U. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 17 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -448 | 0
248 | 39121708 | Carril DIN Perforado RS PRO, dim. 2m x 3 | 1101822039 | 1 | 2025-01-08 |  | 4800002802 | 380 | 2025-01-07 |  |  | 2025-01-09 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2258315 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -469 | 0
249 | 39121708 | Tapa Phoenix Contact serie D-ST, para us | 1101823384 | 1 | 2025-01-13 |  | 4800002813 | 60 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3884637 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
250 | 26121616 | Cable telef&#243;nico Decelect, 2 pares, | 1101823384 | 2 | 2025-01-13 |  | 4800002813 | 70 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5185667 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
251 | 39121432 | Terminal redondo aislado de Cobre TE Con | 1101823384 | 3 | 2025-01-13 |  | 4800002813 | 80 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 4574000 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
252 | 39121432 | Terminal redondo aislado de Cobre RS PRO | 1101823384 | 4 | 2025-01-13 |  | 4800002813 | 90 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2673739 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
253 | 39121405 | Terminal redondo tubular no aislado de C | 1101823384 | 5 | 2025-01-13 |  | 4800002813 | 100 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0531071 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
254 | 39121412 | Carcasa de conector circular Amphenol Li | 1101823384 | 6 | 2025-01-13 |  | 4800002813 | 110 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067532 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
255 | 39121412 | Carcasa de conector circular Amphenol Li | 1101823384 | 7 | 2025-01-13 |  | 4800002813 | 120 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067529 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
256 | 39121412 | Carcasa de conector circular Amphenol Li | 1101823384 | 8 | 2025-01-13 |  | 4800002813 | 130 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067523 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
257 | 39121432 | Contacto del conector circular Amphenol | 1101823384 | 9 | 2025-01-13 |  | 4800002813 | 140 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6918897 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
258 | 39121324 | Caja de pared ABB SR2 Monobloc de Acero | 1101823384 | 10 | 2025-01-13 |  | 4800002813 | 150 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7685686 |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
259 | 32000000 | Conector circular MIL-C-38999 serie III | 1101823392 | 1 | 2025-01-13 |  | 4800002813 | 160 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804849 |  | 0 | 0 |  | 7218¦JA2583_1001 | 3 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
260 | 39121415 | Conector D-sub FCT from Molex, Serie FL, | 1101823431 | 1 | 2025-01-13 |  | 4800002813 | 180 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8126368 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
261 | 39121529 | Contactor Schneider Electric TeSys D LC1 | 1101823431 | 2 | 2025-01-13 |  | 4800002813 | 190 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7447535 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
262 | 39121603 | Interruptor autom&#225;tico 2P, 16A, Cur | 1101823431 | 3 | 2025-01-13 |  | 4800002813 | 200 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7349664 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
263 | 39121402 | Toma Kopp de 2P de color Negro, para Eur | 1101823436 | 1 | 2025-01-13 |  | 4800002813 | 210 | 2025-01-11 |  |  | 2025-01-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425811 |  | 0 | 0 |  | 7218¦JA2593_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -464 | 0
264 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101823928 | 1 | 2025-01-14 |  | 4200593528 | 40 | 2025-01-17 | 2025-01-17 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
265 |  | TRABAJOS SIMULADOR A320 | 1101824014 | 1 | 2025-01-14 |  | 4300338932 | 10 | 2025-01-20 | 2025-01-21 |  | 2025-02-06 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 17 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -441 | 0
266 | 43211503 | WD Elements Desktop WDBWLG0160HBK - Disc | 1101824064 | 1 | 2025-01-14 |  | 4800002811 | 300 | 2025-01-10 |  |  | 2025-01-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 6205759 |  | 0 | 0 |  | 7218¦JA2594_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -463 | 0
267 | 9999000981111 | N.R.TRANSFORMADOS DE CHAPA ESTÁNDAR | 1101824091 | 1 | 2025-01-14 |  | 4200593300 | 10 | 2025-01-16 | 2025-01-21 |  | 2025-02-14 | 120 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | CONSUEGRA SOC. COOP. LTD. |  |  |  | 0 | 0 |  | 7218¦JA2589_1001 | 29 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -433 | 0
268 | 39121412 | Carcasa de conector circular Amphenol Li | 1101824124 | 1 | 2025-01-14 |  | 4800002822 | 120 | 2025-01-14 |  |  | 2025-01-15 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2259368 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -463 | 0
269 | 26121609 | Cable Ethernet Cat6 U/UTP StarTech.com d | 1101824151 | 1 | 2025-01-14 |  | 4800002822 | 160 | 2025-01-14 |  |  | 2025-01-15 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1861994 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -463 | 0
270 | 31201523 | Cinta americana, Pel&#237;cula de PE con | 1101824256 | 1 | 2025-01-14 |  | 4800002822 | 210 | 2025-01-14 |  |  | 2025-01-15 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3731577 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 1 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -463 | 0
271 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101825214 | 1 | 2025-01-16 |  | 4200594187 | 10 | 2025-01-22 | 2025-01-23 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
272 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101825214 | 2 | 2025-01-16 |  | 4200594187 | 20 | 2025-01-22 | 2025-01-23 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
273 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101825214 | 3 | 2025-01-16 |  | 4200594187 | 30 | 2025-01-22 | 2025-01-23 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
274 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101825214 | 4 | 2025-01-16 |  | 4200594187 | 40 | 2025-01-22 | 2025-01-23 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
275 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101825218 | 1 | 2025-01-16 |  | 4200594187 | 50 | 2025-01-22 | 2025-01-23 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
276 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101825218 | 2 | 2025-01-16 |  | 4200594187 | 60 | 2025-01-22 | 2025-01-23 |  | 2025-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
277 | 44122025 | PK100 FUNDA MULTIT LYRECO A4 80 M TRS RG | 1101825252 | 1 | 2025-01-16 |  | 4800002798 | 1250 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 317868 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
278 | 44121703 | PLUMA DESECHABLE PILOT V-PEN AZL SPW4M-L | 1101825252 | 2 | 2025-01-16 |  | 4800002798 | 1260 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 2521151 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
279 | 44121708 | ROTUL PERM STAEDTLER LUMOCOL 0,4MM ROJO | 1101825252 | 3 | 2025-01-16 |  | 4800002798 | 1270 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 183103 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
280 | 44121708 | ROTUL PERM STAEDTLER LUMOCOL 0,4MM AZUL | 1101825252 | 4 | 2025-01-16 |  | 4800002798 | 1280 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 183091 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
281 | 14111530 | PK6 NOTAS LYRECO 76X76 COL SURTIDOS BRIL | 1101825252 | 5 | 2025-01-16 |  | 4800002798 | 1290 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 2515489 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
282 | 44122107 | CJ1000 GRAPAS LYRECO 24/6 GALVANIZADAS | 1101825252 | 6 | 2025-01-16 |  | 4800002798 | 1300 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 5002534 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
283 | 44122002 | S&#237; Funda disipativa de est&#225;tic | 1101825319 | 1 | 2025-01-16 |  | 4800002825 | 410 | 2025-01-15 |  |  | 2025-01-17 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0733952 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
284 | 44122025 | PK100 FUNDA MULTIT LYRECO A4 80 M TRS RG | 1101825324 | 1 | 2025-01-16 |  | 4800002798 | 1350 | 2025-01-02 |  |  | 2025-01-17 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 317868 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
285 | 39121402 | Toma Kopp de 2P de color Negro, para Eur | 1101825332 | 1 | 2025-01-16 |  | 4800002825 | 450 | 2025-01-15 |  |  | 2025-01-17 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425811 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
286 | 39121603 | Interruptor autom&#225;tico 2P, 16A, Cur | 1101825338 | 1 | 2025-01-16 |  | 4800002825 | 470 | 2025-01-15 |  |  | 2025-01-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7349664 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
287 | 11162114 | Cinta de gancho y bucle 3M SJ356D de col | 1101825338 | 2 | 2025-01-16 |  | 4800002825 | 480 | 2025-01-15 |  |  | 2025-01-17 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 4587337 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
288 | 31161735 | Tuerca en jaula RS PRO Hierro M6 | 1101825396 | 1 | 2025-01-16 |  | 4800002825 | 600 | 2025-01-15 |  |  | 2025-01-17 | 0 | 0 |  | 250 | 250 | 250 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2662268 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -461 | 0
289 | 39121321 | Juego de tornillos Rittal serie EL, para | 1101825869 | 1 | 2025-01-17 |  | 4800002831 | 250 | 2025-01-17 |  |  | 2025-01-18 | 0 | 0 |  | 150 | 150 | 150 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8262903 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 150 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -460 | 0
290 | 39121432 | Terminal redondo aislado de Cobre RS PRO | 1101825869 | 2 | 2025-01-17 |  | 4800002831 | 260 | 2025-01-17 |  |  | 2025-01-18 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2673880 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -460 | 0
291 | 26121630 | Capuch&#243;n termoretr&#225;ctil TE Con | 1101825869 | 3 | 2025-01-17 |  | 4800002831 | 270 | 2025-01-17 |  |  | 2025-01-18 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8741500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -460 | 0
292 | 26121522 | Cable para Entornos Hostiles TE Connecti | 1101825905 | 1 | 2025-01-17 |  | 4800002831 | 290 | 2025-01-17 |  |  | 2025-01-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2291416 |  | 0 | 0 |  | 7218¦JA2594_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -460 | 0
293 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101826509 | 1 | 2025-01-20 |  | 4200594781 | 10 | 2025-01-27 | 2025-01-27 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
294 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101826509 | 2 | 2025-01-20 |  | 4200594781 | 20 | 2025-01-27 | 2025-01-27 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
295 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101826509 | 3 | 2025-01-20 |  | 4200594781 | 30 | 2025-01-27 | 2025-01-27 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
296 | 39121321 | Carpeta de documentos Schneider Electric | 1101826924 | 1 | 2025-01-21 |  | 4800002836 | 360 | 2025-01-20 |  |  | 2025-01-22 | 0 | 0 |  | 18 | 18 | 18 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6899780 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 2 | - |  | YES | 18 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -456 | 0
297 |  | MONTAJE SIMULADOR A320 | 1101826992 | 1 | 2025-01-21 |  | 4400085683 | 10 | 2025-01-21 | 2025-01-21 |  | 2025-02-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | APLICACIONES DE SIMULACION |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 24 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -433 | 0
298 |  | TRABAJOS SIMULADOR A320 | 1101827012 | 1 | 2025-01-21 |  | 4300339244 | 10 | 2025-01-23 | 2025-01-29 |  | 2025-02-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | TALLERES SANTIAGO DATO, S.L.U. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 22 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -433 | 0
299 | 24112003 | Gaveta RS PRO, Rojo de Cart&#243;n, 100m | 1101827598 | 1 | 2025-01-22 |  | 4800002838 | 260 | 2025-01-21 |  |  | 2025-01-23 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2281065 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -455 | 0
300 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101828001 | 1 | 2025-01-22 |  | 4200595284 | 100 | 2025-01-29 | 2025-01-30 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 12 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
301 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101828001 | 2 | 2025-01-22 |  | 4200595284 | 110 | 2025-01-29 | 2025-01-30 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 12 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
302 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101828001 | 3 | 2025-01-22 |  | 4200595284 | 120 | 2025-01-29 | 2025-01-30 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 12 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
303 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101828001 | 4 | 2025-01-22 |  | 4200595284 | 130 | 2025-01-29 | 2025-01-30 |  | 2025-02-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 12 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -437 | 0
304 | 32111502 | Vishay 1.7 (Dia.) x 3.9mm Simple BZX55C6 | 1101828411 | 1 | 2025-01-23 |  | 4800002840 | 580 | 2025-01-22 |  |  | 2025-01-24 | 0 | 0 |  | 250 | 250 | 250 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6997806 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
305 | 31201623 | Adhesivo de contacto Teroson Terokal 244 | 1101828417 | 1 | 2025-01-23 |  | 4800002840 | 600 | 2025-01-22 |  |  | 2025-01-24 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5246059 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
306 | 32121506 | Condensador cer&#225;mico multicapa MLCC | 1101828476 | 1 | 2025-01-23 |  | 4800002841 | 30 | 2025-01-23 |  |  | 2025-01-24 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6994920 |  | 0 | 0 |  | 7218¦JA2594_1001 | 1 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
307 | 39121004 | Fuente de alimentaci&#243;n conmutada Ex | 1101828497 | 1 | 2025-01-23 |  | 4800002841 | 40 | 2025-01-23 |  |  | 2025-01-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6273787 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
308 | 39121402 | Clavija Legrand de 2P+E de color Negro, | 1101828497 | 2 | 2025-01-23 |  | 4800002841 | 50 | 2025-01-23 |  |  | 2025-01-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2008444 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
309 | 39121402 | Clavija Legrand de 2P+E de color Negro, | 1101828497 | 3 | 2025-01-23 |  | 4800002841 | 60 | 2025-01-23 |  |  | 2025-01-24 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7050872 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
310 | 27111714 | Llave en cruz para armario de control RS | 1101828497 | 4 | 2025-01-23 |  | 4800002841 | 70 | 2025-01-23 |  |  | 2025-01-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8417005 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
311 | 26121636 | Cable de alimentaci&#243;n RS PRO Negro | 1101828497 | 5 | 2025-01-23 |  | 4800002841 | 80 | 2025-01-23 |  |  | 2025-01-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1230958 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -454 | 0
312 | 1261190420000 | BATERIA RECARG P/IMPRESOR RHINO4200/5200 | 1101829056 | 1 | 2025-01-24 |  | 4200595281 | 10 | 2025-01-29 | 2025-01-29 |  | 2025-02-12 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ELECTRONIC EQUIPMENT TRADING SAU (E | DYMO | 1759398 |  | 0 | 0 |  | 7218¦S24B05_P10322 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -435 | 0
313 |  | REFORMA ESCALERA BAHIA 3 | 1101829104 | 1 | 2025-01-24 |  | 4300339373 | 10 | 2025-01-27 | 2025-01-28 |  | 2025-03-17 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | ESTRUCTURAS COSAN,S.L. |  |  |  | 0 | 0 |  | 7218¦S24B05_S1075 | 49 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -402 | 0
314 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101829654 | 1 | 2025-01-27 |  | 4200595602 | 80 | 2025-01-30 | 2025-01-30 |  | 2025-02-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -433 | 0
315 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101829654 | 2 | 2025-01-27 |  | 4200595602 | 90 | 2025-01-30 | 2025-01-30 |  | 2025-02-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -433 | 0
316 | 39121404 | Puntera hueca de crimpado TE Connectivit | 1101829712 | 1 | 2025-01-27 |  | 4800002844 | 300 | 2025-01-27 |  |  | 2025-01-28 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7187359 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -450 | 0
317 | 39121432 | Terminal redondo no aislado de N&#237;qu | 1101829712 | 2 | 2025-01-27 |  | 4800002844 | 310 | 2025-01-27 |  |  | 2025-01-28 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1611285 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -450 | 0
318 | 32000000 | Conector circular MIL-C-38999 serie III | 1101829869 | 1 | 2025-01-27 |  | 4800002845 | 400 | 2025-01-27 |  |  | 2025-01-28 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804851 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -450 | 0
319 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101829887 | 1 | 2025-01-27 |  | 4200596100 | 10 | 2025-02-03 | 2025-02-03 |  | 2025-02-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -430 | 0
320 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101829888 | 1 | 2025-01-27 |  | 4200596100 | 20 | 2025-02-03 | 2025-02-03 |  | 2025-02-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -430 | 0
321 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101829913 | 1 | 2025-01-27 |  | 4200596107 | 80 | 2025-02-03 | 2025-02-03 |  | 2025-02-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -430 | 0
322 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101829941 | 1 | 2025-01-27 |  | 4200596234 | 60 | 2025-02-04 | 2025-02-04 |  | 2025-02-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -430 | 0
323 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101830334 | 1 | 2025-01-28 |  | 4900010251 | 10 | 2025-01-28 |  |  | 2025-03-31 | 40 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦JA2594_1001 | 62 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -388 | 0
324 | 39121402 | Punto de toma de tierra para rack para p | 1101831419 | 1 | 2025-01-30 |  | 4800002850 | 280 | 2025-01-29 |  |  | 2025-01-31 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0392141 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
325 | 39121404 | Puntera hueca de crimpado TE Connectivit | 1101831419 | 2 | 2025-01-30 |  | 4800002850 | 290 | 2025-01-29 |  |  | 2025-01-31 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7187359 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
326 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831641 | 1 | 2025-01-30 |  | 4200596485 | 20 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
327 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831641 | 2 | 2025-01-30 |  | 4200596485 | 30 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
328 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831671 | 1 | 2025-01-30 |  | 4200596485 | 40 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
329 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831749 | 1 | 2025-01-30 |  | 4200596508 | 30 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
330 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831775 | 1 | 2025-01-30 |  | 4200596514 | 10 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
331 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831775 | 2 | 2025-01-30 |  | 4200596514 | 20 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
332 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831775 | 3 | 2025-01-30 |  | 4200596514 | 30 | 2025-02-05 | 2025-02-06 |  | 2025-02-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -428 | 0
333 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831788 | 1 | 2025-01-30 |  | 4200596803 | 10 | 2025-02-07 | 2025-02-07 |  | 2025-02-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -426 | 0
334 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101831788 | 2 | 2025-01-30 |  | 4200596803 | 20 | 2025-02-07 | 2025-02-07 |  | 2025-02-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -426 | 0
335 | 39121412 | Carcasa de conector circular Amphenol Li | 1101832041 | 1 | 2025-01-31 |  | 4800002853 | 400 | 2025-01-30 |  |  | 2025-02-01 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2259368 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -446 | 0
336 | 55121612 | TMS-SCE-3/16-2.0-9 | 1101832041 | 2 | 2025-01-31 |  | 4800002853 | 410 | 2025-01-30 |  |  | 2025-02-01 | 0 | 0 |  | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2657051 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -446 | 0
337 | 55121611 | Etiquetas termorretr&#225;ctiles TE Conn | 1101832041 | 3 | 2025-01-31 |  | 4800002853 | 420 | 2025-01-30 |  |  | 2025-02-01 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2672556 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -446 | 0
338 | 32000000 | Conector circular MIL-C-38999 serie III | 1101832041 | 4 | 2025-01-31 |  | 4800002853 | 430 | 2025-01-30 |  |  | 2025-02-01 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804922 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -446 | 0
339 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101832157 | 1 | 2025-01-31 |  | 4200596840 | 30 | 2025-02-07 | 2025-02-07 |  | 2025-02-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -426 | 0
340 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101832157 | 2 | 2025-01-31 |  | 4200596840 | 40 | 2025-02-07 | 2025-02-07 |  | 2025-02-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -426 | 0
341 | 32000000 | Conector circular MIL-C-38999 serie III | 1101832199 | 1 | 2025-01-31 |  | 4800002855 | 110 | 2025-01-31 |  |  | 2025-02-01 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804851 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -446 | 0
342 | 39121432 | Terminal de leng&#252;eta hembra aislado | 1101832711 | 1 | 2025-02-03 |  | 4800002856 | 210 | 2025-02-03 |  |  | 2025-02-04 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2455446 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -443 | 0
343 | 46171509 | Armario para llaves con 20 ganchos Secur | 1101832948 | 1 | 2025-02-04 |  | 4800002856 | 590 | 2025-02-03 |  |  | 2025-02-05 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0219734 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -442 | 0
344 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101833067 | 1 | 2025-02-04 |  | 4200597455 | 10 | 2025-02-12 | 2025-02-13 |  | 2025-02-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -421 | 0
345 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101833096 | 1 | 2025-02-04 |  | 4200597455 | 20 | 2025-02-12 | 2025-02-13 |  | 2025-02-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -421 | 0
346 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101833136 | 1 | 2025-02-04 |  | 4200597461 | 30 | 2025-02-12 | 2025-02-13 |  | 2025-02-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -421 | 0
347 | 1589903560200 | BASE REGULAR 0.6M | 1101833790 | 1 | 2025-02-05 |  | 4200597875 | 10 | 2025-02-14 | 2025-02-19 |  | 2025-02-28 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | LAYHER IBERICA, S.L. | LAYHER | 4001.060 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 14 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
348 | 1589903560300 | EXTENSION HORIZONT 1,09X1,57M | 1101833790 | 2 | 2025-02-05 |  | 4200597875 | 20 | 2025-02-14 | 2025-02-19 |  | 2025-02-28 | 40 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | LAYHER IBERICA, S.L. | LAYHER | 2606.001 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 14 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
349 | 1589903560400 | EXTENSION HORIZONTAL 1,57X2,57M | 1101833790 | 3 | 2025-02-05 |  | 4200597875 | 30 | 2025-02-14 | 2025-02-19 |  | 2025-02-28 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | LAYHER IBERICA, S.L. | LAYHER | 2606.000 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 14 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
350 | 1589903560500 | PUERTA ACC C/RODAPIE P/TORRE DE 073 T20 | 1101833790 | 4 | 2025-02-05 |  | 4200597875 | 40 | 2025-02-14 | 2025-02-19 |  | 2025-02-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LAYHER IBERICA, S.L. | LAYHER | 2627073 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
351 | 39122325 | Rel&#233; modular Finder 58 Series, 4PDT | 1101834193 | 1 | 2025-02-06 |  | 4800002865 | 460 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6237292 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
352 | 39121432 | Terminal redondo no aislado de N&#237;qu | 1101834195 | 1 | 2025-02-06 |  | 4800002865 | 470 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1611285 |  | 0 | 0 |  | 7218¦JA2578_1001 | 2 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
353 | 39121404 | Puntera hueca de crimpado TE Connectivit | 1101834195 | 2 | 2025-02-06 |  | 4800002865 | 480 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7187359 |  | 0 | 0 |  | 7218¦JA2578_1001 | 2 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
354 | 39121444 | Conector RJ45 Macho Bel-Stewart serie 94 | 1101834195 | 3 | 2025-02-06 |  | 4800002865 | 490 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 60 | 60 | 60 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0477321 |  | 0 | 0 |  | 7218¦JA2578_1001 | 2 | - |  | YES | 60 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
355 | 39121444 | Funda RS PRO RJ45 para uso con Conectore | 1101834195 | 4 | 2025-02-06 |  | 4800002865 | 500 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 30 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2022608 |  | 0 | 0 |  | 7218¦JA2578_1001 | 2 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
356 | 32000000 | Conector circular MIL-C-38999 serie III | 1101834197 | 1 | 2025-02-06 |  | 4800002865 | 510 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804851 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
357 | 32000000 | Conector circular MIL-C-38999 serie III | 1101834197 | 2 | 2025-02-06 |  | 4800002865 | 520 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804922 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
358 | 39121302 | Abrazadera de Pared Schneider Electric d | 1101834197 | 3 | 2025-02-06 |  | 4800002865 | 530 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 8 | 8 | 8 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6174450 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
359 | 39121412 | Carcasa de conector circular Amphenol Li | 1101834197 | 4 | 2025-02-06 |  | 4800002865 | 540 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2259368 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
360 | 26121609 | Cable Ethernet Cat6 U/UTP StarTech.com d | 1101834228 | 1 | 2025-02-06 |  | 4800002865 | 620 | 2025-02-05 |  |  | 2025-02-07 | 0 | 0 |  | 7 | 7 | 7 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1929573 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 7 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -440 | 0
361 | 39121404 | Manguitos de soldadura, TE Connectivity, | 1101835057 | 1 | 2025-02-07 |  | 4800002869 | 1020 | 2025-02-06 |  |  | 2025-02-08 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2652726 |  | 0 | 0 |  | 7218¦JA2594_1001 | 2 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -439 | 0
362 | 31163102 | Puntera hueca de crimpado RS PRO, Aislad | 1101835057 | 2 | 2025-02-07 |  | 4800002869 | 1030 | 2025-02-06 |  |  | 2025-02-08 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 458689A |  | 0 | 0 |  | 7218¦JA2594_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -439 | 0
363 | 39121603 | Interruptor autom&#225;tico 2P, 32A, Cur | 1101835341 | 1 | 2025-02-10 |  | 4800002871 | 230 | 2025-02-08 |  |  | 2025-02-11 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7349670 |  | 0 | 0 |  | 7218¦JA2594_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -436 | 0
364 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101835527 | 1 | 2025-02-10 |  | 4200597749 | 20 | 2025-02-13 | 2025-02-13 |  | 2025-02-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -420 | 0
365 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101835527 | 2 | 2025-02-10 |  | 4200597749 | 30 | 2025-02-13 | 2025-02-13 |  | 2025-02-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -420 | 0
366 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101835529 | 1 | 2025-02-10 |  | 4200597749 | 40 | 2025-02-13 | 2025-02-13 |  | 2025-02-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -420 | 0
367 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101835535 | 1 | 2025-02-10 |  | 4200597749 | 50 | 2025-02-13 | 2025-02-13 |  | 2025-02-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -420 | 0
368 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101835562 | 1 | 2025-02-10 |  | 4200597766 | 30 | 2025-02-13 | 2025-02-13 |  | 2025-02-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -420 | 0
369 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101836333 | 1 | 2025-02-11 |  | 4200597997 | 10 | 2025-02-14 | 2025-02-18 |  | 2025-02-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
370 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101836579 | 1 | 2025-02-12 |  | 4200598014 | 10 | 2025-02-14 | 2025-02-18 |  | 2025-02-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
371 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101836579 | 2 | 2025-02-12 |  | 4200598014 | 20 | 2025-02-14 | 2025-02-18 |  | 2025-02-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
372 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101836584 | 1 | 2025-02-12 |  | 4200598014 | 30 | 2025-02-14 | 2025-02-18 |  | 2025-02-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
373 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101836584 | 2 | 2025-02-12 |  | 4200598014 | 40 | 2025-02-14 | 2025-02-18 |  | 2025-02-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
374 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101836593 | 1 | 2025-02-12 |  | 4200598014 | 50 | 2025-02-14 | 2025-02-18 |  | 2025-02-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -419 | 0
375 | 39121708 | Tira de jumpers Entrelec serie JB5, para | 1101837083 | 1 | 2025-02-13 |  | 4800002882 | 300 | 2025-02-12 |  |  | 2025-02-14 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6663468 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -433 | 0
376 | 39121004 | Fuente de alimentaci&#243;n conmutada TD | 1101837083 | 2 | 2025-02-13 |  | 4800002882 | 310 | 2025-02-12 |  |  | 2025-02-14 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6352177 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -433 | 0
377 | 31161816 | Separador roscado hexagonal Macho/Hembra | 1101837083 | 3 | 2025-02-13 |  | 4800002882 | 320 | 2025-02-12 |  |  | 2025-02-14 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0606686 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -433 | 0
378 | 24102007 | Estante voladizo 2U RS PRO, ventilado de | 1101837083 | 4 | 2025-02-13 |  | 4800002882 | 330 | 2025-02-12 |  |  | 2025-02-14 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8020282 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -433 | 0
379 | 46151501 | Barrera Retr&#225;ctil Tensator, Negro, | 1101837105 | 1 | 2025-02-13 |  | 4800002882 | 470 | 2025-02-12 |  |  | 2025-02-14 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7682624 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 2 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -433 | 0
380 | 39121432 | Terminal de leng&#252;eta hembra aislado | 1101837370 | 1 | 2025-02-13 |  | 4800002888 | 340 | 2025-02-13 |  |  | 2025-02-14 | 0 | 0 |  | 400 | 400 | 400 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2455446 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -433 | 0
381 | 39121432 | Terminal de leng&#252;eta hembra aislado | 1101837764 | 1 | 2025-02-14 |  | 4800002890 | 170 | 2025-02-14 |  |  | 2025-02-15 | 0 | 0 |  | 500 | 500 | 500 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2455446 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -432 | 0
382 |  | MONTAJE EQUIPO CABINA SIMULADOR A320 | 1101837770 | 1 | 2025-02-14 |  | 4300340863 | 10 | 2025-02-17 | 2025-02-21 |  | 2025-03-21 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 32 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -398 | 0
383 | 43211503 | ASUS TUF Gaming P1 - Alfombrilla de rat� | 1101837809 | 1 | 2025-02-14 |  | 4800002872 | 600 | 2025-02-10 |  |  | 2025-02-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 7202896 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -430 | 0
384 | 43211708 | CHERRY MW 3000 - Rat�n - diestro - infra | 1101837809 | 2 | 2025-02-14 |  | 4800002872 | 610 | 2025-02-10 |  |  | 2025-02-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 2418108 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -430 | 0
385 | 43211503 | ASUS TUF Gaming P1 - Alfombrilla de rat� | 1101837818 | 1 | 2025-02-14 |  | 4800002872 | 620 | 2025-02-10 |  |  | 2025-02-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 7202896 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -430 | 0
386 |  | TRABAJOS SIMULADOR A320 | 1101838192 | 1 | 2025-02-17 |  | 4300340871 | 10 | 2025-02-17 | 2025-02-19 |  | 2025-03-12 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 23 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -407 | 0
387 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101838768 | 1 | 2025-02-18 |  | 4200599497 | 30 | 2025-02-25 | 2025-02-25 |  | 2025-03-11 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -408 | 0
388 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101839340 | 1 | 2025-02-19 |  | 4200599594 | 10 | 2025-02-25 | 2025-02-25 |  | 2025-03-11 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -408 | 0
389 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101839366 | 1 | 2025-02-19 |  | 4900010383 | 10 | 2025-02-19 |  |  | 2025-02-19 | 40 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦JA2594_1001 | 0 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -428 | 0
390 | 31201600 | Adhesivo instant&#225;neo Loctite 401 de | 1101841110 | 1 | 2025-02-24 |  | 4800002908 | 240 | 2025-02-24 |  |  | 2025-02-25 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0317715 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -422 | 0
391 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101841169 | 1 | 2025-02-24 |  | 4200600359 | 30 | 2025-02-28 | 2025-03-03 |  | 2025-03-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2583_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -405 | 0
392 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101841171 | 1 | 2025-02-24 |  | 4200600366 | 10 | 2025-02-28 | 2025-03-03 |  | 2025-03-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2583_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -405 | 0
393 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101841174 | 1 | 2025-02-24 |  | 4200600371 | 10 | 2025-02-28 | 2025-03-03 |  | 2025-03-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2583_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -405 | 0
394 | 39121412 | Carcasa de conector circular Amphenol Li | 1101841553 | 1 | 2025-02-25 |  | 4800002909 | 70 | 2025-02-25 |  |  | 2025-02-26 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2067532 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -421 | 0
395 | 43201404 | Adaptador de red USB 3.0 StarTech.com, c | 1101841555 | 1 | 2025-02-25 |  | 4800002909 | 110 | 2025-02-25 |  |  | 2025-02-26 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1862768 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -421 | 0
396 |  | TRABAJOS SIMULADOR A320 | 1101841755 | 1 | 2025-02-25 |  | 4300341780 | 20 | 2025-03-03 | 2025-03-04 |  | 2025-02-25 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | TALLERES SANTIAGO DATO, S.L.U. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | -6 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -422 | 0
397 |  | MODIFICACION SIMULADOR A320 | 1101842371 | 1 | 2025-02-26 |  | 4300341835 | 10 | 2025-03-04 | 2025-03-06 |  | 2025-03-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 10 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -405 | 0
398 | 39122221 | Bloque de contactos Schneider Electric Z | 1101843367 | 1 | 2025-02-28 |  | 4800002913 | 630 | 2025-02-27 |  |  | 2025-03-01 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3310489 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -418 | 0
399 |  | ANALISIS DE LOS MEDIOS EXISTENTES | 1101843533 | 1 | 2025-03-03 |  | 4300341826 | 10 | 2025-03-04 | 2025-03-10 |  | 2025-05-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | HILTI ESPAÑOLA, S.A. |  |  |  | 1 | 1 |  | 7218¦JA2594_1001 | 88 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -327 | 0
400 |  | TRABAJOS SIMULADOR A320 | 1101843560 | 1 | 2025-03-03 |  | 4300341853 | 10 | 2025-03-04 | 2025-03-06 |  | 2025-03-26 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 22 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -393 | 0
401 | 55121611 | Etiquetas termorretr&#225;ctiles TE Conn | 1101844258 | 1 | 2025-03-04 |  | 4800002920 | 220 | 2025-03-04 |  |  | 2025-03-05 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2672433 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -414 | 0
402 | 32000000 | Carcasa de conector Molex 03-06-2042, Se | 1101844596 | 1 | 2025-03-05 |  | 4800002920 | 570 | 2025-03-04 |  |  | 2025-03-06 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6794855P |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -413 | 0
403 | 39121432 | Contacto de crimpado macho Molex serie S | 1101844596 | 2 | 2025-03-05 |  | 4800002920 | 580 | 2025-03-04 |  |  | 2025-03-06 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1786907 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -413 | 0
404 | 32000000 | Carcasa de conector Molex 03-06-2092, Se | 1101844596 | 3 | 2025-03-05 |  | 4800002920 | 590 | 2025-03-04 |  |  | 2025-03-06 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6794865P |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -413 | 0
405 |  | MONTAJE SIMULADOR A320 | 1101844652 | 1 | 2025-03-05 |  | 4400087082 | 10 | 2025-03-05 | 2025-03-05 |  | 2025-04-24 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | APLICACIONES DE SIMULACION |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 50 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -364 | 0
406 | 39121404 | Manguitos de soldadura, TE Connectivity, | 1101844710 | 1 | 2025-03-05 |  | 4800002920 | 720 | 2025-03-04 |  |  | 2025-03-06 | 0 | 0 |  | 9 | 9 | 9 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2652726 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -413 | 0
407 | 24102004 | Estanter&#237;a para Componente 1U APC N | 1101845229 | 1 | 2025-03-06 |  | 4800002923 | 240 | 2025-03-05 |  |  | 2025-03-07 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2387216 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -412 | 0
408 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845357 | 1 | 2025-03-06 |  | 4200601519 | 10 | 2025-03-07 | 2025-03-07 |  | 2025-03-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -398 | 0
409 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845357 | 2 | 2025-03-06 |  | 4200601519 | 20 | 2025-03-07 | 2025-03-07 |  | 2025-03-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -398 | 0
410 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845357 | 3 | 2025-03-06 |  | 4200601519 | 30 | 2025-03-07 | 2025-03-07 |  | 2025-03-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -398 | 0
411 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845357 | 4 | 2025-03-06 |  | 4200601519 | 40 | 2025-03-07 | 2025-03-07 |  | 2025-03-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -398 | 0
412 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845371 | 1 | 2025-03-06 |  | 4200601594 | 10 | 2025-03-10 | 2025-03-10 |  | 2025-03-24 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -395 | 0
413 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845657 | 1 | 2025-03-06 |  | 4200602096 | 10 | 2025-03-12 | 2025-03-12 |  | 2025-03-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -393 | 0
414 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845701 | 1 | 2025-03-06 |  | 4200601859 | 50 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
415 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845711 | 1 | 2025-03-06 |  | 4200601867 | 10 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
416 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845711 | 2 | 2025-03-06 |  | 4200601867 | 20 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
417 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845711 | 3 | 2025-03-06 |  | 4200601867 | 30 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
418 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845711 | 4 | 2025-03-06 |  | 4200601867 | 40 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
419 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845711 | 5 | 2025-03-06 |  | 4200601867 | 50 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
420 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845711 | 6 | 2025-03-06 |  | 4200601867 | 60 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
421 |  | TAPADO DE CARTELAS | 1101845816 | 1 | 2025-03-07 |  | 4300342309 | 10 | 2025-03-11 | 2025-03-13 |  | 2025-04-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2582_1001 | 34 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -374 | 0
422 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845909 | 1 | 2025-03-07 |  | 4200601902 | 10 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
423 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101845909 | 2 | 2025-03-07 |  | 4200601902 | 20 | 2025-03-11 | 2025-03-11 |  | 2025-03-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
424 | 1805710000000 | IMPRIMACION 94 AMBAR APROX 6% SOLIDOS | 1101847347 | 1 | 2025-03-11 |  | 4200604894 | 10 | 2025-03-31 | 2025-04-01 |  | 2025-04-30 | 61 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | 3M | 70-0160-5477-0 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 30 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -358 | 0
425 | 39121432 | Terminal de leng&#252;eta macho aislado | 1101848094 | 1 | 2025-03-13 |  | 4800002944 | 440 | 2025-03-12 |  |  | 2025-03-14 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2455244 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -405 | 0
426 | 39121413 | Conector circular Amphenol Limited Conec | 1101848095 | 1 | 2025-03-13 |  | 4800002944 | 450 | 2025-03-12 |  |  | 2025-03-14 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368151 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -405 | 0
427 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101848675 | 1 | 2025-03-14 |  | 4200602773 | 40 | 2025-03-17 | 2025-03-17 |  | 2025-03-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -388 | 0
428 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101848678 | 1 | 2025-03-14 |  | 4200602877 | 10 | 2025-03-18 | 2025-03-19 |  | 2025-04-01 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -387 | 0
429 | 27112009 | Rasqueta de acero RS PRO, 100 piezas | 1101848721 | 1 | 2025-03-14 |  | 4800002947 | 360 | 2025-03-13 |  |  | 2025-03-15 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 4846181 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -404 | 0
430 | 31161618 | Varillas Roscada, RS PRO, Plano, Acero I | 1101848721 | 2 | 2025-03-14 |  | 4800002947 | 370 | 2025-03-13 |  |  | 2025-03-15 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0280420 |  | 0 | 0 |  | 7218¦S24B05_P10253 | 2 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -404 | 0
431 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101849461 | 1 | 2025-03-17 |  | 4200604390 | 10 | 2025-03-26 | 2025-03-27 |  | 2025-04-09 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
432 | 39122241 | Interruptor de seguridad Telemecanique S | 1101851726 | 1 | 2025-03-24 |  | 4800002961 | 300 | 2025-03-21 |  |  | 2025-03-25 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2201359 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
433 | 31163100 | Conector IEC C14 macho Bulgin, Recto, Mo | 1101851726 | 2 | 2025-03-24 |  | 4800002961 | 310 | 2025-03-21 |  |  | 2025-03-25 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0449922 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
434 | 43211730 | Inyector de PoE 2 puertos, entrada 100 - | 1101851726 | 3 | 2025-03-24 |  | 4800002961 | 320 | 2025-03-21 |  |  | 2025-03-25 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2753549 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
435 | 26121629 | Cable de alimentaci&#243;n StarTech.com | 1101851726 | 4 | 2025-03-24 |  | 4800002961 | 330 | 2025-03-21 |  |  | 2025-03-25 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2677825 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
436 | 45111823 | HDMI to VGA Adapter - With Audio - 1080p | 1101851726 | 5 | 2025-03-24 |  | 4800002961 | 340 | 2025-03-21 |  |  | 2025-03-25 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1778828 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
437 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101852067 | 1 | 2025-03-24 |  | 4200604081 | 10 | 2025-03-25 | 2025-03-26 |  | 2025-04-08 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -380 | 0
438 | 43202222 | Cable DisplayPort blanco Roline, con. A: | 1101852578 | 1 | 2025-03-25 |  | 4800002964 | 590 | 2025-03-25 |  |  | 2025-03-26 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7903937 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -393 | 0
439 |  | DISEÑO MECÁNICO GTA SMOKE BOX | 1101853398 | 1 | 2025-03-26 |  | 4300343504 | 10 | 2025-03-31 | 2025-04-01 |  | 2025-05-12 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | ACOM SISTEMAS, S.L. |  |  |  | 1 | 1 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -346 | 0
440 | 39121432 | Terminales eléctricos | 1101853401 | 1 | 2025-03-26 |  | 4800002967 | 380 | 2025-03-26 |  |  | 2025-03-31 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1648670 |  | 0 | 0 |  | 7218¦JA2585_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -388 | 0
441 | 39121413 | Conector circular Amphenol Limited Conec | 1101853598 | 1 | 2025-03-27 |  | 4800002968 | 150 | 2025-03-27 |  |  | 2025-03-28 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368155 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -391 | 0
442 | 39121410 | Borne terminal pasante, Gris, Terminaci& | 1101853930 | 1 | 2025-03-27 |  | 4800002970 | 30 | 2025-03-27 |  |  | 2025-03-28 | 0 | 0 |  | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6879436 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -391 | 0
443 | 32121615 | Resistencia RS PRO, de 220? &#177;5%, 0. | 1101854632 | 1 | 2025-03-31 |  | 4800002972 | 130 | 2025-03-28 |  |  | 2025-04-01 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7078176 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -387 | 0
444 |  | MONTAJE SIMULADOR A320 | 1101855158 | 1 | 2025-04-01 |  | 4300343596 | 20 | 2025-04-01 | 2025-04-02 |  | 2025-04-24 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 23 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
445 |  | MONTAJE SIMULADOR A320 | 1101855424 | 1 | 2025-04-01 |  | 4300343641 | 10 | 2025-04-02 | 2025-04-02 |  | 2025-04-24 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 22 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
446 | 41113633 | Potenci&#243;metro de 4.7k?, &#177;20%, | 1101855938 | 1 | 2025-04-02 |  | 4800002981 | 60 | 2025-04-02 |  |  | 2025-04-03 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7904435 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -385 | 0
447 | 39121534 | Luz piloto, Universal LED, di&#225;metro | 1101856109 | 1 | 2025-04-02 |  | 4800002981 | 420 | 2025-04-02 |  |  | 2025-04-03 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6095701 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -385 | 0
448 | 39121402 | Punto de toma de tierra para rack para p | 1101856114 | 1 | 2025-04-02 |  | 4800002981 | 430 | 2025-04-02 |  |  | 2025-04-03 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0392141 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -385 | 0
449 | 32000000 | Mu&#241;equera antiest&#225;tica Encaje | 1101856114 | 2 | 2025-04-02 |  | 4800002981 | 440 | 2025-04-02 |  |  | 2025-04-03 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2517691 |  | 0 | 0 |  | 7218¦JA2593_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -385 | 0
450 | 9999000322010 | N.R. PANELES SIMULADORES | 1101856565 | 1 | 2025-04-03 |  | 4200605815 | 20 | 2025-04-04 | 2025-04-09 |  | 2025-05-19 | 175 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS |  |  |  | 0 | 0 |  | 7218¦JA2583_1001 | 45 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -339 | 0
451 | 43202222 | Cable DisplayPort negro StarTech.com, co | 1101857469 | 1 | 2025-04-07 |  | 4800002987 | 540 | 2025-04-04 |  |  | 2025-04-08 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2677818 |  | 0 | 0 |  | 7218¦JA2582_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -380 | 0
452 | 43202222 | Cable DisplayPort negro StarTech.com, co | 1101858156 | 1 | 2025-04-08 |  | 4800002989 | 270 | 2025-04-07 |  |  | 2025-04-09 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2677818 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -379 | 0
453 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101858741 | 1 | 2025-04-09 |  | 4200607085 | 10 | 2025-04-11 | 2025-04-21 |  | 2025-04-25 | 30 | 8 | Liberado | 1 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -363 | 0
454 | 39121332 | Caja de conexiones Legrand 0 920 12, 7, | 1101861627 | 1 | 2025-04-22 |  | 4800003010 | 460 | 2025-04-22 |  |  | 2025-04-23 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3982488 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -365 | 0
455 | 31161518 | Tornillo Allen de cabeza cil&#237;ndrica | 1101861969 | 1 | 2025-04-23 |  | 4800003013 | 620 | 2025-04-22 |  |  | 2025-04-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1247350 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
456 | 31161618 | Varillas Roscada, RS PRO, Galvanizado, A | 1101861969 | 2 | 2025-04-23 |  | 4800003013 | 630 | 2025-04-22 |  |  | 2025-04-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1757007 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
457 | 32000000 | Conector circular MIL-C-38999 serie III | 1101862318 | 1 | 2025-04-23 |  | 4800003017 | 60 | 2025-04-23 |  |  | 2025-04-24 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2804849 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
458 | 32000000 | Mu&#241;equera antiest&#225;tica Encaje | 1101862318 | 2 | 2025-04-23 |  | 4800003017 | 70 | 2025-04-23 |  |  | 2025-04-24 | 0 | 0 |  | 4 | 4 | 4 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2517691 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
459 | 32121618 | Resistencia TE Connectivity, de 250? &#1 | 1101862318 | 3 | 2025-04-23 |  | 4800003017 | 80 | 2025-04-23 |  |  | 2025-04-24 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1355198 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
460 | 26121522 | Cable para Entornos Hostiles TE Connecti | 1101862318 | 4 | 2025-04-23 |  | 4800003017 | 90 | 2025-04-23 |  |  | 2025-04-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3299483 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
461 | 26121522 | Cable de conexi&#243;n TE Connectivity M | 1101862318 | 5 | 2025-04-23 |  | 4800003017 | 100 | 2025-04-23 |  |  | 2025-04-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1135826 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -364 | 0
462 |  | TRABAJOS MONTAJE SIM H175 | 1101862638 | 1 | 2025-04-24 |  | 4300344953 | 10 | 2025-04-24 | 2025-04-25 |  | 2025-05-24 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 30 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -334 | 0
463 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101864124 | 1 | 2025-04-29 |  | 4200608928 | 10 | 2025-04-30 | 2025-05-05 |  | 2025-05-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -344 | 0
464 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101864402 | 1 | 2025-04-30 |  | 4200609201 | 10 | 2025-05-05 | 2025-05-05 |  | 2025-05-19 | 30 | 8 | Liberado | 1 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -339 | 0
465 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101864402 | 2 | 2025-04-30 |  | 4200609201 | 20 | 2025-05-05 | 2025-05-05 |  | 2025-05-19 | 30 | 8 | Liberado | 1 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -339 | 0
466 |  | TRABAJOS INFRASESTRUCTURA COSLADA NH90 | 1101865310 | 1 | 2025-05-05 |  | 4300345640 | 10 | 2025-05-08 | 2025-05-09 |  | 2025-05-28 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 20 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -330 | 0
467 | 39121708 | Jumper Bar Phoenix Contact serie FBS 2-5 | 1101867478 | 1 | 2025-05-09 |  | 4800003052 | 520 | 2025-05-09 |  |  | 2025-05-10 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6879792 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -348 | 0
468 |  | JOSÉ MARÍA CHAVERO | 1101869421 | 1 | 2025-05-15 |  | 4300346317 | 10 | 2025-05-20 | 2025-05-21 |  | 2025-07-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | TINDAI FORMACION, PREVENCION Y |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 72 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 5 | 100% |  | -266 | 0
469 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101869602 | 1 | 2025-05-15 |  | 4200611095 | 30 | 2025-05-16 | 2025-05-16 |  | 2025-05-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -328 | 0
470 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101870648 | 1 | 2025-05-19 |  | 4200612503 | 10 | 2025-05-26 | 2025-05-26 |  | 2025-06-09 | 30 | 8 | Liberado | 1 | 13 | 13 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 13 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -318 | 0
471 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101870648 | 2 | 2025-05-19 |  | 4200612503 | 20 | 2025-05-26 | 2025-05-26 |  | 2025-06-09 | 30 | 8 | Liberado | 1 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -318 | 0
472 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101870648 | 3 | 2025-05-19 |  | 4200612503 | 30 | 2025-05-26 | 2025-05-26 |  | 2025-06-09 | 30 | 8 | Liberado | 1 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -318 | 0
473 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101870648 | 4 | 2025-05-19 |  | 4200612503 | 40 | 2025-05-26 | 2025-05-26 |  | 2025-06-09 | 30 | 8 | Liberado | 1 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -318 | 0
474 | 43211503 | Kingston ValueRAM - DDR4 - m�dulo - 16 G | 1101870650 | 1 | 2025-05-19 |  | 4800003053 | 690 | 2025-05-10 |  |  | 2025-05-20 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 5490987 |  | 0 | 0 |  | 7218¦JA2594_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -338 | 0
475 | 31211904 | Brocha para pintura Loctite con punta p | 1101871032 | 1 | 2025-05-20 |  | 4800003072 | 650 | 2025-05-20 |  |  | 2025-05-21 | 0 | 0 |  | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2907745 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -337 | 0
476 | 46182002 | Mascarillas desechables FFP1 9312+, seri | 1101871032 | 2 | 2025-05-20 |  | 4800003072 | 660 | 2025-05-20 |  |  | 2025-05-21 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7660378 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -337 | 0
477 | 31161518 | Tornillo Allen de cabeza cil&#237;ndrica | 1101871205 | 1 | 2025-05-20 |  | 4800003073 | 30 | 2025-05-20 |  |  | 2025-05-21 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0293325 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -337 | 0
478 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101871581 | 1 | 2025-05-21 |  | 4200612677 | 10 | 2025-05-27 | 2025-05-27 |  | 2025-06-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -317 | 0
479 |  | TRABAJOS MONTAJE SIM H175 | 1101872115 | 1 | 2025-05-22 |  | 4300346671 | 10 | 2025-05-26 | 2025-05-26 |  | 2025-06-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 0 | 0 |  | 7218¦JA2593_1001 | 19 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -313 | 0
480 | 26121609 | Cable telef&#243;nico Decelect, 2 pares, | 1101872649 | 1 | 2025-05-23 |  | 4800003080 | 80 | 2025-05-23 |  |  | 2025-05-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5185667 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -334 | 0
481 | 31162906 | Abrazadera HI-TORQUE de Acero inoxidable | 1101873624 | 1 | 2025-05-27 |  | 4800003085 | 120 | 2025-05-27 |  |  | 2025-05-28 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2682684 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -330 | 0
482 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101874504 | 1 | 2025-05-28 |  | 4200613724 | 10 | 2025-06-02 | 2025-06-02 |  | 2025-06-16 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -311 | 0
483 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101874516 | 1 | 2025-05-28 |  | 4200613726 | 10 | 2025-06-02 | 2025-06-02 |  | 2025-06-16 | 30 | 8 | Liberado | 1 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -311 | 0
484 | 47131821 | Desengrasante industrial 3M Industrial D | 1101874630 | 1 | 2025-05-28 |  | 4800003089 | 590 | 2025-05-28 |  |  | 2025-05-29 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1921475 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -329 | 0
485 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101875026 | 1 | 2025-05-29 |  | 4200613313 | 10 | 2025-05-29 | 2025-05-30 |  | 2025-06-12 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -315 | 0
486 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101875026 | 2 | 2025-05-29 |  | 4200613313 | 20 | 2025-05-29 | 2025-05-30 |  | 2025-06-12 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -315 | 0
487 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101875035 | 1 | 2025-05-29 |  | 4200613559 | 20 | 2025-06-02 | 2025-06-02 |  | 2025-06-16 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -311 | 0
488 |  | TRABAJOS MONTAJE SIM H175 | 1101876071 | 1 | 2025-06-02 |  | 4300347247 | 30 | 2025-06-03 | 2025-06-05 |  | 2025-08-25 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | AUXITEL, S.L. |  |  |  | 1 | 1 |  | 7218¦JA2593_1001 | 83 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -241 | 0
489 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 1 | 2025-06-03 |  | 4200614302 | 10 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 110 | 110 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 110 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
490 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 2 | 2025-06-03 |  | 4200614302 | 20 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
491 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 3 | 2025-06-03 |  | 4200614302 | 30 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
492 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 4 | 2025-06-03 |  | 4200614302 | 40 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
493 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 5 | 2025-06-03 |  | 4200614302 | 50 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 40 | 40 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
494 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 6 | 2025-06-03 |  | 4200614302 | 60 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
495 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 7 | 2025-06-03 |  | 4200614302 | 70 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 70 | 70 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 70 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
496 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 8 | 2025-06-03 |  | 4200614302 | 80 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
497 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101876404 | 9 | 2025-06-03 |  | 4200614302 | 90 | 2025-06-05 | 2025-06-05 |  | 2025-06-19 | 30 | 8 | Liberado | 1 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
498 | 39121421 | Carcasa de conector Molex 39-01-4031, Se | 1101876743 | 1 | 2025-06-04 |  | 4800003109 | 110 | 2025-06-04 |  |  | 2025-06-05 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6795842 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -322 | 0
499 |  | ADEC. LUMINARIAS BANCO ST.01 | 1101876885 | 1 | 2025-06-04 |  | 4300348534 | 10 | 2025-06-25 | 2025-06-26 |  | 2025-10-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 128 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 6 | 100% |  | -174 | 0
500 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101876990 | 1 | 2025-06-04 |  | 4200616938 | 20 | 2025-06-24 | 2025-06-25 |  | 2025-07-08 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S08 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -289 | 0
501 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 1 | 2025-06-04 |  | 4200614720 | 10 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
502 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 2 | 2025-06-04 |  | 4200614720 | 20 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
503 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 3 | 2025-06-04 |  | 4200614720 | 30 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
504 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 4 | 2025-06-04 |  | 4200614720 | 40 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
505 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 5 | 2025-06-04 |  | 4200614720 | 50 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
506 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 6 | 2025-06-04 |  | 4200614720 | 60 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
507 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 7 | 2025-06-04 |  | 4200614720 | 70 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
508 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 8 | 2025-06-04 |  | 4200614720 | 80 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
509 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101877066 | 9 | 2025-06-04 |  | 4200614720 | 90 | 2025-06-09 | 2025-06-09 |  | 2025-06-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -304 | 0
510 | 43211609 | Concentrador de bus serial universal o c | 1101877309 | 1 | 2025-06-05 |  | 4800003111 | 200 | 2025-06-05 |  |  | 2025-06-06 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368995 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -321 | 0
511 | 39122216 | Seta de emergencia Schneider Electric se | 1101877310 | 1 | 2025-06-05 |  | 4800003111 | 210 | 2025-06-05 |  |  | 2025-06-06 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 4262808 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -321 | 0
512 | 39121006 | Adaptador AC/DC MEAN WELL 100V ac, 12V d | 1101878578 | 1 | 2025-06-09 |  | 4800003113 | 730 | 2025-06-06 |  |  | 2025-06-10 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1361342 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -317 | 0
513 | 31162401 | Pasamuro SES Sterling DK de PVC Negro, & | 1101878755 | 1 | 2025-06-09 |  | 4800003116 | 70 | 2025-06-09 |  |  | 2025-06-10 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1366862 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -317 | 0
514 | 47121607 | Accesorio para Aspiradora Sidamo 2049802 | 1101879032 | 1 | 2025-06-10 |  | 4800003116 | 340 | 2025-06-09 |  |  | 2025-06-11 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8952094 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -316 | 0
515 | 46000000 | Cinta perimetral RS PRO de color Rojo/bl | 1101879032 | 2 | 2025-06-10 |  | 4800003116 | 350 | 2025-06-09 |  |  | 2025-06-11 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7632049 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -316 | 0
516 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101879317 | 1 | 2025-06-10 |  | 4200615774 | 10 | 2025-06-16 | 2025-06-17 |  | 2025-06-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -297 | 0
517 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101879317 | 2 | 2025-06-10 |  | 4200615774 | 20 | 2025-06-16 | 2025-06-17 |  | 2025-06-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -297 | 0
518 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101879317 | 3 | 2025-06-10 |  | 4200615774 | 30 | 2025-06-16 | 2025-06-17 |  | 2025-06-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -297 | 0
519 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101879317 | 4 | 2025-06-10 |  | 4200615774 | 40 | 2025-06-16 | 2025-06-17 |  | 2025-06-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -297 | 0
520 | 39121324 | Caja Spelsberg de Poliestireno Transpare | 1101879439 | 1 | 2025-06-10 |  | 4800003116 | 780 | 2025-06-09 |  |  | 2025-06-11 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5337284 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -316 | 0
521 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101880388 | 1 | 2025-06-12 |  | 4200616063 | 10 | 2025-06-17 | 2025-06-18 |  | 2025-07-01 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -296 | 0
522 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101880388 | 2 | 2025-06-12 |  | 4200616063 | 20 | 2025-06-17 | 2025-06-18 |  | 2025-07-01 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -296 | 0
523 |  | INSTALACION SIMULADOR A320 | 1101880855 | 1 | 2025-06-13 |  | 4300347981 | 40 | 2025-06-16 | 2025-06-19 |  | 2025-07-06 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 | X | 0.00 |  | ISC Instalaciones y Servicios de |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 20 | - |  | YES | 0 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -291 | 0
524 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101881047 | 1 | 2025-06-16 |  | 4200616463 | 20 | 2025-06-19 | 2025-06-19 |  | 2025-07-03 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -294 | 0
525 | 55121612 | PK100 ETIQ APLI POLIEST A4 BCO 12121 | 1101881292 | 1 | 2025-06-16 |  | 4800003098 | 2080 | 2025-06-02 |  |  | 2025-06-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 10208643 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -310 | 0
526 |  | INSTALACION SIMULADOR A320 | 1101881742 | 1 | 2025-06-17 |  | 4300348535 | 30 | 2025-06-25 | 2025-07-01 |  | 2025-07-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | TALLERES SANTIAGO DATO, S.L.U. |  |  |  | 1 | 1 |  | 7218¦JA2594_1001 | 36 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 6 | 100% |  | -266 | 0
527 | 31163100 | Conector IEC C14 macho Bulgin, Recto, Mo | 1101881962 | 1 | 2025-06-17 |  | 4800003131 | 60 | 2025-06-17 |  |  | 2025-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0195912 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -309 | 0
528 | 39121332 | Caja de conexi&#243;n HENSEL KF 0606 B, | 1101881962 | 2 | 2025-06-17 |  | 4800003131 | 70 | 2025-06-17 |  |  | 2025-06-18 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2765466 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -309 | 0
529 | 32000000 | Prensaestopas HENSEL ASS de Poliamida Ne | 1101881962 | 3 | 2025-06-17 |  | 4800003131 | 80 | 2025-06-17 |  |  | 2025-06-18 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0117545 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -309 | 0
530 | 39131705 | Canalizaci&#243;n de cables miniatura Le | 1101882393 | 1 | 2025-06-18 |  | 4800003136 | 210 | 2025-06-18 |  |  | 2025-06-19 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1613039 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -308 | 0
531 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101882729 | 1 | 2025-06-19 |  | 4200617180 | 20 | 2025-06-25 | 2025-06-26 |  | 2025-07-09 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -288 | 0
532 | 32000000 | Kits de pasamuros NEMIQ de Caucho Negro, | 1101883901 | 1 | 2025-06-23 |  | 4800003138 | 810 | 2025-06-19 |  |  | 2025-06-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2884369 |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -303 | 0
533 | 31162401 | Pasamuro SES Sterling DH de Policloropre | 1101883901 | 2 | 2025-06-23 |  | 4800003138 | 820 | 2025-06-19 |  |  | 2025-06-24 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1366294 |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -303 | 0
534 | 39122325 | Rel&#233; de potencia sin enclavamiento | 1101884220 | 1 | 2025-06-24 |  | 4800003141 | 320 | 2025-06-24 |  |  | 2025-06-25 | 0 | 0 |  | 19 | 19 | 19 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0154526 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 19 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -302 | 0
535 | 41111905 | Juego de cables de prueba RS PRO, CAT II | 1101884352 | 1 | 2025-06-25 |  | 4800003141 | 390 | 2025-06-24 |  |  | 2025-06-26 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2432998 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -301 | 0
536 | 39121413 | Conector circular Amphenol Limited Conec | 1101884977 | 1 | 2025-06-26 |  | 4800003141 | 850 | 2025-06-24 |  |  | 2025-06-27 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2368155 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -300 | 0
537 |  | INSTAL. CONDUCTOS PINGÜINO SF.03 | 1101885147 | 1 | 2025-06-26 |  | 4300349565 | 10 | 2025-07-11 | 2025-07-14 |  | 2025-10-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦S24B05_S1075 | 112 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 6 | 100% |  | -174 | 0
538 | 3230100640000 | SOFTWARE MICROSOFT | 1101885873 | 1 | 2025-06-30 |  | 4200618716 | 10 | 2025-07-08 | 2025-07-08 |  | 2025-10-23 | 140 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | INGRAM MICRO, S.L.U. | MICROSOFT | LICENCIA OEM |  | 1 | 1 |  | 7218¦JA2583_1001 | 107 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -182 | 0
539 | 9999000981312 | N.R.PLATAFORMAS (SIMULADORES) | 1101886396 | 1 | 2025-07-01 |  | 4200620010 | 10 | 2025-07-16 | 2025-07-23 |  | 2025-09-01 | 180 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TALLERES XUQUER, SL |  |  |  | 0 | 0 |  | 7218¦JA2580_1001 | 47 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -234 | 0
540 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101886453 | 1 | 2025-07-01 |  | 4200619728 | 10 | 2025-07-15 | 2025-07-16 |  | 2025-09-30 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦S24B05_S1075 | 77 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
541 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101886462 | 1 | 2025-07-01 |  | 4200619731 | 10 | 2025-07-15 | 2025-07-16 |  | 2025-09-30 | 30 | 8 | Liberado | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 77 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
542 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101886462 | 2 | 2025-07-01 |  | 4200619731 | 20 | 2025-07-15 | 2025-07-16 |  | 2025-09-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 77 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
543 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101886462 | 3 | 2025-07-01 |  | 4200619731 | 30 | 2025-07-15 | 2025-07-16 |  | 2025-09-30 | 30 | 8 | Liberado | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 77 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
544 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101886462 | 4 | 2025-07-01 |  | 4200619731 | 40 | 2025-07-15 | 2025-07-16 |  | 2025-09-30 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 77 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
545 | 45111823 | HDMI to VGA Adapter - With Audio - 1080p | 1101887079 | 1 | 2025-07-02 |  | 4800003156 | 1140 | 2025-07-01 |  |  | 2025-07-03 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1778828 |  | 0 | 0 |  | 7218¦JA2594_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -294 | 0
546 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101887437 | 1 | 2025-07-03 |  | 4900011056 | 10 | 2025-07-03 |  |  | 2025-10-31 | 40 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦JA2594_1001 | 120 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -174 | 0
547 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101887443 | 1 | 2025-07-03 |  | 4900011059 | 10 | 2025-07-03 |  |  | 2025-09-30 | 40 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦JA2594_1001 | 89 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
548 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101887662 | 1 | 2025-07-03 |  | 4200620036 | 10 | 2025-07-16 | 2025-07-17 |  | 2025-09-30 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 76 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
549 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101887664 | 1 | 2025-07-03 |  | 4200620036 | 20 | 2025-07-16 | 2025-07-17 |  | 2025-09-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 76 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
550 | 32000000 | Panel del Rack 1U nVent SCHROFF de Alumi | 1101888882 | 1 | 2025-07-08 |  | 4800003167 | 270 | 2025-07-07 |  |  | 2025-07-09 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2839198 |  | 0 | 0 |  | 7218¦JA2594_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -288 | 0
551 | 27111710 | Juego de llaves hexagonales en L Facom d | 1101889452 | 1 | 2025-07-09 |  | 4800003170 | 170 | 2025-07-09 |  |  | 2025-07-10 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7554122 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -287 | 0
552 |  | MOQUETA A320 FFS | 1101890088 | 1 | 2025-07-10 |  | 4300349810 | 10 | 2025-07-17 | 2025-07-18 |  | 2025-11-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ANTONIO RAMIREZ DECORACION SL |  |  |  | 0 | 0 |  | 7218¦S24B05_S1076 | 136 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 7 | 100% |  | -144 | 0
553 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101890242 | 1 | 2025-07-10 |  | 4200620293 | 50 | 2025-07-17 | 2025-07-21 |  | 2025-09-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 75 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
554 | 55121620 | Hoja de etiquetas Avery L7651-25, 25 Dir | 1101890718 | 1 | 2025-07-11 |  | 4800003179 | 410 | 2025-07-11 |  |  | 2025-07-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2893595 |  | 0 | 0 |  | 7218¦JA2582_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -285 | 0
555 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101890983 | 1 | 2025-07-14 |  | 4200620401 | 10 | 2025-07-18 | 2025-07-21 |  | 2025-09-30 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 74 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
556 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101891012 | 1 | 2025-07-14 |  | 4200620441 | 10 | 2025-07-18 | 2025-07-21 |  | 2025-09-30 | 30 | 8 | Liberado | 70 | 70 | 70 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 74 | - |  | YES | 70 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
557 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101891012 | 2 | 2025-07-14 |  | 4200620441 | 20 | 2025-07-18 | 2025-07-21 |  | 2025-09-30 | 30 | 8 | Liberado | 70 | 70 | 70 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2585_1001 | 74 | - |  | YES | 70 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
558 | 39122335 | Z&#243;calo de rel&#233; Finder 96 para | 1101892281 | 1 | 2025-07-16 |  | 4800003183 | 450 | 2025-07-16 |  |  | 2025-07-17 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2455711 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -280 | 0
559 | 31161816 | Separador roscado hexagonal Macho/Hembra | 1101892362 | 1 | 2025-07-16 |  | 4800003183 | 540 | 2025-07-16 |  |  | 2025-07-17 | 0 | 0 |  | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0606686 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -280 | 0
560 | 43211503 | Kensington CH1000 - Hub - 2 x USB 3.1 + | 1101892552 | 1 | 2025-07-17 |  | 4800003172 | 570 | 2025-07-10 |  |  | 2025-07-18 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 4787170 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -279 | 0
561 | 39122213 | Final de carrera con Palanca de rodillo | 1101892592 | 1 | 2025-07-17 |  | 4800003184 | 120 | 2025-07-17 |  |  | 2025-07-18 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 3081664 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -279 | 0
562 | 43211503 | C2G 4-Port USB-A Hub - Hub - 4 x USB 2.0 | 1101893679 | 1 | 2025-07-21 |  | 4800003172 | 710 | 2025-07-10 |  |  | 2025-07-22 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. |  | 6999238 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -275 | 0
563 |  | TRABAJOS DE CORTE DE MAYLAR - COSLADA | 1101893680 | 1 | 2025-07-21 |  | 4300350504 | 10 | 2025-07-30 | 2025-07-30 |  | 2025-08-13 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ISC Instalaciones y Servicios de |  |  |  | 0 | 0 |  | 7218¦S24B05_P10253 | 14 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 7 | 100% |  | -253 | 0
564 | 43211617 | Cable USB 2.0 Hama, con A. USB A Macho, | 1101893846 | 1 | 2025-07-22 |  | 4800003188 | 500 | 2025-07-21 |  |  | 2025-07-23 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2386143 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -274 | 0
565 |  | FABRICACION PIEZAS | 1101893987 | 1 | 2025-07-22 |  | 4300350909 | 10 | 2025-08-07 | 2025-08-07 |  | 2025-09-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ESTRUCTURAS COSAN,S.L. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001 | 38 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 7 | 100% |  | -221 | 0
566 | 43211617 | Cable USB 2.0 Hama, con A. USB A Macho, | 1101894884 | 1 | 2025-07-24 |  | 4800003193 | 600 | 2025-07-23 |  |  | 2025-07-25 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2386143 |  | 0 | 0 |  | 7218¦JA2585_1001 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -272 | 0
567 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101896436 | 1 | 2025-07-30 |  | 4200624192 | 10 | 2025-08-22 | 2025-08-25 |  | 2025-10-21 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 60 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -184 | 0
568 | 39121723 | Funda termorrectr&#225;ctil recta TE Con | 1101898212 | 1 | 2025-08-05 |  | 4800003218 | 110 | 2025-08-05 |  |  | 2025-08-06 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7183092 |  | 0 | 0 |  | 7218¦JA2585_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -260 | 0
569 |  | MONTAJE REJIBAND SF.03 | 1101898253 | 1 | 2025-08-05 |  | 4300351264 | 10 | 2025-08-18 | 2025-08-19 |  | 2025-12-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦S24B05_GAR03 | 135 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 8 | 100% |  | -113 | 0
570 | 26121539 | Cable de conexi&#243;n Lapp 4160203, &#2 | 1101898527 | 1 | 2025-08-06 |  | 4800003218 | 550 | 2025-08-05 |  |  | 2025-08-07 | 0 | 0 |  | 15 | 15 | 15 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7244238 |  | 0 | 0 |  | 7218¦JA2593_1001 | 2 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -259 | 0
571 | 39121324 | Caja Spelsberg de Poliestireno Gris, 254 | 1101898813 | 1 | 2025-08-07 |  | 4800003218 | 880 | 2025-08-05 |  |  | 2025-08-08 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0832554 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -258 | 0
572 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101898899 | 1 | 2025-08-07 |  | 4200624413 | 10 | 2025-08-25 | 2025-08-26 |  | 2025-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2581_1001 | 67 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
573 | 55121612 | PK100 ETIQ APLI POLIEST A4 BCO 12121 | 1101899457 | 1 | 2025-08-11 |  | 4800003205 | 510 | 2025-08-01 |  |  | 2025-08-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 10208643 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -254 | 0
574 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101899460 | 1 | 2025-08-11 |  | 4200624525 | 10 | 2025-08-26 | 2025-08-27 |  | 2025-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 66 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
575 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101899460 | 2 | 2025-08-11 |  | 4200624525 | 20 | 2025-08-26 | 2025-08-27 |  | 2025-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 66 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
576 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101899460 | 3 | 2025-08-11 |  | 4200624525 | 30 | 2025-08-26 | 2025-08-27 |  | 2025-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 66 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
577 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101899460 | 4 | 2025-08-11 |  | 4200624525 | 40 | 2025-08-26 | 2025-08-27 |  | 2025-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 66 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
578 | 39121606 | Fusible de cartucho cer&#225;mico Mersen | 1101899657 | 1 | 2025-08-12 |  | 4800003223 | 600 | 2025-08-08 |  |  | 2025-08-13 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1886962 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 5 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -253 | 0
579 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101900103 | 1 | 2025-08-13 |  | 4200624659 | 10 | 2025-08-27 | 2025-08-28 |  | 2025-10-31 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 65 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
580 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101900103 | 2 | 2025-08-13 |  | 4200624659 | 20 | 2025-08-27 | 2025-08-28 |  | 2025-10-31 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 65 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
581 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101900103 | 3 | 2025-08-13 |  | 4200624659 | 30 | 2025-08-27 | 2025-08-28 |  | 2025-10-31 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 65 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
582 | 1357007369100 | MARCADOR ADH P/SERIE H 3000X | 1101900185 | 1 | 2025-08-13 |  | 4200624090 | 10 | 2025-08-21 | 2025-08-21 |  | 2025-08-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SOLUCIONES SICNOVA, S.L. | SHINING 3D | P00012182 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -238 | 0
583 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101900360 | 1 | 2025-08-14 |  | 4200624673 | 10 | 2025-08-27 | 2025-08-28 |  | 2025-10-31 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 65 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
584 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101900360 | 2 | 2025-08-14 |  | 4200624673 | 20 | 2025-08-27 | 2025-08-28 |  | 2025-10-31 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 65 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
585 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101901582 | 1 | 2025-08-21 |  | 4200625226 | 10 | 2025-09-02 | 2025-09-05 |  | 2025-10-13 | 30 | 8 | Liberado | 6 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2581_1001 | 41 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -192 | 0
586 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101902110 | 1 | 2025-08-25 |  | 4200625298 | 10 | 2025-09-02 | 2025-09-05 |  | 2025-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 59 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -174 | 0
587 | 32151703 | Memoria Phoenix Contact SD FLASH 512MB | 1101903948 | 1 | 2025-09-02 |  | 4800003245 | 130 | 2025-09-02 |  |  | 2025-09-03 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2416141 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -232 | 0
588 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101904260 | 1 | 2025-09-03 |  | 4200626753 | 10 | 2025-09-12 | 2025-09-17 |  | 2025-11-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 77 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -146 | 0
589 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101904270 | 1 | 2025-09-03 |  | 4200626754 | 10 | 2025-09-12 | 2025-09-17 |  | 2026-01-02 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 112 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -111 | 0
590 | 26111722 | Adaptador AC/DC RS PRO 100 ? 240V ac, 15 | 1101904399 | 1 | 2025-09-03 |  | 4800003245 | 700 | 2025-09-02 |  |  | 2025-09-04 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2008924 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -231 | 0
591 | 39121004 | Adaptador AC/DC Ansmann 135 ? 370 V dc, | 1101904399 | 2 | 2025-09-03 |  | 4800003245 | 710 | 2025-09-02 |  |  | 2025-09-04 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7023261 |  | 0 | 0 |  | 7218¦S24B05_S1077 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -231 | 0
592 |  | INSTALACION SIMULADOR H175 | 1101904455 | 1 | 2025-09-03 |  | 4300352010 | 20 | 2025-09-05 | 2025-09-17 |  | 2025-10-15 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ISC Instalaciones y Servicios de |  |  |  | 1 | 1 |  | 7218¦JA2593_1001 | 40 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 9 | 100% |  | -190 | 0
593 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101907155 | 1 | 2025-09-11 |  | 4200627807 | 10 | 2025-09-19 | 2025-09-23 |  | 2025-11-29 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 71 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -145 | 0
594 | 55121704 | Se&#241;al de salida de emergencia S21 S | 1101907243 | 1 | 2025-09-11 |  | 4800003266 | 790 | 2025-09-10 |  |  | 2025-09-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2209907 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -223 | 0
595 | 55121704 | Se&#241;al de salida de emergencia con f | 1101907243 | 2 | 2025-09-11 |  | 4800003266 | 800 | 2025-09-10 |  |  | 2025-09-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2209885 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -223 | 0
596 | 55121704 | Se&#241;al de protecci&#243;n contra inc | 1101907243 | 3 | 2025-09-11 |  | 4800003266 | 810 | 2025-09-10 |  |  | 2025-09-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2209929 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -223 | 0
597 | 55121704 | Se&#241;al de protecci&#243;n contra inc | 1101907243 | 4 | 2025-09-11 |  | 4800003266 | 820 | 2025-09-10 |  |  | 2025-09-12 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2209930 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -223 | 0
598 | 44121615 | GRAPADORA PETRUS 210 25H NGO | 1101907259 | 1 | 2025-09-11 |  | 4800003240 | 2540 | 2025-09-01 |  |  | 2025-09-12 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 6018307 |  | 0 | 0 |  | 7218¦JA2594_1001 | 11 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -223 | 0
599 | 31161518 | Tornillo Allen de cabeza cil&#237;ndrica | 1101908872 | 1 | 2025-09-16 |  | 4800003275 | 560 | 2025-09-15 |  |  | 2025-09-17 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1247350 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -218 | 0
600 | 39121415 | Conector macho para PCB Molex serie SL d | 1101909391 | 1 | 2025-09-17 |  | 4800003278 | 360 | 2025-09-17 |  |  | 2025-09-18 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6700835 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -217 | 0
601 | 32121612 | Resistencia Vishay, de 3.9k? &#177;1%, 0 | 1101909391 | 2 | 2025-09-17 |  | 4800003278 | 370 | 2025-09-17 |  |  | 2025-09-18 | 0 | 0 |  | 25 | 25 | 25 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6833641 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -217 | 0
602 | 44122109 | Cinta de gancho y bucle RS PRO de color | 1101910399 | 1 | 2025-09-19 |  | 4800003284 | 100 | 2025-09-19 |  |  | 2025-09-20 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8904149 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -215 | 0
603 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101910728 | 1 | 2025-09-22 |  | 4900011337 | 10 | 2025-09-23 |  |  | 2025-12-31 | 40 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦2GP240_1020 | 99 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -113 | 0
604 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101910881 | 1 | 2025-09-22 |  | 4200628789 | 10 | 2025-09-26 | 2025-09-29 |  | 2025-11-14 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 49 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -160 | 0
605 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101911213 | 1 | 2025-09-23 |  | 4900011345 | 10 | 2025-09-23 |  |  | 2025-11-30 | 40 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦JA2594_1001 | 68 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -144 | 0
606 | 55121612 | PK20 ETQ LSR 210X297 VDE FLUO APLI 2881 | 1101911902 | 1 | 2025-09-24 |  | 4800003240 | 4640 | 2025-09-01 |  |  | 2025-09-25 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | FUNDACION JUAN XXIII-RONCALLI DISC. |  | 993168 |  | 0 | 0 |  | 7218¦JA2594_1001 | 24 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -210 | 0
607 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101911917 | 1 | 2025-09-24 |  | 4200628787 | 10 | 2025-09-26 | 2025-09-29 |  | 2025-11-16 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦S24B05_S107G | 51 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -158 | 0
608 | 32111601 | Fototransistor NPN Vishay sensible a IR, | 1101912966 | 1 | 2025-09-26 |  | 4800003291 | 530 | 2025-09-25 |  |  | 2025-09-27 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7082822 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -208 | 0
609 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101912981 | 1 | 2025-09-26 |  | 4200630006 | 10 | 2025-10-06 | 2025-10-07 |  | 2025-11-29 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 54 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -145 | 0
610 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101913015 | 1 | 2025-09-26 |  | 4200630007 | 10 | 2025-10-06 | 2025-10-07 |  | 2025-11-27 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | GRUPO ELECTRO-STOCKS,S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 52 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -147 | 0
611 | 32000000 | Funda termorrectr&#225;ctil TE Connectiv | 1101913156 | 1 | 2025-09-26 |  | 4800003291 | 590 | 2025-09-25 |  |  | 2025-09-27 | 40 | 8 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 7183317P |  | 0 | 0 |  | 7218¦S24B05_S08 | 2 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -208 | 0
612 |  | CONEXIÓN CENTRALITAS INCENDIOS | 1101915959 | 1 | 2025-10-03 |  | 4300353869 | 10 | 2025-10-07 | 2025-10-07 |  | 2026-01-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦S24B05_S1076 | 116 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -82 | 0
613 | 39121004 | Fuente de alimentaci&#243;n conmutada Ex | 1101915964 | 1 | 2025-10-03 |  | 4800003318 | 80 | 2025-10-03 |  |  | 2025-10-04 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 6273787 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -201 | 0
614 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101916037 | 1 | 2025-10-03 |  | 4200630828 | 10 | 2025-10-10 | 2025-10-14 |  | 2025-12-31 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2578_1001 | 82 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -113 | 0
615 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101916037 | 2 | 2025-10-03 |  | 4200630828 | 20 | 2025-10-10 | 2025-10-14 |  | 2025-12-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2578_1001 | 82 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -113 | 0
616 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101916037 | 3 | 2025-10-03 |  | 4200630828 | 30 | 2025-10-10 | 2025-10-14 |  | 2025-12-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2578_1001 | 82 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -113 | 0
617 | 39121421 | Conector de potencia industrial Macho, F | 1101916440 | 1 | 2025-10-06 |  | 4800003320 | 280 | 2025-10-06 |  |  | 2025-10-07 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 5306101 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -198 | 0
618 | 55121704 | Se&#241;al de protecci&#243;n contra inc | 1101917916 | 1 | 2025-10-09 |  | 4800003327 | 50 | 2025-10-08 |  |  | 2025-10-10 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2209872 |  | 0 | 0 |  | 7218¦JA2582_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -195 | 0
619 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101918375 | 1 | 2025-10-09 |  | 4200631682 | 10 | 2025-10-16 | 2025-10-21 |  | 2025-12-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2578_1001 | 76 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -113 | 0
620 | 39121529 | Contactor ABB ESB25-40N-01 ESB de 4 polo | 1101918581 | 1 | 2025-10-10 |  | 4800003329 | 630 | 2025-10-09 |  |  | 2025-10-11 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2111460 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -194 | 0
621 |  | PROGRAMACIÓN CENTRALITA DE INCENDIOS | 1101920430 | 1 | 2025-10-15 |  | 4300354754 | 10 | 2025-10-23 | 2025-11-18 |  | 2025-11-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | IBERCOIN INGENIEROS, S.L. |  |  |  | 2 | 2 |  | 7218¦S24B05_S1076 | 38 | - | [5 empty] | 1 |  | 0% |  |  |  |  | 10 | 100% |  | -144 | 0
622 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101920785 | 1 | 2025-10-16 |  | 4200633117 | 10 | 2025-10-28 | 2025-10-30 |  | 2025-12-08 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | FELIPE DE MARCO, S.A. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 41 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -136 | 0
623 | 7889090900000 | ROPA LABORAL CATALOGO INDRA | 1101921504 | 1 | 2025-10-20 |  | 4900011607 | 10 | 2025-10-20 |  |  | 2025-12-31 | 0 | 8 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | VESTUARIO Y PROTECCION LABORAL JOYS | INDRA SISTEMAS S.A. | 7889090900000 |  | 0 | 0 |  | 7218¦JA2594_1001 | 72 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -113 | 0
624 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101921894 | 1 | 2025-10-20 |  | 4200634297 | 10 | 2025-11-04 | 2025-11-05 |  | 2025-12-31 | 30 | 8 | Liberado | 7 | 7 | 7 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1074 | 57 | - |  | YES | 7 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -113 | 0
625 | 31201503 | Cinta de enmascarar de Papel 3M SCOTCH 1 | 1101923738 | 1 | 2025-10-23 |  | 4800003359 | 170 | 2025-10-23 |  |  | 2025-10-24 | 0 | 0 |  | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 1240913 |  | 0 | 0 |  | 7218¦S24B05_S1071 | 1 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -181 | 0
626 | 39121402 | Clavija Kopp de 2P de color Negro, para | 1101923956 | 1 | 2025-10-23 |  | 4800003359 | 620 | 2025-10-23 |  |  | 2025-10-24 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2425782 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -181 | 0
627 | 3220190900000 | ACCESORIOS PARA MONITORES / TELEVISIONES | 1101926538 | 1 | 2025-10-29 |  | 4200634682 | 10 | 2025-11-06 | 2025-11-06 |  | 2025-11-11 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | DELL COMPUTER, S.A. | OTROS FABRICANTES | 3220190900000 |  | 0 | 0 |  | 7218¦S24B05_P10261 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -163 | 0
628 | 31161716 | Tuerca autoblocante 1/4-28 (NE)plg RS PR | 1101927261 | 1 | 2025-10-30 |  | 4800003376 | 140 | 2025-10-30 |  |  | 2025-10-31 | 0 | 0 |  | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2451276 |  | 0 | 0 |  | 7218¦JA2583_1001 | 1 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -174 | 0
629 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101930054 | 1 | 2025-11-06 |  | 4200636221 | 10 | 2025-11-14 | 2025-11-17 |  | 2026-01-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SARVER S.L. | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦S24B05_S1076 | 78 | - |  |  |  | YES | 1 | 0 |  | 0% |  |  |  |  | 11 | 100% |  | -82 | 0
630 | 26121629 | Cable de conexi&#243;n RS PRO, &#225;rea | 1101935942 | 1 | 2025-11-20 |  | 4800003427 | 420 | 2025-11-19 |  |  | 2025-11-21 | 0 | 0 |  | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 8114431 |  | 0 | 0 |  | 7218¦JA2581_1001 | 2 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -153 | 0
631 | 32111503 | Bombilla LED, 4,2 W, casquillo GU10, Bla | 1101939635 | 1 | 2025-11-28 |  | 4800003446 | 170 | 2025-11-27 |  |  | 2025-11-29 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2889633 |  | 0 | 0 |  | 7218¦JA2581_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -145 | 0
632 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101942089 | 1 | 2025-12-03 |  | 4200644071 | 50 | 2026-01-07 | 2026-01-08 |  | 2026-01-21 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | GRUPO ELECTRO-STOCKS,S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -92 | 0
633 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101942113 | 1 | 2025-12-03 |  | 4200644074 | 20 | 2026-01-07 | 2026-01-08 |  | 2026-01-21 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | GRUPO ELECTRO-STOCKS,S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2593_1001 | 14 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -92 | 0
634 | 32000000 | Prensaestopas HENSEL ASS de Poliamida Ne | 1101942236 | 1 | 2025-12-04 |  | 4800003490 | 60 | 2025-12-11 |  |  | 2025-12-05 | 0 | 0 |  | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 0117664 |  | 0 | 0 |  | 7218¦JA2582_1001 | -6 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -139 | 0
635 |  | PROCESSORS RACK (ENSAYOS MARKING CE) | 1101944187 | 1 | 2025-12-10 |  | 4300358085 | 10 | 2025-12-15 | 2026-01-19 |  | 2026-02-10 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 15033.70 |  | ALTER TECHNOLOGY-TÜV NORD |  |  |  | 0 | 0 |  | 7218¦S24B05_S05 | 57 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 12 | 100% |  | -72 | 0
636 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101948479 | 1 | 2025-12-17 |  | 4200645743 | 10 | 2026-01-20 | 2026-01-21 |  | 2026-02-03 | 40 | 8 | Liberado | 6 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | OTROS FABRICANTES | 1709800000500 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  |  |  | YES | 6 | 0 |  | 0% |  |  |  |  | 12 | 100% |  | -79 | 0
637 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101948508 | 1 | 2025-12-17 |  | 4200645756 | 10 | 2026-01-20 | 2026-01-21 |  | 2026-02-03 | 40 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | GRUPO ELECTRO-STOCKS,S.L.U | OTROS FABRICANTES | 1359900000500 |  | 0 | 0 |  | 7218¦JA2594_1001 | 14 | - |  |  |  | YES | 20 | 0 |  | 0% |  |  |  |  | 12 | 100% |  | -79 | 0
638 | 43211730 | Inyector de PoE 2 puertos, entrada 100 - | 1101949201 | 1 | 2025-12-18 |  | 4800003514 | 460 | 2025-12-18 |  |  | 2025-12-19 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2753549 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -125 | 0
639 | 26121629 | Cable de alimentaci&#243;n StarTech.com | 1101949201 | 2 | 2025-12-18 |  | 4800003514 | 470 | 2025-12-18 |  |  | 2025-12-19 | 0 | 0 |  | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | AMIDATA, S.A. |  | 2677825 |  | 0 | 0 |  | 7218¦JA2581_1001 | 1 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -125 | 0
640 | 1390706600000 | DEPURADOR HUMO 2250M3/HR 30CM PRE/HEPA | 1101955015 | 1 | 2026-01-14 |  | 4200645767 | 10 | 2026-01-20 | 2026-01-23 |  | 2026-02-15 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 3610.77 |  | MILEXIA IBÉRICA, S.A.U. | CONCEPT SMOKE | CEL SS-2000 |  | 1 | 0 |  | 7218¦S24B05_P10261 | 26 | - | [5 empty] | 0 |  | 0% | 4200645767 |  |  |  | 1 | 100% |  | -67 | 0
641 | 1709800000500 | COMPRA DIRECTA FERRETERIA Y HERRAMIENTAS | 1101958852 | 1 | 2026-01-21 |  |  | 0 |  |  |  |  | 40 | 8 |  | 3 | 0 | 0 | 0 | 0 | 0 |  | 0.00 | [5 empty] | 0 | 0 |  | 7218¦S24B05_P10261 | #VALUE! | - | [5 empty] | 0 |  | 0% |  |  |  |  | 1 | 100% |  | #VALUE! | #VALUE! | #VALUE! | X
642 | 3210202420000 | MARCADOR EINSCAN SE-H ADH3000 P/ESCAN 3D | 1101961041 | 1 | 2026-01-26 |  |  | 0 |  |  |  |  | 40 | 8 |  | 2 | 0 | 0 | 0 | 0 | 0 |  | 0.00 | [5 empty] | 0 | 0 |  | 7218¦JA2578_1001 | #VALUE! | - | [5 empty] | 0 |  | 0% |  |  |  |  | 1 | 100% |  | #VALUE! | #VALUE! | #VALUE! | X
643 | 1359900000500 | COMPRA DIRECTA ELECTRICOS/ELECTRONICOS | 1101962616 | 1 | 2026-01-28 |  |  | 0 |  |  |  |  | 40 | 8 |  | 3 | 0 | 0 | 0 | 0 | 0 |  | 0.00 | [5 empty] | 0 | 0 |  | 7218¦JA2582_1001 | #VALUE! | - | [5 empty] | 0 |  | 0% |  |  |  |  | 1 | 100% |  | #VALUE! | #VALUE! | #VALUE! | X
644 | 1204000333720 | CNC CIR 8-98 (3M) PLUG MS3476L8-98P | 1800108782 | 10 | 2024-06-14 |  | 4200569250 | 10 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 56 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L8-98P |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
645 | 1204100333620 | CNC CIR 8-98 (3M) RECEPT CRIMP MS3470L | 1800108782 | 20 | 2024-06-14 |  | 4200569260 | 10 | 2024-07-03 | 2024-07-04 |  | 2024-07-30 | 115 | 8 | Liberado | 20 | 20 | 40 | 0 | 20 | 20 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3470L8-98P |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -632 | 0
646 | 1204101933620 | CNC CIR 14-19 19P (M) MS3470L14-19P | 1800108782 | 30 | 2024-06-14 |  | 4200569260 | 20 | 2024-07-03 | 2024-07-04 |  | 2024-07-30 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3470L14-19P |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -632 | 0
647 | 1204200430722 | CNC CIR 13-4 4M PLUG CRIMP | 1800108782 | 40 | 2024-06-14 |  | 4200569022 | 10 | 2024-07-02 |  | BORR | 2024-07-15 | 65 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 199.88 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZC4PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
648 | 1204200430722 | CNC CIR 13-4 4M PLUG CRIMP | 1800108782 | 40 | 2024-06-14 |  | 4200569161 | 20 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 65 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZC4PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
649 | 1204200630320 | CNC CIR 9-35 6M PLUG D38999/26ZA35PN | 1800108782 | 50 | 2024-06-14 |  | 4200569022 | 20 | 2024-07-02 |  | BORR | 2024-07-15 | 35 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 93.74 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZA35PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
650 | 1204200630320 | CNC CIR 9-35 6M PLUG D38999/26ZA35PN | 1800108782 | 50 | 2024-06-14 |  | 4200569161 | 30 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 35 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZA35PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
651 | 1204201130020 | CNC CIR 19-11P/M PLUG RECT AL ZN/NI R-N | 1800108782 | 60 | 2024-06-14 |  | 4200569161 | 40 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZF11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
652 | 1204201130020 | CNC CIR 19-11P/M PLUG RECT AL ZN/NI R-N | 1800108782 | 60 | 2024-06-14 |  | 4200569022 | 30 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 128.62 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZF11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
653 | 1204201930820 | CNC CIR 15-19 19M PLUG RECT ZN/NI ROT-N | 1800108782 | 70 | 2024-06-14 |  | 4200569161 | 50 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZD19PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
654 | 1204201930820 | CNC CIR 15-19 19M PLUG RECT ZN/NI ROT-N | 1800108782 | 70 | 2024-06-14 |  | 4200569022 | 40 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 89.76 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZD19PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
655 | 1204204130820 | CNC CIR 21-41 41M PLUG RECT ZN/NI ROT-N | 1800108782 | 80 | 2024-06-14 |  | 4200569022 | 50 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 14 | 14 | 0 | 14 | 0 | 0 |  | 938.28 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZG41PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
656 | 1204204130820 | CNC CIR 21-41 41M PLUG RECT ZN/NI ROT-N | 1800108782 | 80 | 2024-06-14 |  | 4200569165 | 10 | 2024-07-02 | 2024-07-10 |  | 2024-07-15 | 40 | 8 | Liberado | 14 | 14 | 14 | 0 | 14 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/26ZG41PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
657 | 1204204131820 | CNC CIR 21-41 41M PLUG RECT ZN/NI ROT-A | 1800108782 | 90 | 2024-06-14 |  | 4200569022 | 60 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 3 | 3 | 0 | 3 | 0 | 0 |  | 486.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZG41PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
658 | 1204204131820 | CNC CIR 21-41 41M PLUG RECT ZN/NI ROT-A | 1800108782 | 90 | 2024-06-14 |  | 4200569161 | 60 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZG41PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
659 | 1204205530021 | CNC CIR 23-55P/M PLUG RECT AL ZN/NI R-A | 1800108782 | 100 | 2024-06-14 |  | 4200569022 | 70 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 295.46 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZH55PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
660 | 1204205530021 | CNC CIR 23-55P/M PLUG RECT AL ZN/NI R-A | 1800108782 | 100 | 2024-06-14 |  | 4200569161 | 70 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZH55PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
661 | 1204205530820 | CNC CIR 23-55 55M PLUG RECT ZN/NI ROT-N | 1800108782 | 110 | 2024-06-14 |  | 4200569022 | 80 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 16 | 16 | 0 | 16 | 0 | 0 |  | 1300.80 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZH55PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
662 | 1204205530820 | CNC CIR 23-55 55M PLUG RECT ZN/NI ROT-N | 1800108782 | 110 | 2024-06-14 |  | 4200569168 | 10 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 16 | 16 | 16 | 0 | 16 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZH55PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 16 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
663 | 1204206631820 | CNC CIR 19-35 66M STRAIGHT PLUG D38999 A | 1800108782 | 120 | 2024-06-14 |  | 4200569168 | 20 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 75 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZF35PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
664 | 1204206631820 | CNC CIR 19-35 66M STRAIGHT PLUG D38999 A | 1800108782 | 120 | 2024-06-14 |  | 4200569022 | 90 | 2024-07-02 |  | BORR | 2024-07-15 | 75 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 219.74 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZF35PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
665 | 1204300430820 | CNC CIR 13-4 4M RECPT WALL ZN/NI ROT-N | 1800108782 | 130 | 2024-06-14 |  | 4200569168 | 30 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 9 | 9 | 9 | 0 | 9 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZC4PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
666 | 1204300430820 | CNC CIR 13-4 4M RECPT WALL ZN/NI ROT-N | 1800108782 | 130 | 2024-06-14 |  | 4200569022 | 100 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 9 | 9 | 0 | 9 | 0 | 0 |  | 532.62 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZC4PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
667 | 1204300431820 | CNC CIR 13-4 4M RECPT WALL ZN/NI ROT-A | 1800108782 | 140 | 2024-06-14 |  | 4200569161 | 80 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZC4PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
668 | 1204300431820 | CNC CIR 13-4 4M RECPT WALL ZN/NI ROT-A | 1800108782 | 140 | 2024-06-14 |  | 4200569022 | 110 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 3 | 3 | 0 | 3 | 0 | 0 |  | 291.75 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZC4PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
669 | 1204300730820 | CNC CIR 11-99 7M RECPT WALL ZN/NI ROT-N | 1800108782 | 150 | 2024-06-14 |  | 4200569161 | 90 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZB99PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
670 | 1204300730820 | CNC CIR 11-99 7M RECPT WALL ZN/NI ROT-N | 1800108782 | 150 | 2024-06-14 |  | 4200569022 | 120 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 62.87 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZB99PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
671 | 1204301130020 | CNC CIR 21-11 11P(M) RECEP CRIMP PANEL | 1800108782 | 160 | 2024-06-14 |  | 4200569022 | 130 | 2024-07-02 |  | BORR | 2024-07-15 | 30 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 154.69 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZG11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
672 | 1204301130020 | CNC CIR 21-11 11P(M) RECEP CRIMP PANEL | 1800108782 | 160 | 2024-06-14 |  | 4200569161 | 100 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZG11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
673 | 1204301130021 | CNC CIR 19-11P/M RCPT RECT AL ZN/NI R-N | 1800108782 | 170 | 2024-06-14 |  | 4200569022 | 140 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 139.94 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZF11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
674 | 1204301130021 | CNC CIR 19-11P/M RCPT RECT AL ZN/NI R-N | 1800108782 | 170 | 2024-06-14 |  | 4200569161 | 110 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZF11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
675 | 1204301130620 | CNC CIR 21-11 11M RECEP WALL CRIMP ROT-N | 1800108782 | 180 | 2024-06-14 |  | 4200569161 | 120 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZG11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
676 | 1204301130620 | CNC CIR 21-11 11M RECEP WALL CRIMP ROT-N | 1800108782 | 180 | 2024-06-14 |  | 4200569022 | 150 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 229.70 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZG11PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
677 | 1204301930821 | CNC CIR 15-19 19M RECPT WALL ZN/NI ROT-N | 1800108782 | 190 | 2024-06-14 |  | 4200569161 | 130 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZD19PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
678 | 1204301930821 | CNC CIR 15-19 19M RECPT WALL ZN/NI ROT-N | 1800108782 | 190 | 2024-06-14 |  | 4200569022 | 160 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 79.95 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZD19PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
679 | 1204301931820 | CNC CIR 15-19 19M RECPT WALL ZN/NI ROT-A | 1800108782 | 200 | 2024-06-14 |  | 4200569022 | 170 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 94.21 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZD19PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
680 | 1204301931820 | CNC CIR 15-19 19M RECPT WALL ZN/NI ROT-A | 1800108782 | 200 | 2024-06-14 |  | 4200569161 | 140 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZD19PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
681 | 1204304130820 | CNC CIR 21-41 41M RECPT WALL ZN/NI ROT-N | 1800108782 | 210 | 2024-06-14 |  | 4200569022 | 180 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 4 | 4 | 0 | 4 | 0 | 0 |  | 379.24 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZG41PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
682 | 1204304130820 | CNC CIR 21-41 41M RECPT WALL ZN/NI ROT-N | 1800108782 | 210 | 2024-06-14 |  | 4200569161 | 150 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZG41PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
683 | 1204305530022 | CNC CIR 23-55P/M RCPT RECT AL ZN/NI R-A | 1800108782 | 220 | 2024-06-14 |  | 4200569165 | 20 | 2024-07-02 | 2024-07-10 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/20ZH55PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
684 | 1204305530022 | CNC CIR 23-55P/M RCPT RECT AL ZN/NI R-A | 1800108782 | 220 | 2024-06-14 |  | 4200569022 | 190 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 547.08 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZH55PA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
685 | 1204305530820 | CNC CIR 23-55 55M RECPT WALL ZN/NI ROT-N | 1800108782 | 230 | 2024-06-14 |  | 4200569165 | 30 | 2024-07-02 | 2024-07-10 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/20ZH55PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
686 | 1204305530820 | CNC CIR 23-55 55M RECPT WALL ZN/NI ROT-N | 1800108782 | 230 | 2024-06-14 |  | 4200569022 | 200 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 151.88 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZH55PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
687 | 1209990030120 | CONTACTO MACHO M39029/4-111 | 1800108782 | 240 | 2024-06-14 |  | 4200569159 | 170 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 30 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M39029/4-111 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
688 | 1212090200020 | PIN H CRIMP CNC SUB-D #20 AWG20-24(0,2-0 | 1800108782 | 250 | 2024-06-14 |  | 4200569159 | 180 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 50 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M39029/63-368 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
689 | 1214000333721 | CNC CIR 8-98 (3H) MS3476L8-98S | 1800108782 | 260 | 2024-06-14 |  | 4200569250 | 20 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 45 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L8-98S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
690 | 1214001933721 | CNC CIR AER 14-19 (19H) MS3476L14-19S | 1800108782 | 270 | 2024-06-14 |  | 4200569250 | 30 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 35 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L14-19S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
691 | 1214001933722 | CNC CIR 14-19 (19H) MS3476L14-19SW | 1800108782 | 280 | 2024-06-14 |  | 4200569250 | 40 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 56 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L14-19SW |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
692 | 1214001933723 | CNC CIR 14-19 19P (H) PLUG MS3476L14-19S | 1800108782 | 290 | 2024-06-14 |  | 4200568992 | 70 | 2024-07-01 | 2024-07-05 |  | 2024-07-22 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L14-19SX |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
693 | 1214002432621 | CNC CIR 16-24 24/H PLUG M83723/75R16247 | 1800108782 | 300 | 2024-06-14 |  | 4200569168 | 40 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 56 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M83723/75R16247 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
694 | 1214002432621 | CNC CIR 16-24 24/H PLUG M83723/75R16247 | 1800108782 | 300 | 2024-06-14 |  | 4200569022 | 210 | 2024-07-02 |  | BORR | 2024-07-15 | 56 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 237.88 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M83723/75R16247 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
695 | 1214002432622 | CNC CIR 16-24 24/H PLUG M83723/75R16248 | 1800108782 | 310 | 2024-06-14 |  | 4200569022 | 220 | 2024-07-02 |  | BORR | 2024-07-15 | 56 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 241.74 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M83723/75R16248 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
696 | 1214002432622 | CNC CIR 16-24 24/H PLUG M83723/75R16248 | 1800108782 | 310 | 2024-06-14 |  | 4200569168 | 50 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 56 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M83723/75R16248 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
697 | 1214002633727 | CNC CIR 16-26 26P/H PLUG MS3476L16-26S | 1800108782 | 320 | 2024-06-14 |  | 4200569250 | 50 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L16-26S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
698 | 1214002633742 | CNC CIR 16-26 (26H) MS3476L16-26SY | 1800108782 | 330 | 2024-06-14 |  | 4200569250 | 60 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 56 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L16-26SY |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
699 | 1214002633762 | CNC CIR 16-26 (26H) MS3476L16-26SW | 1800108782 | 340 | 2024-06-14 |  | 4200569250 | 70 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 56 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L16-26SW |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
700 | 1214003233721 | CNC CIR 18-32 32S (H) MS3476L18-32SN | 1800108782 | 350 | 2024-06-14 |  | 4200568992 | 80 | 2024-07-01 | 2024-07-05 |  | 2024-07-22 | 125 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L18-32SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
701 | 1214003233761 | CNC CIR 18-32 (32H) MS3476L18-32SW | 1800108782 | 360 | 2024-06-14 |  | 4200568992 | 90 | 2024-07-01 | 2024-07-05 |  | 2024-07-22 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L18-32SW |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
702 | 1214004130021 | CNC CIR 20-41S/H PLUG RECT ELECT-NI R-Y | 1800108782 | 370 | 2024-06-14 |  | 4200569161 | 180 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | MS3476L20-41SY |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
703 | 1214004130021 | CNC CIR 20-41S/H PLUG RECT ELECT-NI R-Y | 1800108782 | 370 | 2024-06-14 |  | 4200569022 | 230 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 235.65 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | MS3476L20-41SY |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
704 | 1214004133721 | CNC CIR 20-41 (41H) MS3476L20-41S | 1800108782 | 380 | 2024-06-14 |  | 4200569250 | 80 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L20-41S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
705 | 1214005533721 | CNC CIR 22-55 (55H) MS3476L22-55S | 1800108782 | 390 | 2024-06-14 |  | 4200569260 | 30 | 2024-07-03 | 2024-07-04 |  | 2024-07-15 | 56 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L22-55S |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
706 | 1214005533760 | CNC CIR 22-55 55H PLUG RECT CRIMP ROT-W | 1800108782 | 400 | 2024-06-14 |  | 4200568992 | 100 | 2024-07-01 | 2024-07-05 |  | 2024-07-22 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L22-55SW |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
707 | 1214006133721 | CNC CIR 24-61 (61H) MS3476L24-61S | 1800108782 | 410 | 2024-06-14 |  | 4200569260 | 40 | 2024-07-03 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L24-61S |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
708 | 1214006133761 | CNC CIR 24-61 (61H) MS3476L24-61SW | 1800108782 | 420 | 2024-06-14 |  | 4200569250 | 90 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3476L24-61SW |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
709 | 1214100333620 | CNC CIR 08-98 3H RECEPT BAYO CRIMP ROT-N | 1800108782 | 430 | 2024-06-14 |  | 4200569250 | 100 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 56 | 8 | Liberado | 20 | 20 | 40 | 0 | 20 | 20 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3470L8-98S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
710 | 1214101033620 | CNC CIR 12-10 10P (H) MS3470L12-10S | 1800108782 | 440 | 2024-06-14 |  | 4200568992 | 110 | 2024-07-01 | 2024-07-05 |  | 2024-07-22 | 65 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3470L12-10S |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
711 | 1214101933621 | CNC CIR 14-19 (19H) MS3470L14-19S | 1800108782 | 450 | 2024-06-14 |  | 4200569250 | 110 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 55 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS3470L14-19S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
712 | 1214105330530 | CNC CIR 18-53 53H RECPT WALL EL-NI ROT-N | 1800108782 | 460 | 2024-06-14 |  | 4200569250 | 120 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY STANDARDS | MS27472E18F53S |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
713 | 1214200430721 | CNC CIR 13-4 4H PLUG D38999/26ZC4SN | 1800108782 | 470 | 2024-06-14 |  | 4200569022 | 240 | 2024-07-02 |  | BORR | 2024-07-15 | 60 | 8 |  | 9 | 9 | 0 | 9 | 0 | 0 |  | 678.51 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZC4SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
714 | 1214200430721 | CNC CIR 13-4 4H PLUG D38999/26ZC4SN | 1800108782 | 470 | 2024-06-14 |  | 4200569161 | 190 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 60 | 8 | Liberado | 9 | 9 | 9 | 0 | 9 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZC4SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
715 | 1214201130020 | CNC CIR 19-11S/H PLUG RECT AL ZN/NI R-N | 1800108782 | 480 | 2024-06-14 |  | 4200569161 | 200 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZF11SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
716 | 1214201130020 | CNC CIR 19-11S/H PLUG RECT AL ZN/NI R-N | 1800108782 | 480 | 2024-06-14 |  | 4200569022 | 250 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 148.20 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZF11SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
717 | 1214201930820 | CNC CIR 15-19 19H PLUG RECT ZN/NI ROT-N | 1800108782 | 490 | 2024-06-14 |  | 4200569161 | 210 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZD19SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
718 | 1214201930820 | CNC CIR 15-19 19H PLUG RECT ZN/NI ROT-N | 1800108782 | 490 | 2024-06-14 |  | 4200569022 | 260 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 121.83 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZD19SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
719 | 1214201931820 | CNC CIR 15-19 19H PLUG RECT ZN/NI ROT-A | 1800108782 | 500 | 2024-06-14 |  | 4200569161 | 220 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZD19SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
720 | 1214201931820 | CNC CIR 15-19 19H PLUG RECT ZN/NI ROT-A | 1800108782 | 500 | 2024-06-14 |  | 4200569022 | 270 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 112.83 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZD19SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
721 | 1214204130820 | CNC CIR 21-41 41H PLUG RECT ZN/NI ROT-N | 1800108782 | 510 | 2024-06-14 |  | 4200569161 | 230 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZG41SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
722 | 1214204130820 | CNC CIR 21-41 41H PLUG RECT ZN/NI ROT-N | 1800108782 | 510 | 2024-06-14 |  | 4200569022 | 280 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 4 | 4 | 0 | 4 | 0 | 0 |  | 474.20 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZG41SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
723 | 1214205530820 | CNC CIR 23-55 55H PLUG RECT ZN/NI ROT-N | 1800108782 | 520 | 2024-06-14 |  | 4200569161 | 240 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZH55SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
724 | 1214205530820 | CNC CIR 23-55 55H PLUG RECT ZN/NI ROT-N | 1800108782 | 520 | 2024-06-14 |  | 4200569022 | 290 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 173.31 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZH55SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
725 | 1214300431820 | CNC CIR 13-04 4H RECEPT CRMP ZN/NI ROT-N | 1800108782 | 530 | 2024-06-14 |  | 4200569161 | 250 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZC4SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
726 | 1214300431820 | CNC CIR 13-04 4H RECEPT CRMP ZN/NI ROT-N | 1800108782 | 530 | 2024-06-14 |  | 4200569022 | 300 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 156.68 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZC4SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
727 | 1214300631720 | CNC CIR 09-35 6H RECEPT CRMP ZN/NI ROT-N | 1800108782 | 540 | 2024-06-14 |  | 4200569161 | 260 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZA35SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
728 | 1214300631720 | CNC CIR 09-35 6H RECEPT CRMP ZN/NI ROT-N | 1800108782 | 540 | 2024-06-14 |  | 4200569022 | 310 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 46.24 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZA35SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
729 | 1214301130022 | CNC CIR 19-11S/H RCPT RECT AL ZN/NI R-N | 1800108782 | 550 | 2024-06-14 |  | 4200569161 | 270 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZF11SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
730 | 1214301130022 | CNC CIR 19-11S/H RCPT RECT AL ZN/NI R-N | 1800108782 | 550 | 2024-06-14 |  | 4200569022 | 320 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 159.46 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZF11SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
731 | 1214301130620 | CNC CIR 21-11 11H RECEP WALL CRIMP ROT-N | 1800108782 | 560 | 2024-06-14 |  | 4200569161 | 280 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZG11SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
732 | 1214301130620 | CNC CIR 21-11 11H RECEP WALL CRIMP ROT-N | 1800108782 | 560 | 2024-06-14 |  | 4200569022 | 330 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 142.96 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZG11SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
733 | 1214303734920 | CNC CIR 15-35 37H RECPT CRMP ZN/NI ROT-N | 1800108782 | 570 | 2024-06-14 |  | 4200569161 | 290 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZD35SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
734 | 1214303734920 | CNC CIR 15-35 37H RECPT CRMP ZN/NI ROT-N | 1800108782 | 570 | 2024-06-14 |  | 4200569022 | 340 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 111.40 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZD35SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
735 | 1214304131820 | CNC CIR 21-41 41H RECPT WALL ZN/NI ROT-A | 1800108782 | 580 | 2024-06-14 |  | 4200569161 | 300 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZG41SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
736 | 1214304131820 | CNC CIR 21-41 41H RECPT WALL ZN/NI ROT-A | 1800108782 | 580 | 2024-06-14 |  | 4200569022 | 350 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 3 | 3 | 0 | 3 | 0 | 0 |  | 354.15 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZG41SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
737 | 1214305330820 | CNC CIR 23-54 53H RECPT WALL ZN/NI ROT-N | 1800108782 | 590 | 2024-06-14 |  | 4200569165 | 40 | 2024-07-02 | 2024-07-10 | BORR | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 57.41 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/20ZH54SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
738 | 1214305330820 | CNC CIR 23-54 53H RECPT WALL ZN/NI ROT-N | 1800108782 | 590 | 2024-06-14 |  | 4200569871 | 10 | 2024-07-09 | 2024-07-10 |  | 2024-07-31 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZH54SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 22 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
739 | 1214305530020 | CNC CIR 23-55S/H RCPT RECT AL ZN/NI R-A | 1800108782 | 600 | 2024-06-14 |  | 4200569161 | 320 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZH55SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
740 | 1214305530020 | CNC CIR 23-55S/H RCPT RECT AL ZN/NI R-A | 1800108782 | 600 | 2024-06-14 |  | 4200569022 | 360 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 335.04 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZH55SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
741 | 1214305530821 | CNC CIR 23-55 55H RECPT WALL ZN/NI ROT-N | 1800108782 | 610 | 2024-06-14 |  | 4200569165 | 50 | 2024-07-02 | 2024-07-10 |  | 2024-07-15 | 40 | 8 | Liberado | 16 | 16 | 32 | 0 | 16 | 16 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/20ZH55SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 32 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
742 | 1214305530821 | CNC CIR 23-55 55H RECPT WALL ZN/NI ROT-N | 1800108782 | 610 | 2024-06-14 |  | 4200569022 | 370 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 16 | 16 | 0 | 16 | 0 | 0 |  | 1195.04 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZH55SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
743 | 1214306630021 | CNC CIR 19-35S/66H RCPT REC AL ZN/NI R-B | 1800108782 | 620 | 2024-06-14 |  | 4200569161 | 330 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZF35SB |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
744 | 1214306630021 | CNC CIR 19-35S/66H RCPT REC AL ZN/NI R-B | 1800108782 | 620 | 2024-06-14 |  | 4200569022 | 380 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 102.94 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZF35SB |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
745 | 1214306632020 | CNC CIR 19-35 66H RECPT CRMP ZN/NI ROT-A | 1800108782 | 630 | 2024-06-14 |  | 4200569161 | 340 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZF35SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
746 | 1214306632020 | CNC CIR 19-35 66H RECPT CRMP ZN/NI ROT-A | 1800108782 | 630 | 2024-06-14 |  | 4200569022 | 390 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 268.64 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/20ZF35SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
747 | 1214333530020 | CNC CIR 19-66 (66M) PLUG RECT CRIMP NIQU | 1800108782 | 640 | 2024-06-14 |  | 4200569165 | 60 | 2024-07-02 | 2024-07-10 |  | 2024-07-15 | 35 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/26ZF35PB |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
748 | 1214333530020 | CNC CIR 19-66 (66M) PLUG RECT CRIMP NIQU | 1800108782 | 640 | 2024-06-14 |  | 4200569022 | 400 | 2024-07-02 |  | BORR | 2024-07-15 | 35 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 169.15 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZF35PB |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
749 | 1214890160020 | CONTACTO H AWG16 M39029/5-116 | 1800108782 | 650 | 2024-06-14 |  | 4200569022 | 410 | 2024-07-02 |  | BORR | 2024-07-15 | 85 | 8 |  | 200 | 200 | 0 | 200 | 0 | 0 |  | 512.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M39029/5-116 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
750 | 1214890160020 | CONTACTO H AWG16 M39029/5-116 | 1800108782 | 650 | 2024-06-14 |  | 4200569161 | 350 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 85 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | M39029/5-116 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
751 | 1239024273050 | MANG AUTOSOLDABLE M83519/1-2 | 1800108782 | 660 | 2024-06-14 |  | 4200569022 | 420 | 2024-07-02 |  | BORR | 2024-07-15 | 30 | 8 |  | 300 | 300 | 0 | 300 | 0 | 0 |  | 357.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M83519/1-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
752 | 1239024273050 | MANG AUTOSOLDABLE M83519/1-2 | 1800108782 | 660 | 2024-06-14 |  | 4200569161 | 360 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 30 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | M83519/1-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
753 | 1239025439050 | MANG AUTOSOLDABLE 4,3MM M83519/1-3 | 1800108782 | 670 | 2024-06-14 |  | 4200569022 | 430 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 1000 | 1000 | 0 | 1000 | 0 | 0 |  | 670.00 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | M83519/1-3 |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
754 | 1239025439050 | MANG AUTOSOLDABLE 4,3MM M83519/1-3 | 1800108782 | 670 | 2024-06-14 |  | 4200569255 | 50 | 2024-07-03 | 2024-07-10 |  | 2024-07-25 | 40 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | M83519/1-3 |  | 0 | 0 |  | 7218¦JA2581_1001 | 22 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -637 | 0
755 | 1853200020100 | INSERTADOR/EXTRACTOR M81969/1-02 | 1800108782 | 680 | 2024-06-14 |  | 4200575219 | 30 | 2024-08-26 | 2024-08-26 |  | 2024-09-09 | 30 | 8 | Liberado | 30 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M81969/1-02 |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -591 | 0
756 | 7853200161200 | INSERTADOR/EXTRACTOR PINES 22D M81969/14 | 1800108782 | 690 | 2024-06-14 |  | 4200575219 | 40 | 2024-08-26 | 2024-08-26 |  | 2024-09-09 | 40 | 8 | Liberado | 30 | 500 | 500 | 0 | 0 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M81969/14-01 |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -591 | 0
757 | 1210790220200 | CONTACTO H #22 RECPT CRIMP TRAS ARINC600 | 1800108783 | 10 | 2024-06-14 |  | 4200583938 | 10 | 2024-10-31 | 2025-05-13 |  | 2024-12-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | SORIAU | 8660-206 |  | 1 | 0 |  | 7218¦JA2581_1001 | 57 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -482 | 0
758 | 1210790220200 | CONTACTO H #22 RECPT CRIMP TRAS ARINC600 | 1800108783 | 10 | 2024-06-14 |  | 4200583117 | 420 | 2024-10-28 | 2024-11-15 | BORR | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 198.31 |  | TTI INC. | SORIAU | 8660-206 |  | 0 | 0 |  | 7218¦JA2581_1001 | -105 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
759 | 1220100163401.LO | CBL FLEX 1XAWG16 600V PVDF AMA/VER ROHS | 1800108783 | 20 | 2024-06-14 |  | 4200571556 | 150 | 2024-07-19 | 2024-07-24 |  | 2024-07-26 | 60 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0111-16-45 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
760 | 1220100202010 | CBL FLEX 1XAWG20 PVDF 600V AM/VE ROHS | 1800108783 | 30 | 2024-06-14 |  | 4200568089 | 10 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 30 | 8 | Liberado | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0111-20-45 |  | 0 | 0 |  | 7218¦JA2581_1001 | 24 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
761 | 1220100222002.LO | CBL FLEX 1XAWG22 600V PVDF AM/VE CUSN | 1800108783 | 40 | 2024-06-14 |  | 4200575495 | 160 | 2024-08-28 | 2024-09-27 |  | 2024-09-25 | 65 | 8 | Liberado | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A0111-22-45 |  | 0 | 0 |  | 7218¦JA2581_1001 | 28 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -575 | 0
762 | 1220100242001 | CBL FLEX 1XAWG24 600V PVDF AMAR/VER ROHS | 1800108783 | 50 | 2024-06-14 |  | 4200571556 | 160 | 2024-07-19 | 2024-07-24 |  | 2024-07-26 | 85 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0111-24-45 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
763 | 1221100122500 | CBL APANT 1XAWG12 PVDF 600V AV | 1800108783 | 60 | 2024-06-14 |  | 4200575740 | 10 | 2024-08-30 | 2024-09-01 |  | 2024-09-20 | 30 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RAYCHEM CORP | 44A0111-12-54 |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -580 | 0
764 | 1221100182500 | CBL APAN 1 COND AWG18 VE DIAM=1,65MM | 1800108783 | 70 | 2024-06-14 |  | 4200570149 | 30 | 2024-07-10 | 2024-07-11 |  | 2024-08-07 | 30 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | RAYCHEM CORP | 44A0111-18-5 |  | 0 | 0 |  | 7218¦JA2581_1001 | 28 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -624 | 0
765 | 1221200202221 | CBL APA 2XAWG20 PVDF 600V CU/SN NE/BL-BL | 1800108783 | 80 | 2024-06-14 |  | 4200571560 | 120 | 2024-07-19 | 2024-10-11 |  | 2024-11-08 | 35 | 8 | Liberado | 600 | 600 | 600 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A1121-20-0/9-9 |  | 2 | 0 |  | 7218¦JA2581_1001 | 112 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -531 | 0
766 | 1221200222900 | CBL APANT 2XAWG22 PVDF 600V BL/NE-BL | 1800108783 | 90 | 2024-06-14 |  | 4200567987 | 120 | 2024-06-20 | 2024-11-15 |  | 2024-11-07 | 45 | 8 | Liberado | 1500 | 1500 | 1500 | 0 | 1500 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A1121-22-0/9-9 |  | 1 | 0 |  | 7218¦JA2581_1001 | 140 | - |  | YES | 1500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -532 | 0
767 | 1221300222000.LO | CBL APAN 3XAWG22 600V PVDF RO/AM/AZ ROHS | 1800108783 | 100 | 2024-06-14 |  | 4200571560 | 130 | 2024-07-19 | 2024-10-11 |  | 2024-10-10 | 85 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A1131-22-2/4/6-9 |  | 1 | 0 |  | 7218¦JA2581_1001 | 83 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -560 | 0
768 | 1221400222402.LO | CBL APANT 4XAWG22 CU-SN NE-RO-VE-BL/BL | 1800108783 | 110 | 2024-06-14 |  | 4200569218 | 210 | 2024-07-03 | 2025-08-22 |  | 2025-07-11 | 85 | 8 | Liberado | 100 | 977 | 977 | 0 | 977 | 0 | X | 0.00 |  | ARROW IBERIA ELECTRONICA SLU | TYCO ELECTR. FRANCE | 44A1141-22-0/2/5/9-9 |  | 1 | 0 |  | 7218¦JA2581_1001 | 373 | - |  | YES | 977 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -286 | 0
769 | 1222200182010.LO | CBLTRENZ 2XAWG18 PVDF 600V NE/RO ROHS | 1800108783 | 130 | 2024-06-14 |  | 4200571560 | 140 | 2024-07-19 | 2024-10-11 |  | 2024-11-08 | 65 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A0121-18-0/2 |  | 2 | 0 |  | 7218¦JA2581_1001 | 112 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -531 | 0
770 | 1222200202210 | CBL FLEX 2XAWG20 PVDF 600V NE/BL | 1800108783 | 140 | 2024-06-14 |  | 4200569380 | 510 | 2024-07-04 | 2024-09-26 |  | 2024-09-16 | 60 | 8 | Liberado | 600 | 600 | 600 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0121-20-0/9 |  | 0 | 0 |  | 7218¦JA2581_1001 | 74 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -584 | 0
771 | 1229991079506 | CBL FLEX TRENZ 2XAWG20 600V PVDF NGR/ROJ | 1800108783 | 150 | 2024-06-14 |  | 4200571560 | 150 | 2024-07-19 | 2024-10-11 |  | 2024-10-28 | 40 | 8 | Liberado | 300 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A0121-20-0/2 |  | 1 | 0 |  | 7218¦JA2581_1001 | 101 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -542 | 0
772 | 1233090000040 | CUERDA 0,060" PA WAX NYLON M43435-I-4-B | 1800108783 | 160 | 2024-06-14 |  | 4200568066 | 10 | 2024-06-21 | 2024-06-27 |  | 2024-08-02 | 30 | 8 | Liberado | 200 | 457 | 457 | 0 | 457 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | FEDERAL SPEC. | AA52080-B-4 BLACK |  | 0 | 0 |  | 7218¦JA2581_1001 | 42 | - |  | YES | 457 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -629 | 0
773 | 1233090000040 | CUERDA 0,060" PA WAX NYLON M43435-I-4-B | 1800108783 | 160 | 2024-06-14 |  | 4200568063 | 10 | 2024-06-21 |  | BORR | 2024-07-15 | 30 | 8 |  | 200 | 457.2 | 0 | 457.2 | 0 | 0 |  | 36.58 |  | Technipol Suministros, S.L. | FEDERAL SPEC. | AA52080-B-4 BLACK |  | 0 | 0 |  | 7218¦JA2581_1001 | 24 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
774 | 1204800600000 | CNC CIR PANEL 08-35 6P (M) AWG22 ROJO | 1800108784 | 10 | 2024-06-14 |  | 4200573052 | 30 | 2024-07-31 | 2024-11-11 |  | 2024-11-27 | 56 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SOURIAU | SOURIAU/FCI | 8STA0 08-35PN |  | 1 | 0 |  | 7218¦JA2581_1001 | 119 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -512 | 0
775 | 1209990080100 | PIN M ENGASTAR #22 WIRED END NSA937910 | 1800108784 | 20 | 2024-06-14 |  | 4200573048 | 20 | 2024-07-31 | 2024-07-31 |  | 2024-12-06 | 30 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | PEI GENESISUK LTD | SOURIAU/FCI | 8559-122 |  | 0 | 0 |  | 7218¦JA2581_1001 | 128 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -503 | 0
776 | 1215500702900 | CNC TWINAX CABLE CRIMP JACK | 1800108784 | 30 | 2024-06-14 |  | 4200573125 | 60 | 2024-08-01 | 2024-12-12 |  | 2024-08-19 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TROMPETER | CJ70-29 |  | 1 | 1 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
777 | 1219990110080 | PIN M ENGASTAR #20 WIRED END NSA937910 | 1800108784 | 40 | 2024-06-14 |  | 4200573052 | 100 | 2024-07-31 | 2024-11-11 |  | 2024-10-28 | 30 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | SOURIAU | SOURIAU/FCI | EN3155-016-M-20-18 |  | 1 | 1 |  | 7218¦JA2581_1001 | 89 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -542 | 0
778 | 1233590160200 | CLAMP MODULE 8559S | 1800108784 | 50 | 2024-06-14 |  | 4200573052 | 110 | 2024-07-31 | 2024-11-11 |  | 2024-12-03 | 85 | 8 | Liberado | 40 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | SOURIAU | SOURIAU | 8559S |  | 2 | 1 |  | 7218¦JA2581_1001 | 125 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -506 | 0
779 | 1234524199010 | CASQ TERM AUTSLD D=2,65-3,68MM PVDF/SNPB | 1800108784 | 60 | 2024-06-14 |  | 4200569198 | 80 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 40 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | SAE INC. | M83519/1-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
780 | 1237090062100 | BORNA RAIL SIZE22 5A 8559N2203B S/SELLAR | 1800108784 | 70 | 2024-06-14 |  | 4200573052 | 120 | 2024-07-31 | 2024-11-11 |  | 2024-10-28 | 40 | 8 | Liberado | 90 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SOURIAU | SOURIAU | 8559N2203B |  | 1 | 1 |  | 7218¦JA2581_1001 | 89 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -542 | 0
781 | 1237090072100 | BORNA RAIL SIZE20 7,5A 8559N2002B S/SELL | 1800108784 | 80 | 2024-06-14 |  | 4200573052 | 130 | 2024-07-31 | 2024-11-11 |  | 2024-10-28 | 90 | 8 | Liberado | 60 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SOURIAU | SOURIAU | 8559N2002B |  | 1 | 1 |  | 7218¦JA2581_1001 | 89 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -542 | 0
782 | 1239024433900 | MANG AUTOSOLD AWG22 C/TERMIN M83519/2-8 | 1800108784 | 90 | 2024-06-14 |  | 4200571556 | 170 | 2024-07-19 | 2024-07-24 |  | 2024-07-26 | 30 | 8 | Liberado | 500 | 500 | 0 | 500 | 0 | 0 |  | 500.00 |  | TTI INC. | TE CONNECTIVITY | S02-08-R |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - | [5 empty] | 1 |  | 0% | 4200571556 |  |  |  | 6 | 100% |  | -636 | 0
783 | 1239024593000 | MANG AUTOSOLDABLE DI= 5,97MM M83519/2-9 | 1800108784 | 100 | 2024-06-14 |  | 4200575740 | 20 | 2024-08-30 | 2024-09-01 |  | 2024-09-13 | 85 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RAYCHEM LTD | S02-09-R |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -587 | 0
784 | 0973528190300 | DISTRIBUTION PANEL ASSY | 1800108785 | 10 | 2024-06-14 |  | 4200579198 | 10 | 2024-09-30 | 2024-12-02 |  | 2025-03-21 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | AUXITEL, S.L. | INDRA SISTEMAS S.A. | 0973528190300 |  | 2 | 0 |  | 7218¦JA2581_1001 | 172 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -398 | 0
785 | 1202094770000 | ACC CNC SUB-D CIERRE TOR 4-40 UNC | 1800108785 | 20 | 2024-06-14 |  | 4200571180 | 140 | 2024-07-18 | 2024-09-16 |  | 2024-08-06 | 80 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | TTI INC. | ITT CANNON | D20419-18 |  | 0 | 0 |  | 7218¦JA2581_1001 | 19 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
786 | 1219000292300 | CAJA PORTACONTACTOS 10P (H) PASO 3,96MM | 1800108785 | 30 | 2024-06-14 |  | 4200577705 | 290 | 2024-09-18 | 2025-02-24 |  | 2024-10-02 | 80 | 8 | Liberado | 8 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | CONEXCON | 3940-2101 |  | 1 | 1 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -568 | 0
787 | 1219000990400 | CAJA PORTACONTACTOS 9/H CRIMP SERIE SL | 1800108785 | 40 | 2024-06-14 |  | 4200570128 | 120 | 2024-07-10 | 2024-07-11 |  | 2024-07-24 | 80 | 8 | Liberado | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MOLEX | 50-57-9409 |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -638 | 0
788 | 1219090030200 | TERMINAL HEMBRA CRIMPAR AWG24-30 MGRID | 1800108785 | 50 | 2024-06-14 |  | 4200570128 | 130 | 2024-07-10 | 2024-07-11 |  | 2024-07-24 | 50 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MOLEX | 50394-8052 |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -638 | 0
789 | 1219090080000 | CONTACTO ENGASTAR AWG18-26 1,14MM | 1800108785 | 60 | 2024-06-14 |  | 4200579147 | 50 | 2024-09-30 | 2024-10-04 |  | 2024-10-07 | 80 | 8 | Liberado | 80 | 80 | 80 | 0 | 80 | 0 | X | 0.00 |  | CENVALSA, S.L. | CENVALSA | 3979-2001 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 80 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -563 | 0
790 | 1219590030000 | TERMINAL PIN P/PASO 2,54MM | 1800108785 | 70 | 2024-06-14 |  | 4200568685 | 10 | 2024-06-27 | 2024-06-28 |  | 2024-07-15 | 45 | 8 | Liberado | 60 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ARRAY ELECTRONICA PROFESIONAL, S.A. | ARISTON | CO 3570 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
791 | 1220114152000 | CBL FLEX 1X1,5 MM2 PVC 750V AV H07VK | 1800108785 | 80 | 2024-06-14 |  | 4200575330 | 40 | 2024-08-27 | 2024-09-03 |  | 2024-09-03 | 30 | 8 | Liberado | 50 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | LUJISA, S.A. | AISMALIBAR | H07V-K/1X1,5MM2 AMARILLO/VERDE |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -597 | 0
792 | 1220114153000 | CBL FLEX 1X1,5MM2 PVC 450/750V H07V-K NE | 1800108785 | 90 | 2024-06-14 |  | 4200570846 | 60 | 2024-07-16 | 2024-08-23 |  | 2024-07-22 | 85 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | GENERAL CABLE | 1174106NG |  | 0 | 0 |  | 7218¦JA2581_1001 | 6 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
793 | 1220114153600 | CBL FLEX 1X1,5MM2 PVC 450/750V H07V-K AZ | 1800108785 | 100 | 2024-06-14 |  | 4200571213 | 10 | 2024-07-18 | 2024-07-18 |  | 2024-07-26 | 30 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | CERVI, S.L. | CERVI | 06901416 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
794 | 1220114153800 | CBL FLEX 1X1,5 MM2 PVC 750V GR H07VK | 1800108785 | 110 | 2024-06-14 |  | 4200570846 | 70 | 2024-07-16 | 2024-08-23 |  | 2024-07-22 | 55 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | GENERAL CABLE | GENLIS-F H07V-K/1X1,5MM2 GRIS |  | 0 | 0 |  | 7218¦JA2581_1001 | 6 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
795 | 1220114252000 | CBL FLEX 1X2,5 MM2 PVC 750V AV H07VK | 1800108785 | 120 | 2024-06-14 |  | 4200570846 | 80 | 2024-07-16 | 2024-08-23 |  | 2024-07-22 | 30 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | GENERAL CABLE | GENLIS-F H07V-K/1X2,5MM2 AMARILLO/VERDE |  | 0 | 0 |  | 7218¦JA2581_1001 | 6 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
796 | 1220114253000 | CBL FLEX 1X2,5 MM2 PVC 750V NE H07VK | 1800108785 | 130 | 2024-06-14 |  | 4200570846 | 90 | 2024-07-16 | 2024-08-23 |  | 2024-07-22 | 30 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | GENERAL CABLE | GENLIS-F H07V-K/1X2,5MM2 NEGRO |  | 0 | 0 |  | 7218¦JA2581_1001 | 6 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
797 | 1220114253100 | CBL FLEX 1X2,5 MM2 PVC 750V MA H07VK | 1800108785 | 140 | 2024-06-14 |  | 4200570846 | 100 | 2024-07-16 | 2024-08-23 |  | 2024-07-22 | 55 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | GENERAL CABLE | GENLIS-F H07V-K/1X2,5MM2 MARRON |  | 0 | 0 |  | 7218¦JA2581_1001 | 6 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
798 | 1220114253800 | CBL FLEX 1X2,5 MM2 PVC 750V GR H07VK | 1800108785 | 150 | 2024-06-14 |  | 4200575330 | 50 | 2024-08-27 | 2024-09-03 |  | 2024-09-03 | 30 | 8 | Liberado | 50 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | LUJISA, S.A. | AISMALIBAR | H07V-K/1X2,5MM2 GRIS |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -597 | 0
799 | 1221200243200.LO | CBL AP 2XAWG24 ASCB-D/CEPT-E1 125R FLPLM | 1800108785 | 160 | 2024-06-14 |  | 4200575045 | 10 | 2024-08-22 | 2024-08-23 |  | 2024-09-12 | 40 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | ELECTRONIC CBL SPEC | 322402 |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -588 | 0
800 | 1231024740900 | TUBO TERMORRETRACTIL 7,44-1,65MM L=30MM | 1800108785 | 170 | 2024-06-14 |  | 4200573771 | 50 | 2024-08-06 | 2024-12-10 |  | 2024-08-20 | 60 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TYCO ELECTR. FRANCE | ES-CAP-NO.2-B9-X-30MM |  | 1 | 1 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -611 | 0
801 | 1238524350200 | TERMINAL PREAISLADO REDONDO D=3,5MM ROJO | 1800108785 | 180 | 2024-06-14 |  | 4200574756 | 30 | 2024-08-19 | 2024-08-20 |  | 2024-08-26 | 110 | 8 | Liberado | 150 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CEMBRE | RF-M3,5 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -605 | 0
802 | 956002516 | TERM PRE REDONDO DIA 6MM AMARILLO | 1800108785 | 230 | 2024-06-14 |  | 4200573125 | 90 | 2024-08-01 | 2024-12-12 |  | 2024-08-19 | 85 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | OTROS FABRICANTES | 956002516 |  | 1 | 1 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
803 | 1233524550900 | BASE ANGULAR A/BRIDAS=5,5X1,7MM TALADRO | 1800108786 | 10 | 2024-06-14 |  | 4200570101 | 40 | 2024-07-10 | 2024-08-14 |  | 2024-07-15 | 45 | 8 | Liberado | 300 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | UNEX | 1257 |  | 0 | 0 |  | 7218¦JA2581_1001 | 5 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
804 | 0972888203300 | AUDIO MIXER PLATE | 1800108787 | 10 | 2024-06-14 |  | 4200568870 | 50 | 2024-07-01 | 2024-07-02 |  | 2025-03-08 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0972888203300 |  | 3 | 3 |  | 7218¦JA2584_1001 | 250 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -411 | 0
805 | 0972888133000 | ENCODER SUPPORT | 1800108788 | 10 | 2024-06-14 |  | 4200568870 | 60 | 2024-07-01 | 2024-07-02 |  | 2025-01-14 | 1 | 8 | Liberado | 2 | 2 | 4 | 0 | 2 | 2 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0972888133000 |  | 2 | 2 |  | 7218¦JA2587_1001 | 197 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -464 | 0
806 | 3210503440000 | EXTENSOR USB 2.0/CAT5 100MT | 1800108788 | 20 | 2024-06-14 |  | 4200570690 | 10 | 2024-07-15 | 2024-07-15 |  | 2024-08-12 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | CHARMEX INTERNACIONAL S.A. | GEFEN INC | EXT-USB2.0-LR |  | 0 | 0 |  | 7218¦JA2587_1001 | 28 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -619 | 0
807 | 3190700971100 | MONITOR IPS 24" FHD 1920X1080 300NITS | 1800108789 | 30 | 2024-06-14 |  | 4200568538 | 10 | 2024-06-27 | 2024-06-27 |  | 2024-07-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | HEWLETT PACKARD | E24T G5 |  | 0 | 0 |  | 7218¦JA2588_1001 | 18 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
808 | 3190402881100 | PANTALLA LED 15,6" 1920X1080 16:9 | 1800108790 | 10 | 2024-06-14 |  | 4200569360 | 10 | 2024-07-04 | 2024-07-04 |  | 2024-07-26 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | ASUS | MB16ACV |  | 1 | 1 |  | 7218¦JA2580_1001 | 22 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
809 | 1200300890200 | MOD CNC 8P #16 HL103 SELLADO | 1800108793 | 10 | 2024-06-14 |  | 4200572876 | 30 | 2024-07-30 | 2024-10-07 |  | 2024-11-15 | 85 | 8 | Liberado | 4 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001115 302 02 |  | 1 | 1 |  | 7218¦JA2581_1001 | 108 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -524 | 0
810 | 1200301890000 | MOD CNC 18P(2X12+4X16+12X20) HL103 SELL | 1800108793 | 20 | 2024-06-14 |  | 4200572876 | 40 | 2024-07-30 | 2024-10-07 |  | 2024-11-15 | 30 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001115 503 02 |  | 1 | 1 |  | 7218¦JA2581_1001 | 108 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -524 | 0
811 | 1200390091200 | PIN CNC MOD #12 CRIMP AWG12-14 HL103 | 1800108793 | 30 | 2024-06-14 |  | 4200569854 | 10 | 2024-07-09 | 2025-10-21 |  | 2024-09-19 | 30 | 8 | Liberado | 200 | 200 | 200 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL AIR-LB | 001104 400 02 |  | 1 | 1 |  | 7218¦JA2581_1001 | 72 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -581 | 0
812 | 1200390091600 | PIN CNC MOD #16 CRIMP AWG16-20 HL103 | 1800108793 | 40 | 2024-06-14 |  | 4200572876 | 60 | 2024-07-30 | 2024-10-07 |  | 2024-11-15 | 35 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001104 300 02 |  | 1 | 1 |  | 7218¦JA2581_1001 | 108 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -524 | 0
813 | 1200390091600 | PIN CNC MOD #16 CRIMP AWG16-20 HL103 | 1800108793 | 40 | 2024-06-14 |  | 4200568826 | 10 | 2024-06-28 | 2024-07-16 | BORR | 2024-07-15 | 35 | 8 | Liberado | 200 | 200 | 0 | 200 | 0 | 0 |  | 262.00 |  | PEI GENESISUK LTD | AMPHENOL AIR-LB | 001104 300 02 |  | 0 | 0 |  | 7218¦JA2581_1001 | 17 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
814 | 1200391070100 | ACC PROTECTOR 5 BORN CNC BJT TYP2 | 1800108793 | 50 | 2024-06-14 |  | 4200572888 | 10 | 2024-07-30 | 2024-07-30 |  | 2024-11-01 | 80 | 8 | Liberado | 6 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | PEI GENESISUK LTD | AMPHENOL AIR-LB | 001129 205 39 |  | 0 | 0 |  | 7218¦JA2581_1001 | 94 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -538 | 0
815 | 1200391070100 | ACC PROTECTOR 5 BORN CNC BJT TYP2 | 1800108793 | 50 | 2024-06-14 |  | 4200572876 | 80 | 2024-07-30 | 2024-10-07 | BORR | 2024-11-15 | 80 | 8 | Liberado | 6 | 10 | 0 | 10 | 0 | 0 |  | 311.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001129 205 39 |  | 1 | 1 |  | 7218¦JA2581_1001 | 108 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -524 | 0
816 | 1200394000101 | TOPE RETENC IZQUIERDO CNC MOD HL103/104 | 1800108793 | 60 | 2024-06-14 |  | 4200572888 | 20 | 2024-07-30 | 2024-07-30 |  | 2024-08-26 | 80 | 8 | Liberado | 6 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | PEI GENESISUK LTD | AMPHENOL AIR-LB | 001102 007 60 |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -605 | 0
817 | 1200394000101 | TOPE RETENC IZQUIERDO CNC MOD HL103/104 | 1800108793 | 60 | 2024-06-14 |  | 4200572876 | 90 | 2024-07-30 | 2024-10-07 | BORR | 2024-11-15 | 80 | 8 | Liberado | 6 | 100 | 0 | 100 | 0 | 0 |  | 1530.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001102 007 60 |  | 1 | 1 |  | 7218¦JA2581_1001 | 108 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -524 | 0
818 | 1200394000102 | TOPE RETENC DERECHO CNC MOD HL103/104 | 1800108793 | 70 | 2024-06-14 |  | 4200572888 | 30 | 2024-07-30 | 2024-07-30 |  | 2024-08-26 | 80 | 8 | Liberado | 6 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | PEI GENESISUK LTD | AMPHENOL AIR-LB | 001102 004 60 |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -605 | 0
819 | 1200394000102 | TOPE RETENC DERECHO CNC MOD HL103/104 | 1800108793 | 70 | 2024-06-14 |  | 4200572876 | 100 | 2024-07-30 | 2024-10-07 | BORR | 2024-11-15 | 80 | 8 | Liberado | 6 | 100 | 0 | 100 | 0 | 0 |  | 1529.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001102 004 60 |  | 1 | 1 |  | 7218¦JA2581_1001 | 108 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -524 | 0
820 | 1200394000103 | SEPARADOR MTJE MODULO BJT PTFE | 1800108793 | 80 | 2024-06-14 |  | 4200572888 | 40 | 2024-07-30 | 2024-07-30 |  | 2024-08-26 | 80 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | PEI GENESISUK LTD | AMPHENOL AIR-LB | 001126 000 39 |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -605 | 0
821 | 1200394000103 | SEPARADOR MTJE MODULO BJT PTFE | 1800108793 | 80 | 2024-06-14 |  | 4200572876 | 110 | 2024-07-30 | 2024-10-07 | BORR | 2024-10-04 | 80 | 8 | Liberado | 10 | 10 | 0 | 10 | 0 | 0 |  | 196.50 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001126 000 39 |  | 1 | 1 |  | 7218¦JA2581_1001 | 66 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -566 | 0
822 | 1200394000104 | SEPARADOR SH MTJE MODULO BJT PTFE | 1800108793 | 90 | 2024-06-14 |  | 4200572888 | 50 | 2024-07-30 | 2024-07-30 |  | 2024-09-30 | 30 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | PEI GENESISUK LTD | AMPHENOL AIR-LB | 001123 000 39 |  | 0 | 0 |  | 7218¦JA2581_1001 | 62 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -570 | 0
823 | 1200394000104 | SEPARADOR SH MTJE MODULO BJT PTFE | 1800108793 | 90 | 2024-06-14 |  | 4200572876 | 120 | 2024-07-30 | 2024-10-07 | BORR | 2024-10-04 | 30 | 8 | Liberado | 40 | 100 | 0 | 100 | 0 | 0 |  | 1442.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001123 000 39 |  | 1 | 1 |  | 7218¦JA2581_1001 | 66 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -566 | 0
824 | 1200394000106 | RAIL CONEXION 5 AGUJEROS D=5 | 1800108793 | 100 | 2024-06-14 |  | 4200571180 | 100 | 2024-07-18 | 2024-09-16 |  | 2024-09-09 | 80 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL AIR-LB | 024055 005 04 |  | 0 | 0 |  | 7218¦JA2581_1001 | 53 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -591 | 0
825 | 1202090240000 | PIN CNC SUB-D M 20-24AWG (ROLLO 400UD) | 1800108793 | 110 | 2024-06-14 |  | 4200569407 | 110 | 2024-07-04 | 2024-07-05 |  | 2024-07-15 | 50 | 8 | Liberado | 400 | 400 | 400 | 0 | 400 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | AMPHENOL CORP | 17RRD1M11400 |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
826 | 1202091050300 | CAPERUZA P/SUB-D 9 C/TOR UNC 4-40 POLIAM | 1800108793 | 120 | 2024-06-14 |  | 4200569854 | 100 | 2024-07-09 | 2025-10-21 |  | 2024-09-19 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL CORP | DPPK09-SLIM |  | 1 | 1 |  | 7218¦JA2581_1001 | 72 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -581 | 0
827 | 1204890370020 | ACC CNC CIR PIN #22 115VAC ORO | 1800108793 | 130 | 2024-06-14 |  | 4200566624 | 20 | 2024-06-11 | 2024-06-17 |  | 2024-07-15 | 30 | 8 | Liberado | 60 | 60 | 60 | 0 | 60 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | MILITARY SPECS. | EN3155-003F2222 |  | 0 | 0 |  | 7218¦JA2581_1001 | 34 | - |  | YES | 60 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
828 | 1238090100000 | TERMINAL CNC BJT M5 | 1800108793 | 140 | 2024-06-14 |  | 4200572876 | 790 | 2024-07-30 | 2024-10-07 |  | 2024-10-04 | 40 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AIR-LB | 001152 935 37 |  | 1 | 1 |  | 7218¦JA2581_1001 | 66 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
829 | 949170111-01 | CNC RECT SUB-D 9 M CRIMPAR 117RRE9P | 1800108793 | 150 | 2024-06-14 |  | 4200580627 | 10 | 2024-10-09 | 2024-10-11 |  | 2024-10-25 | 85 | 8 | Liberado | 35 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL CORP | 117RRE9P |  | 0 | 0 |  | 7218¦JA2581_1001 | 16 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -545 | 0
830 | 949170160-02 | CONTACTO HEMBRA 24AWG 17RRD1F11400 | 1800108793 | 160 | 2024-06-14 |  | 4200573368 | 30 | 2024-08-02 | 2024-12-12 |  | 2024-07-15 | 62 | 8 | Liberado | 415 | 415 | 415 | 0 | 415 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL CORP | 17RRD1F11400 |  | 0 | 0 |  | 7218¦JA2581_1001 | -18 | - |  | YES | 415 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
831 | N07025FA4H5T0 | CONECTOR SUB-D SIN PINES 25P M ENG. AMPH | 1800108793 | 170 | 2024-06-14 |  | 4200572876 | 810 | 2024-07-30 | 2024-10-07 |  | 2024-08-16 | 42 | 8 | Liberado | 35 | 35 | 35 | 0 | 35 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL CORP | 117RRB25P |  | 1 | 1 |  | 7218¦JA2581_1001 | 17 | - |  | YES | 35 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -615 | 0
832 | N07025SA4H5T0 | CONECTOR SUB-D SIN PINES 25P H ENG. AMPH | 1800108793 | 180 | 2024-06-14 |  | 4200572876 | 820 | 2024-07-30 | 2024-10-07 |  | 2024-07-15 | 58 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL CORP | 117RRB25S |  | 0 | 0 |  | 7218¦JA2581_1001 | -15 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
833 | 1230524620000 | FUND CBL 1/4" CBL 1/8-1/2" FR POLIES NEG | 1800108794 | 10 | 2024-06-14 |  | 4200571223 | 100 | 2024-07-18 | 2024-10-15 |  | 2024-08-08 | 50 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | WESTERN FILAMENT, INC | FR0250BK |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
834 | 1230525190000.LO | FUND CBL DI=6,35-19,05MM MALLA POLIES NE | 1800108794 | 20 | 2024-06-14 |  | 4200570458 | 20 | 2024-07-12 | 2024-07-18 |  | 2024-09-20 | 60 | 8 | Liberado | 1000 | 1006.5 | 1006.5 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | ALPHA WIRE | GRP-110-1/2BK005 |  | 0 | 0 |  | 7218¦JA2581_1001 | 70 | - |  | YES | 1006.5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -580 | 0
835 | 1230525310000.LO | FUNDA CBL DI=12.7-31.75MM MALLA POLIESTE | 1800108794 | 30 | 2024-06-14 |  | 4200570458 | 30 | 2024-07-12 | 2024-07-18 |  | 2024-09-20 | 30 | 8 | Liberado | 1000 | 1006.5 | 1006.5 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | ALPHA WIRE | GRP-110-3/4 |  | 0 | 0 |  | 7218¦JA2581_1001 | 70 | - |  | YES | 1006.5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -580 | 0
836 | 1231024160020 | TUBO TERMO 2:1 1/16" POLIOLEFINA NEGR RH | 1800108794 | 40 | 2024-06-14 |  | 4200574748 | 20 | 2024-08-19 | 2024-08-23 |  | 2024-09-02 | 50 | 8 | Liberado | 30 | 600 | 600 | 0 | 600 | 0 | X | 0.00 |  | TELKRON, S.A. | TE CONNECTIVITY | RNF-100-1/16-0-SP |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
837 | 1136090066200 | MAGNETOTER 1P 10A SNAP-IN BALANC I/O NEG | 1800108795 | 10 | 2024-06-14 |  | 4200568263 | 110 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 55 | 8 | Liberado | 6 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 3130-F110-H7T1-W01Q-10A |  | 0 | 0 |  | 7218¦JA2581_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
838 | 1136090066400 | MAGNETOTER 3P 16A SNAP-IN BALANC I/O NEG | 1800108795 | 20 | 2024-06-14 |  | 4200568263 | 120 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 52 | 8 | Liberado | 2 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 3130-F130-H7T1-W01Q-16A |  | 0 | 0 |  | 7218¦JA2581_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
839 | 1202107830000 | CNC SUB-D AD 78P M CRIMP RECT S/PINES | 1800108795 | 30 | 2024-06-14 |  | 4200570129 | 10 | 2024-07-10 | 2024-07-12 | BORR | 2024-12-04 | 40 | 8 | Liberado | 95 | 160 | 0 | 160 | 0 | 0 |  | 1160.00 |  | TTI INC. | MOLEX | 1731130072 |  | 0 | 0 |  | 7218¦JA2581_1001 | 147 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -505 | 0
840 | 1202107830000 | CNC SUB-D AD 78P M CRIMP RECT S/PINES | 1800108795 | 30 | 2024-06-14 |  | 4200570328 | 10 | 2024-07-11 | 2024-07-12 |  | 2024-07-19 | 40 | 8 | Liberado | 95 | 95 | 95 | 0 | 95 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | MOLEX | 1731130072 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 95 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -643 | 0
841 | 1208005030000 | CNC RJ45 PLUG 50-PIEZAS TRANSPARENTE | 1800108795 | 40 | 2024-06-14 |  | 4200567469 | 10 | 2024-06-18 | 2024-06-20 |  | 2024-07-15 | 30 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | BELKIN COMPONENTS | R6G088-R-10 |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
842 | 1229590910009 | CBL EQ DISPLAY PORT(M/M) 8K 22,8M NEGRO | 1800108795 | 50 | 2024-06-14 |  | 4200569265 | 10 | 2024-07-03 | 2024-07-05 |  | 2024-07-29 | 30 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | INGE VIDEO, S.A. | EXTRON ELECTRONICS | 26-727-75 |  | 1 | 1 |  | 7218¦JA2581_1001 | 26 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
843 | 1229598230401 | CBL EQ HDMI 1.4-M/M HD PRO P/150 L=45.7M | 1800108795 | 60 | 2024-06-14 |  | 4200569265 | 20 | 2024-07-03 | 2024-07-05 |  | 2024-07-29 | 105 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | INGE VIDEO, S.A. | EXTRON ELECTRONICS | 26-726-150 |  | 1 | 1 |  | 7218¦JA2581_1001 | 26 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
844 | 1231024320000 | TUBO TERMORRETRACTIL 3,2-0,58MM L=22MM P | 1800108795 | 70 | 2024-06-14 |  | 4200574737 | 30 | 2024-08-19 | 2024-08-23 |  | 2024-09-03 | 60 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TYCO ELECTR. FRANCE | PD-CAP-1/8-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 15 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -597 | 0
845 | 1231024320000 | TUBO TERMORRETRACTIL 3,2-0,58MM L=22MM P | 1800108795 | 70 | 2024-06-14 |  | 4200571038 | 30 | 2024-07-17 | 2024-08-23 | BORR | 2024-07-22 | 60 | 8 | Liberado | 200 | 200 | 0 | 200 | 0 | 0 |  | 134.98 |  | FARNELL COMPONENTS, S.L. | TYCO ELECTR. FRANCE | PD-CAP-1/8-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 5 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -640 | 0
846 | 1237000102900 | BORNERO 10P 2X12/8X20 | 1800108795 | 80 | 2024-06-14 |  | 4200569198 | 90 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | EADS NORMALISATION S | NSA 937 901 M 12 02 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
847 | 1237000262200 | BORNERO 21P AWG22-26 5A | 1800108795 | 90 | 2024-06-14 |  | 4200569198 | 100 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 110 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | EADS NORMALISATION S | NSA 937 901 M 22 06 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
848 | 1238524450600 | TERMINAL PREAISLADO REDONDO D=4,5MM AZUL | 1800108795 | 100 | 2024-06-14 |  | 4200567472 | 10 | 2024-06-18 | 2024-06-20 |  | 2024-07-15 | 110 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | LUJISA, S.A. | CEMBRE | BK-M5 |  | 0 | 0 |  | 7218¦JA2581_1001 | 27 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
849 | 1239990800000 | RAIL P/BORNEROS MODULARES 1M NSA937901 | 1800108795 | 110 | 2024-06-14 |  | 4200569198 | 110 | 2024-07-03 | 2024-07-04 |  | 2024-07-21 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | EADS NORMALISATION S | NSA937901RA1000 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
850 | 1587080101200 | ETIQUETA ADH TRANSF TERM 50,8X38,1MM TLS | 1800108795 | 120 | 2024-06-14 |  | 4200569417 | 30 | 2024-07-04 | 2024-07-11 |  | 2024-07-15 | 30 | 8 | Liberado | 2000 | 2000 | 2000 | 0 | 2000 | 0 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | BRADY | PTL-107-427 |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 2000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
851 | 1130622466200 | RELE DPDT 24VDC 10A LED/DIODO SUPR PLUG | 1800108796 | 10 | 2024-06-14 |  | 4200568068 | 10 | 2024-06-21 | 2024-06-21 |  | 2024-07-22 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | OMRON TATEISI | LY2ND224DC |  | 1 | 1 |  | 7218¦JA2581_1001 | 31 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
852 | 1139900462000 | PLACA MTJE ZOCALOS RELES SPDT/DPDT 18 LY | 1800108796 | 20 | 2024-06-14 |  | 4200568068 | 20 | 2024-06-21 | 2024-06-21 |  | 2024-07-22 | 50 | 8 | Liberado | 6 | 6 | 12 | 0 | 6 | 6 | X | 0.00 |  | GITEC CONTROL, S.L. | OMRON TATEISI | PYP-18 |  | 1 | 1 |  | 7218¦JA2581_1001 | 31 | - |  | YES | 12 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
853 | 1139900463000 | ZOCALO RELE SPDT/DPDT S/CBL LY | 1800108796 | 30 | 2024-06-14 |  | 4200568068 | 30 | 2024-06-21 | 2024-06-21 |  | 2025-04-29 | 50 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | OMRON TATEISI | PT08 |  | 3 | 1 |  | 7218¦JA2581_1001 | 312 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -359 | 0
854 | 1202091258100 | CAPERUZA P/SUB-D 25 C/TOR UNC 4-40 POLIA | 1800108796 | 40 | 2024-06-14 |  | 4200569756 | 70 | 2024-07-08 | 2024-07-10 |  | 2024-07-15 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | ELDON | DPPK25-SLIM |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
855 | 1202091379000 | CAPERUZA P/SUB-D 37 PLASTICO | 1800108796 | 50 | 2024-06-14 |  | 4200568537 | 10 | 2024-06-27 | 2024-06-27 |  | 2024-07-15 | 80 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | FRAMATOME CON.FRANCE | 8630-3640A |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
856 | 1202094330000 | ACC TORNILLO MACHO #DD 4-40UNC-2A THD A= | 1800108796 | 60 | 2024-06-14 |  | 4200569756 | 110 | 2024-07-08 | 2024-07-10 |  | 2024-07-26 | 35 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | ITT CANNON ELECTRIC | D20420-13 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
857 | 1232024245400 | MANG IDENTIF TERMO 3/32" 3:1 POLIOLE AMA | 1800108796 | 70 | 2024-06-14 |  | 4200568164 | 10 | 2024-06-21 | 2024-09-11 | BORR | 2024-07-15 | 45 | 8 | Generado documento | 150 | 200 | 2 | 200 | 0 | 2 | X | 95.50 |  | FARNELL COMPONENTS, S.L. | TE CONNECTIVITY | TMS-SCE-3/32-2.0-4 |  | 0 | 0 |  | 7218¦JA2581_1001 | 24 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
858 | 1232024245400 | MANG IDENTIF TERMO 3/32" 3:1 POLIOLE AMA | 1800108796 | 70 | 2024-06-14 |  | 4200588475 | 10 | 2024-12-03 | 2024-12-04 |  | 2024-12-11 | 45 | 8 | Liberado | 150 | 150 | 150 | 0 | 150 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | TE CONNECTIVITY | TMS-SCE-3/32-2.0-4 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 150 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -498 | 0
859 | 1233525320100 | BRIDA 3,6X142MM DMAX=32MM NYLON NATURAL | 1800108796 | 80 | 2024-06-14 |  | 4200570101 | 80 | 2024-07-10 | 2024-08-14 |  | 2024-07-15 | 30 | 8 | Liberado | 5000 | 5000 | 5000 | 0 | 5000 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | UNEX | 2233 |  | 0 | 0 |  | 7218¦JA2581_1001 | 5 | - |  | YES | 5000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
860 | 1238500222000 | TERM PREAISL PUNTERA AWG22 CRIMP BLANCO | 1800108796 | 90 | 2024-06-14 |  | 4200570311 | 100 | 2024-07-11 | 2024-07-16 |  | 2024-10-04 | 40 | 8 | Liberado | 500 | 1000 | 2000 | 0 | 1000 | 1000 | X | 0.00 |  | DICOMAT, S.L. | WAGO | 216-201 |  | 1 | 0 |  | 7218¦JA2581_1001 | 85 | - |  | YES | 2000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
861 | 956001033 | MAC TERMO 1/8" M23053/5-104-0 | 1800108796 | 100 | 2024-06-14 |  | 4200572876 | 10 | 2024-07-30 | 2024-10-07 |  | 2024-08-23 | 30 | 8 | Liberado | 5 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | OTROS FABRICANTES | 956001033 |  | 1 | 1 |  | 7218¦JA2581_1001 | 24 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -608 | 0
862 | 956004007 | BRIDA P/CBL L=390X4.7MM | 1800108796 | 110 | 2024-06-14 |  | 4200573125 | 240 | 2024-08-01 | 2024-12-12 |  | 2024-09-30 | 85 | 8 | Liberado | 4000 | 4000 | 4000 | 0 | 4000 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | OTROS FABRICANTES | 956004007 |  | 1 | 1 |  | 7218¦JA2581_1001 | 60 | - |  | YES | 4000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -570 | 0
863 | 0918530000000 | CANIF-DIO32_TIPO11B | 1800108797 | 20 | 2024-06-16 |  | 4200567892 | 10 | 2024-06-20 | 2024-06-21 |  | 2024-07-20 | 30 | 8 | Liberado | 25 | 25 | 25 | 0 | 25 | 0 | X | 0.00 |  | ELATE,S.A. | INDRA SISTEMAS S.A. | 0918530000000 |  | 0 | 0 |  | 7218¦JA2586_1001 | 30 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -642 | 0
864 | 1002531203209 | RST PELCAR 120R 5% -500,350PPM 1/4W ROHS | 1800108797 | 30 | 2024-06-16 |  | 4200568748 | 20 | 2024-06-28 | 2024-06-28 |  | 2024-07-17 | 30 | 8 | Liberado | 12 | 12 | 12 | 0 | 12 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | YAGEO | CFR-25JR-52-120R |  | 0 | 0 |  | 7218¦JA2586_1001 | 19 | - |  | YES | 12 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -645 | 0
865 | 1002545103100 | RST PELCAR 5K10 5% 1/4W AXIAL ROHS | 1800108797 | 40 | 2024-06-16 |  | 4200569946 | 20 | 2024-07-09 | 2024-07-10 |  | 2024-07-22 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | ARCOL | RCC025 5K1 J |  | 0 | 0 |  | 7218¦JA2586_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
866 | 1060900040000 | PORTALED T1 3/4 D=9,5MM P/LED 5MM PANEL | 1800108797 | 50 | 2024-06-16 |  | 4200568748 | 30 | 2024-06-28 | 2024-06-28 |  | 2024-10-29 | 126 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | ARCOLECTRIC | A104800AAC |  | 1 | 0 |  | 7218¦JA2586_1001 | 123 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -541 | 0
867 | 1209013600000 | REGLETA PINES 1X36M 2,54MM 3,43/5,84 RHS | 1800108797 | 60 | 2024-06-16 |  | 4200568022 | 10 | 2024-06-21 | 2024-06-25 |  | 2024-07-15 | 80 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | FCI | 77311-802-36LF |  | 0 | 0 |  | 7218¦JA2586_1001 | 24 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
868 | 1229594740000 | CBL EQUIPADO INTERFACE 2X CNC SUB-D 25P- | 1800108797 | 70 | 2024-06-16 |  | 4200573607 | 10 | 2024-08-05 | 2024-09-23 |  | 2024-09-23 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | MAX TECHNOLOGIES INC | MAX TECHNOLOGIES INC | MAX-AC-40300 |  | 0 | 0 |  | 7218¦JA2586_1001 | 49 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -577 | 0
869 | 1229594740000 | CBL EQUIPADO INTERFACE 2X CNC SUB-D 25P- | 1800108797 | 70 | 2024-06-16 |  | 4200572642 | 10 | 2024-07-29 | 2024-07-31 | BORR | 2024-09-23 | 30 | 8 |  | 5 | 5 | 0 | 5 | 0 | 0 |  | 2936.20 |  | MAX TECHNOLOGIES INC | MAX TECHNOLOGIES INC | MAX-AC-40300 |  | 0 | 0 |  | 7218¦JA2586_1001 | 56 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -577 | 0
870 | 1229594740100 | CBL EUIPADO INTERFACE 30CM C/INTERFACE D | 1800108797 | 80 | 2024-06-16 |  | 4200572642 | 20 | 2024-07-29 | 2024-07-31 | BORR | 2024-09-23 | 105 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 622.84 |  | MAX TECHNOLOGIES INC | MAX TECHNOLOGIES INC | MAX-AC-40311 |  | 0 | 0 |  | 7218¦JA2586_1001 | 56 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -577 | 0
871 | 1229594740100 | CBL EUIPADO INTERFACE 30CM C/INTERFACE D | 1800108797 | 80 | 2024-06-16 |  | 4200573607 | 20 | 2024-08-05 | 2024-09-23 |  | 2024-09-23 | 105 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MAX TECHNOLOGIES INC | MAX TECHNOLOGIES INC | MAX-AC-40311 |  | 0 | 0 |  | 7218¦JA2586_1001 | 49 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -577 | 0
872 | 1351201460000 | T. PXI 3U INTELLIGENT CARRIER 2X MOD SIT | 1800108797 | 90 | 2024-06-16 |  | 4200575472 | 10 | 2024-08-28 | 2024-09-09 |  | 2024-11-06 | 30 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | MAX TECHNOLOGIES INC | MAX TECHNOLOGIES INC | MAX-SBC-400105 |  | 0 | 0 |  | 7218¦JA2586_1001 | 70 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -533 | 0
873 | 1351201490500 | MOD MEZZANINE IPM MULTI 8TX-8RX PARAMETR | 1800108797 | 100 | 2024-06-16 |  | 4200575472 | 20 | 2024-08-28 | 2024-09-09 |  | 2024-11-06 | 30 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | MAX TECHNOLOGIES INC | MAX TECHNOLOGIES INC | MAX-IP-200142 |  | 0 | 0 |  | 7218¦JA2586_1001 | 70 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -533 | 0
874 | 1351710950100 | MODULO ADPT MULTIFUNCTION DAQ DEVICE USB | 1800108797 | 110 | 2024-06-16 |  | 4200569708 | 10 | 2024-07-08 | 2024-07-08 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | NATIONAL INSTRUMENTS | 779678-01 |  | 0 | 0 |  | 7218¦JA2586_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
875 | 1390303690000 | GATEWAY DR PCAN-ETHERNET 10/100MBPS | 1800108797 | 120 | 2024-06-16 |  | 4200569720 | 10 | 2024-07-08 | 2024-07-08 |  | 2024-07-22 | 45 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | PEAK SYSTEM TECHNIK | IPEH-004010 |  | 0 | 0 |  | 7218¦JA2586_1001 | 14 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
876 | 1701001920000 | CHASIS BACKPLANE 3U 7+1SLOT P/COMPACTPCI | 1800108797 | 130 | 2024-06-16 |  | 4200575104 | 20 | 2024-08-23 | 2024-08-26 |  | 2024-11-04 | 105 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | QNV, S.L. | ADLINK TECHNOLOGY/NU | CPCIS-2632 |  | 0 | 0 |  | 7218¦JA2586_1001 | 73 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -535 | 0
877 | 3170103091600 | SWITCH 8P 10/100/1000BAS-T 123W POE/POE+ | 1800108797 | 140 | 2024-06-16 |  | 4200569793 | 10 | 2024-07-08 | 2024-07-09 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | NETGEAR | GS108PP |  | 0 | 0 |  | 7218¦JA2586_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
878 | 3200501301700 | PC IND Q370 I7-8700 256GB-SSD SATA3 S/OF | 1800108797 | 150 | 2024-06-16 |  | 4200568375 | 10 | 2024-06-26 | 2024-08-01 |  | 2024-08-14 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TEMPEL, S.A. | TEMPEL S.A. | EMB-PC-X86E/MIC-770Q-00A2/231000387 |  | 1 | 1 |  | 7218¦JA2586_1001 | 49 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -617 | 0
879 | 3210501151200 | ADAPT PCAN/USB OPTO-DECOUPLED | 1800108797 | 160 | 2024-06-16 |  | 4200569720 | 20 | 2024-07-08 | 2024-07-08 |  | 2024-07-22 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | PEAK SYSTEM TECHNIK | IPEH-002022 |  | 0 | 0 |  | 7218¦JA2586_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -640 | 0
880 | 1279901170900 | COMPASS PARA A320 | 1800108798 | 10 | 2024-06-16 |  | 4200569673 | 20 | 2024-07-08 | 2024-07-08 |  | 2025-01-30 | 135 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SIMTEK, INC | SIMTEK | 10-7133 |  | 1 | 1 |  | 7218¦JA2583_1001 | 206 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -448 | 0
881 | 1390701500700 | MOD MCDU SEQ27901 C/DISPLAY | 1800108798 | 20 | 2024-06-16 |  | 4200567534 | 10 | 2024-06-18 | 2024-06-21 |  | 2024-12-30 | 130 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ27901 |  | 2 | 1 |  | 7218¦JA2583_1001 | 195 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -479 | 0
882 | 1124510125000 | SWITCH MAGNETICO SPDT 28VDC 200MA C/FUS | 1800108799 | 10 | 2024-06-16 |  | 4200567900 | 110 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 55 | 8 | Liberado | 290 | 290 | 290 | 0 | 290 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2B2 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 290 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
883 | 1124510125200 | SWITCH MAGNETICO SPDT 28VDC 5A VERDE C/D | 1800108799 | 20 | 2024-06-16 |  | 4200568263 | 10 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 24 | 24 | 24 | 0 | 24 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-5A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 24 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
884 | 1124510125300 | SWITCH MAGNETICO SPDT 28VDC 7A 200MA C/D | 1800108799 | 30 | 2024-06-16 |  | 4200568263 | 20 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-7A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
885 | 1124510125400 | SWITCH MAGNETICO SPDT 28VDC 7.5A 200MA C | 1800108799 | 40 | 2024-06-16 |  | 4200568263 | 30 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 27 | 27 | 27 | 0 | 27 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-7.5A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 27 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
886 | 1124510125500 | SWITCH MAGNETICO SPDT 28VDC 10A 200MA C/ | 1800108799 | 50 | 2024-06-16 |  | 4200568263 | 40 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 45 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-10A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
887 | 1124510125600 | SWITCH MAGNETICO SPDT 28VDC 15A 200MA C/ | 1800108799 | 60 | 2024-06-16 |  | 4200568263 | 50 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 6 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-15A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
888 | 1124510125700 | SWITCH MAGNETICO SPDT 28VDC 20A 200MA C/ | 1800108799 | 70 | 2024-06-16 |  | 4200568263 | 60 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-20A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
889 | 1124510125900 | SWITCH MAGNETICO SPDT 28VDC 35A 200MA C/ | 1800108799 | 80 | 2024-06-16 |  | 4200568263 | 70 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-35A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
890 | 1124510126000 | SWITCH MAGNETICO SPDT 28VDC 50A 200MA C/ | 1800108799 | 90 | 2024-06-16 |  | 4200568263 | 80 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-50A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
891 | 1124510126100 | SWITCH MAGNETICO SPDT 28VDC 3A 200MA C/D | 1800108799 | 100 | 2024-06-16 |  | 4200568263 | 90 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 39 | 8 | Liberado | 113 | 113 | 113 | 0 | 113 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-3A |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 113 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
892 | 1128990390300 | ANILLO BLOQUEO OFF ROJO | 1800108799 | 110 | 2024-06-16 |  | 4200568263 | 100 | 2024-06-24 | 2024-06-25 |  | 2024-08-05 | 85 | 8 | Liberado | 25 | 25 | 25 | 0 | 25 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | Y 307 005 01 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
893 | 1128990400100 | INSERTO MARCAJE NEGRO 50A PULS CONFI A/B | 1800108799 | 120 | 2024-06-16 |  | 4200567900 | 180 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 85 | 8 | Liberado | 24 | 24 | 24 | 0 | 24 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 19 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 24 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
894 | 1128990400200 | INSERTO MARCAJE NEGRO 15A PULS CONFI A/B | 1800108799 | 130 | 2024-06-16 |  | 4200567900 | 120 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 55 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 12 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
895 | 1128990400300 | INSERTO MARCAJE NEGRO 20A PULS CONFI A/B | 1800108799 | 140 | 2024-06-16 |  | 4200567900 | 130 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 50 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 13 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
896 | 1128990400400 | INSERTO MARCAJE NEGRO 10A PULS CONFI A/B | 1800108799 | 150 | 2024-06-16 |  | 4200567900 | 140 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 55 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 11 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
897 | 1128990400800 | INSERTO MARCAJE NEGRO 3A PULS CONFIG A/B | 1800108799 | 160 | 2024-06-16 |  | 4200567900 | 150 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 60 | 8 | Liberado | 178 | 178 | 178 | 0 | 178 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 07 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 178 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
898 | 1128990400900 | INSERTO MARCAJE NEGRO 5A PULS CONFIG A/B | 1800108799 | 170 | 2024-06-16 |  | 4200567900 | 160 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 60 | 8 | Liberado | 31 | 31 | 31 | 0 | 31 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 08 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 31 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
899 | 1128990401100 | INSERTO MARCAJE NEGRO 25A PULS CONFI A/B | 1800108799 | 180 | 2024-06-16 |  | 4200567900 | 170 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 60 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 14 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
900 | 1128990401500 | INSERTO MARCAJE NEGRO 7,5A PULS CONF A/B | 1800108799 | 190 | 2024-06-16 |  | 4200567900 | 190 | 2024-06-20 | 2024-06-21 |  | 2024-08-01 | 85 | 8 | Liberado | 33 | 33 | 33 | 0 | 33 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 09 |  | 0 | 0 |  | 7218¦JA2583_1001 | 42 | - |  | YES | 33 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
901 | 0970185470100 | CARD SUPPORT 241VU | 1800108820 | 10 | 2024-06-16 |  | 4200568953 | 10 | 2024-07-01 | 2024-07-02 |  | 2024-10-24 | 40 | 15 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970185470100 |  | 2 | 1 |  | 7218¦JA2583_1001 | 115 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -546 | 0
902 | 0970185470200 | CARD SUPPORT 271VU | 1800108820 | 20 | 2024-06-16 |  | 4200568953 | 20 | 2024-07-01 | 2024-07-02 |  | 2024-10-24 | 40 | 15 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970185470200 |  | 2 | 1 |  | 7218¦JA2583_1001 | 115 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -546 | 0
903 | 0970185470500 | CARD SUPPORT 135VU | 1800108820 | 30 | 2024-06-16 |  | 4200568953 | 30 | 2024-07-01 | 2024-07-02 |  | 2024-10-24 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970185470500 |  | 2 | 1 |  | 7218¦JA2583_1001 | 115 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -546 | 0
904 | 0970785011700 | 24VU PANEL | 1800108820 | 40 | 2024-06-16 |  | 4200570671 | 10 | 2024-07-15 | 2026-01-22 |  | 2024-11-22 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785011700 |  | 2 | 1 |  | 7218¦JA2583_1001 | 130 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -517 | 0
905 | 0970785241600 | CHASSIS 24VU | 1800108820 | 50 | 2024-06-16 |  | 4200570671 | 20 | 2024-07-15 | 2026-01-22 |  | 2026-01-24 | 90 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 182.95 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785241600 |  | 4 | 4 |  | 7218¦JA2583_1001 | 558 | - | [5 empty] | 1 |  | 0% | 4200570671 |  |  |  | 6 | 100% |  | -89 | 0
906 | 0970785241700 | CAN SUPPORT 24VU | 1800108820 | 60 | 2024-06-16 |  | 4200570673 | 10 | 2024-07-15 | 2024-07-16 |  | 2025-07-31 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0970785241700 |  | 5 | 5 |  | 7218¦JA2583_1001 | 381 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -266 | 0
907 | 0970785470100 | CARD SUPPORT 115VU | 1800108820 | 70 | 2024-06-16 |  | 4200570673 | 20 | 2024-07-15 | 2024-07-16 |  | 2024-12-13 | 40 | 15 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0970785470100 |  | 1 | 1 |  | 7218¦JA2583_1001 | 151 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -496 | 0
908 | 0970785470300 | CARD SUPPORT 54 VU | 1800108820 | 80 | 2024-06-16 |  | 4200571231 | 10 | 2024-07-18 | 2024-07-18 |  | 2024-11-22 | 40 | 15 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785470300 |  | 2 | 1 |  | 7218¦JA2583_1001 | 127 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -517 | 0
909 | 0970785470400 | CARD SUPPORT 110 VU | 1800108820 | 90 | 2024-06-16 |  | 4200571231 | 20 | 2024-07-18 | 2024-07-18 |  | 2024-11-22 | 40 | 15 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785470400 |  | 2 | 1 |  | 7218¦JA2583_1001 | 127 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -517 | 0
910 | 0970785470600 | CARD SUPPORT 402VU | 1800108820 | 100 | 2024-06-16 |  | 4200571231 | 30 | 2024-07-18 | 2024-07-18 |  | 2024-11-22 | 40 | 15 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785470600 |  | 2 | 1 |  | 7218¦JA2583_1001 | 127 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -517 | 0
911 | 0970785470700 | CARD SUPPORT 119VU | 1800108820 | 110 | 2024-06-16 |  | 4200571231 | 40 | 2024-07-18 | 2024-07-18 |  | 2024-11-22 | 40 | 15 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785470700 |  | 2 | 1 |  | 7218¦JA2583_1001 | 127 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -517 | 0
912 | 0970785470800 | CARD SUPPORT 130VU | 1800108820 | 120 | 2024-06-16 |  | 4200570673 | 30 | 2024-07-15 | 2024-07-16 |  | 2024-12-20 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0970785470800 |  | 2 | 2 |  | 7218¦JA2583_1001 | 158 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -489 | 0
913 | 0970785470900 | CARD SUPPORT 131VU | 1800108820 | 130 | 2024-06-16 |  | 4200570673 | 40 | 2024-07-15 | 2024-07-16 |  | 2024-12-20 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0970785470900 |  | 1 | 1 |  | 7218¦JA2583_1001 | 158 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -489 | 0
914 | 0971785310100 | DBCU BUTTON DOOR | 1800108821 | 10 | 2024-06-16 |  | 4200568954 | 10 | 2024-07-01 | 2024-07-02 |  | 2025-01-17 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0971785310100 |  | 2 | 2 |  | 7218¦JA2581_1001 | 200 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -461 | 0
915 | 0971788310100 | DBCU CONNECTION PLATE | 1800108821 | 20 | 2024-06-16 |  | 4200568954 | 20 | 2024-07-01 | 2024-07-02 |  | 2025-01-16 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0971788310100 |  | 2 | 2 |  | 7218¦JA2581_1001 | 199 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -462 | 0
916 | 1000954320003 | RST PELMET AXI 43K 0.1% 15PPM 1/4W ROHS | 1800108821 | 30 | 2024-06-16 |  | 4200568748 | 80 | 2024-06-28 | 2024-06-28 |  | 2024-07-17 | 40 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TE CONNECTIVITY | H843K2BYA |  | 0 | 0 |  | 7218¦JA2612_1001 | 19 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -645 | 0
917 | 1002548203009 | RST PELCAR 8K205% 1/4W 0207 | 1800108821 | 40 | 2024-06-16 |  | 4200569759 | 90 | 2024-07-08 | 2024-07-17 |  | 2024-07-15 | 100 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | TCX MICRO, S.L.U |  |  |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
918 | 1139990091100 | ZOCALO RELE CARRIL DIN P/RELE 4PCO | 1800108821 | 50 | 2024-06-16 |  | 4200568057 | 10 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 50 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | FINDER | 96.72 |  | 0 | 0 |  | 7218¦JA2612_1001 | 24 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
919 | 1139990091300 | ZOCALO RELE 250VAC 35MM TOR AZUL P/56.34 | 1800108821 | 60 | 2024-06-16 |  | 4200568061 | 10 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | FINDER | 96.74SMA |  | 0 | 0 |  | 7218¦JA2581_1001 | 24 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
920 | 1142012242600 | INDICADOR LED C/CUERP 24V PLASTIC NARANJ | 1800108821 | 70 | 2024-06-16 |  | 4200569759 | 100 | 2024-07-08 | 2024-07-17 |  | 2024-07-29 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | SCHNEIDER ELECTRIC | ZB5AVB5 |  | 0 | 0 |  | 7218¦JA2612_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
921 | 1146093240100 | AVISADOR LUMINOSO 24V AMBAR CAJA-BLANCA | 1800108821 | 80 | 2024-06-16 |  | 4200571051 | 10 | 2024-07-17 | 2024-07-17 |  | 2024-07-26 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | E2S | L101XDC024BW/A |  | 0 | 0 |  | 7218¦JA2612_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
922 | 1237000282000 | TERMINAL REGLETA AWG28-14 600V GRIS | 1800108821 | 90 | 2024-06-16 |  | 4200570311 | 110 | 2024-07-11 | 2024-07-16 |  | 2024-10-04 | 30 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | DICOMAT, S.L. | WAGO | 280-621 |  | 1 | 0 |  | 7218¦JA2581_1001 | 85 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
923 | 1237090350800 | PLACA 2,5MM INTERM/FINAL REGLETA GRIS (1 | 1800108821 | 100 | 2024-06-16 |  | 4200570311 | 120 | 2024-07-11 | 2024-07-16 |  | 2024-10-04 | 110 | 8 | Liberado | 40 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | DICOMAT, S.L. | WAGO | 280-316 |  | 1 | 0 |  | 7218¦JA2581_1001 | 85 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
924 | 1238524420660 | TERM PREAISL DIA 4,2MM CBL AWG16-14 AZUL | 1800108821 | 110 | 2024-06-16 |  | 4200569232 | 50 | 2024-07-03 | 2024-07-10 |  | 2024-07-21 | 30 | 8 | Liberado | 100 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | TTI INC. | MILITARY STANDARDS | MS25036-153 |  | 0 | 0 |  | 7218¦JA2612_1001 | 18 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -641 | 0
925 | 1289991640000 | TAPON BOTON BLANCO FLECHA-ARIBA XB4/XB5 | 1800108821 | 120 | 2024-06-16 |  | 4200569504 | 260 | 2024-07-05 | 2024-07-05 |  | 2024-07-15 | 85 | 8 | Liberado | 3 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | SCHNEIDER ELECTRIC | ZBAF334 |  | 0 | 0 |  | 7218¦JA2612_1001 | 10 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
926 | 1289991640001 | TAPON BOTON NEGRO FLECHA-ARIBA XB4/XB5 | 1800108821 | 130 | 2024-06-16 |  | 4200569504 | 270 | 2024-07-05 | 2024-07-05 |  | 2024-07-15 | 85 | 8 | Liberado | 3 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | SCHNEIDER ELECTRIC | ZBAF335 |  | 0 | 0 |  | 7218¦JA2612_1001 | 10 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
927 | 1390701501200 | PASARELA IND-13102022-1700 S/OF | 1800108821 | 140 | 2024-06-16 |  | 4200567373 | 10 | 2024-06-17 | 2024-11-25 |  | 2024-11-25 | 110 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | TALLERES XUQUER | 0712100000001/IND-13102022-1700 |  | 2 | 2 |  | 7218¦JA2581_1001 | 161 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -514 | 0
928 | 1589990770000 | CARRIL DIN 35X7,5MM L=2MTR | 1800108821 | 150 | 2024-06-16 |  | 4200575586 | 10 | 2024-08-29 | 2024-08-29 |  | 2024-09-04 | 30 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | LUJISA, S.A. | WAGO | 210-113 |  | 0 | 0 |  | 7218¦JA2581_1001 | 6 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -596 | 0
929 | 1390705229900 | KIT SISTEMA MOV GEN3 SIMULA CC91958 | 1800108899 | 10 | 2024-06-19 |  | 4600003976 | 10 | 2024-06-21 | 2024-09-11 | BORR | 2024-10-02 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 480436.00 |  | MOOG, B.V. | MOOG | CC91958-000A-075-0 | X | 0 | 0 |  | 7218¦JA2612_1001 | 103 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -568 | 0
930 | 1139900460100 | CLIP FIJACION RELES SPDT/DPDT ESTANDAR L | 1800108945 | 10 | 2024-06-19 |  | 4200571230 | 10 | 2024-07-18 | 2024-07-18 |  | 2024-08-01 | 50 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | OMRON TATEISI | PYC-P |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
931 | 1220100202011 | CBL HOOK-UP 20AWG 19X32 600V 1M NEGRO | 1800108945 | 20 | 2024-06-19 |  | 4200572816 | 10 | 2024-07-30 | 2024-07-30 |  | 2024-08-08 | 85 | 8 | Liberado | 600 | 600 | 600 | 0 | 600 | 0 | X | 0.00 |  | TTI INC. | RAYCHEM CORP | 44A0111-20-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 9 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
932 | 1220100202011 | CBL HOOK-UP 20AWG 19X32 600V 1M NEGRO | 1800108945 | 20 | 2024-06-19 |  | 4200571584 | 10 | 2024-07-22 | 2025-04-29 | BORR | 2024-07-29 | 85 | 8 | Liberado | 600 | 600 | 0 | 600 | 0 | 0 |  | 372.00 |  | FARNELL COMPONENTS, S.L. | RAYCHEM CORP | 44A0111-20-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -633 | 0
933 | 1220100203230 | CBL FLEX 1XAWG20 600V PVDF ROJO ROHS | 1800108945 | 30 | 2024-06-19 |  | 4200571563 | 10 | 2024-07-19 | 2024-07-24 |  | 2024-07-29 | 60 | 8 | Liberado | 600 | 600 | 600 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | M81044/12-20-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 10 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
934 | 1220100223030 | CBL FLEX 1XAWG22 600V PVDF NEGRO ROHS | 1800108945 | 40 | 2024-06-19 |  | 4200571599 | 10 | 2024-07-22 | 2024-07-24 |  | 2024-08-22 | 40 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | SAE INC. | M81044/12-22-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 31 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -609 | 0
935 | 1220100223930 | CBL FLEX 1XAWG22 600V PVDF BLANCO ROHS | 1800108945 | 50 | 2024-06-19 |  | 4200571599 | 20 | 2024-07-22 | 2024-07-24 |  | 2024-08-19 | 55 | 8 | Liberado | 4000 | 4000 | 4000 | 0 | 4000 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | SAE INC. | M81044/12-22-9 |  | 0 | 0 |  | 7218¦JA2581_1001 | 28 | - |  | YES | 4000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
936 | 1220100243230 | CBL FLEX 1XAWG24 600V PVDF ROJO ROHS | 1800108945 | 60 | 2024-06-19 |  | 4200571599 | 30 | 2024-07-22 | 2024-07-24 |  | 2024-07-26 | 40 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | SAE INC. | M81044/12-24-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 4 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
937 | 1221100182200 | CBL APANT 1XAWG18 PVDF 600V RO | 1800108945 | 70 | 2024-06-19 |  | 4200571582 | 10 | 2024-07-22 |  | BORR | 2024-07-31 | 30 | 8 |  | 300 | 300 | 0 | 300 | 0 | 0 |  | 417.00 |  | ICOMPPLUS ELECTRONICS S.L | RAYCHEM CORP | 44A0111-18-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 9 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -631 | 0
938 | 1221100182200 | CBL APANT 1XAWG18 PVDF 600V RO | 1800108945 | 70 | 2024-06-19 |  | 4200571579 | 70 | 2024-07-22 | 2024-07-24 |  | 2024-07-31 | 30 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | RAYCHEM CORP | 44A0111-18-2 |  | 1 | 1 |  | 7218¦JA2581_1001 | 9 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
939 | 1229991039503 | CBL FLEX 1XAWG24 600V PVDF NEGRO ROHS | 1800108945 | 80 | 2024-06-19 |  | 4200570835 | 10 | 2024-07-16 | 2024-07-17 |  | 2024-07-23 | 55 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0111-24-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -639 | 0
940 | 1229991069511 | CBL FLEX 1XAWG12 600V PVDF NEGRO ROHS | 1800108945 | 90 | 2024-06-19 |  | 4200571599 | 40 | 2024-07-22 | 2024-07-24 |  | 2024-08-19 | 85 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | SAE INC. | M81044/12-12-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 28 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
941 | 1229991069512 | CBL FLEX 1XAWG12 600V PVDF ROJO ROHS | 1800108945 | 100 | 2024-06-19 |  | 4200571849 | 110 | 2024-07-23 | 2024-08-07 |  | 2024-07-31 | 100 | 8 | Liberado | 300 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0111-12-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
942 | 1229991069524 | CBL FLEX 1XAWG22 600V PVDF ROJO ROHS | 1800108945 | 110 | 2024-06-19 |  | 4200571849 | 120 | 2024-07-23 | 2024-08-07 |  | 2024-07-31 | 60 | 8 | Liberado | 1000 | 1000 | 1000 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 44A0111-22-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
943 | 1233524500900 | BASE ADH BRIDA A=5MM 29X29X2,5MM NYLON B | 1800108945 | 120 | 2024-06-19 |  | 4200571557 | 120 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 85 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 229-560 |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
944 | 1587090630000 | ETQ ADH PELIGRO 12.5X12.5MM VINILO | 1800108945 | 130 | 2024-06-19 |  | 4200581246 | 30 | 2024-10-15 | 2024-10-21 |  | 2024-07-15 | 40 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | AMIDATA, S.A. | RS PRO | 776-0939 |  | 0 | 0 |  | 7218¦JA2581_1001 | -92 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
945 | 1204200730720 | CNC CIR 11-99 7H PLUG RECT AL/ZNI-NI R-N | 1800108946 | 10 | 2024-06-19 |  | 4200571563 | 20 | 2024-07-19 | 2024-07-24 |  | 2024-08-06 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZB99SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
946 | 1204205300020 | CNC CIR 23-54 53P(M) RECT PLUG | 1800108946 | 20 | 2024-06-19 |  | 4200572876 | 200 | 2024-07-30 | 2024-10-07 |  | 2024-08-09 | 105 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL CORP | TV06DZ-23-54P |  | 1 | 1 |  | 7218¦JA2581_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -622 | 0
947 | 1204301230620 | CNC CIR 15-97 12M RCPT RECT CRMP ROT-N | 1800108946 | 30 | 2024-06-19 |  | 4200571563 | 30 | 2024-07-19 | 2024-07-24 |  | 2024-08-06 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZD97PN |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
948 | 1214200430722 | CNC CIR 13-4 4H PLUG D38999/26ZC4SA | 1800108946 | 40 | 2024-06-19 |  | 4200571563 | 40 | 2024-07-19 | 2024-07-24 |  | 2024-08-06 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZC4SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
949 | 1214201230020 | CNC CIR 15-97 12H CRMP MIL-DTL-38999 III | 1800108946 | 50 | 2024-06-19 |  | 4200571563 | 50 | 2024-07-19 | 2024-07-24 |  | 2024-08-06 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZD97SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
950 | 1214304130920 | CNC CIR 21-41 41H RECEPT CRIMP ZN/NI R-N | 1800108946 | 60 | 2024-06-19 |  | 4200571564 | 10 | 2024-07-21 | 2024-07-24 |  | 2024-08-12 | 40 | 8 | Liberado | 14 | 14 | 14 | 0 | 14 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | D38999/20ZG41SN |  | 0 | 0 |  | 7218¦JA2581_1001 | 22 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -619 | 0
951 | 7853201250000 | INSERTADOR/EXTRACTOR CONT #22 BLANC/VER | 1800108946 | 70 | 2024-06-19 |  | 4200575219 | 50 | 2024-08-26 | 2024-08-26 |  | 2024-09-09 | 40 | 8 | Liberado | 30 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M81969/1-01 |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -591 | 0
952 | 1002541009009 | RST PELCAR AXI 1K00 5% 350PPM 1/4W ROHS | 1800108947 | 10 | 2024-06-19 |  | 4200568030 | 120 | 2024-06-21 | 2024-06-21 |  | 2024-07-08 | 100 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RS PRO | 707-7666 |  | 1 | 1 |  | 7218¦JA2586_1001 | 17 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -654 | 0
953 | 1002551003509 | RST PELCAR AXI 10K0 5% 350PPM 1/4W ROHS | 1800108947 | 20 | 2024-06-19 |  | 4200568030 | 130 | 2024-06-21 | 2024-06-21 |  | 2024-07-08 | 100 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RS PRO | 707-7745 |  | 1 | 1 |  | 7218¦JA2586_1001 | 17 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -654 | 0
954 | 1050106909000 | TRT NPN 45V 2A 1W TO-92 ROHS | 1800108947 | 30 | 2024-06-19 |  | 4200568108 | 30 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 105 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | DIODES INC. | ZTX690B |  | 0 | 0 |  | 7218¦JA2586_1001 | 24 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
955 | 1066090000000 | FOTOTRANSISTOR NPN 3MM T-1 IR ROHS | 1800108947 | 40 | 2024-06-19 |  | 4200568010 | 270 | 2024-06-21 | 2024-06-21 |  | 2024-07-05 | 85 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | OSRAM | SFH 3310 |  | 1 | 1 |  | 7218¦JA2586_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
956 | 1217000831000 | CNC RJ-45 PANEL (8X8) NEGRO APANTALLADO | 1800108947 | 50 | 2024-06-19 |  | 4200571557 | 130 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 42 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 186-3111 |  | 0 | 0 |  | 7218¦JA2586_1001 | 12 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
957 | 1219001090100 | CAJA PORTACONTACTOS 10/H CRIMP SERIE SL | 1800108947 | 60 | 2024-06-19 |  | 4200571148 | 40 | 2024-07-17 | 2024-07-18 |  | 2024-07-31 | 80 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MOLEX | 50-57-9410 |  | 1 | 1 |  | 7218¦JA2586_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
958 | 1219090030000 | CONTACTO HEMBRA CRIMPAR AWG22-24 | 1800108947 | 70 | 2024-06-19 |  | 4200571557 | 140 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 65 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 360-6869 |  | 0 | 0 |  | 7218¦JA2586_1001 | 12 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
959 | 1229590140400 | CBL EQ CAT6A LSZH RJ45-M/RJ45-M L=0.5M | 1800108947 | 80 | 2024-06-19 |  | 4200571219 | 10 | 2024-07-18 | 2024-07-24 | BORR | 2024-07-26 | 105 | 8 |  | 6 | 6 | 0 | 6 | 0 | 0 |  | 31.20 |  | OMRON ELECTRONICS IBERIA S.A.U. | OMRON CORPORATION | XS6W-6LSZH8SS50CM-Y |  | 0 | 0 |  | 7218¦JA2586_1001 | 8 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -636 | 0
960 | 1229590140400 | CBL EQ CAT6A LSZH RJ45-M/RJ45-M L=0.5M | 1800108947 | 80 | 2024-06-19 |  | 4200580892 | 10 | 2024-10-11 | 2024-10-15 |  | 2024-10-18 | 105 | 8 | Liberado | 6 | 6 | 0 | 6 | 0 | 0 |  | 31.20 |  | GITEC CONTROL, S.L. | OMRON CORPORATION | XS6W-6LSZH8SS50CM-Y |  | 0 | 0 |  | 7218¦JA2586_1001 | 7 | - | [5 empty] | 1 |  | 0% | 4200580892 |  |  |  | 6 | 100% |  | -552 | 0
961 | 1263511000106 | F.A CONM 190-264V 12V 30W CARRIL DIN | 1800108947 | 90 | 2024-06-19 |  | 4200568262 | 10 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | ELC | ALE1202 |  | 0 | 0 |  | 7218¦JA2586_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
962 | 1002531003609 | RST PELCAR AXI 100R 5% 350PPM 1/4W ROHS | 1800108948 | 10 | 2024-06-19 |  | 4200568010 | 290 | 2024-06-21 | 2024-06-21 |  | 2024-07-05 | 40 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | RS PRO | 707-7587 |  | 1 | 1 |  | 7218¦JA2612_1001 | 14 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
963 | 1002551003309 | RST PELCAR 10K 5% 500PPM 1/4W AXIAL ROHS | 1800108948 | 20 | 2024-06-19 |  | 4200568108 | 190 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 0 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | YAGEO | CFR-25JT-52-10K |  | 0 | 0 |  | 7218¦JA2612_1001 | 24 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
964 | 1124110210004 | MICRORRUPTOR SPDT 16A 250V 6,3X0,8 PALAN | 1800108948 | 30 | 2024-06-19 |  | 4200571039 | 10 | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 49 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | BARCITRONIC S.A. | CHERRY | D459-V3LL |  | 0 | 0 |  | 7218¦JA2612_1001 | 6 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -639 | 0
965 | 1124320115000 | INT FINAL CARRERA C/RODILLO VERT DPST (1 | 1800108948 | 40 | 2024-06-19 |  | 4200571557 | 150 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 49 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 308-1664 |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
966 | 1125110113403 | PULSADOR SETA 1P NC D=40MM C/CAJA ETIQUE | 1800108948 | 50 | 2024-06-19 |  | 4200571638 | 10 | 2024-07-22 | 2024-07-24 |  | 2024-07-29 | 85 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | LUJISA, S.A. | TELEMECANIQUE | XAL-K17814 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
967 | 1126622240000 | ESTACION CTRL 2PUL 1NO+1NC FLUSH NEG/BLN | 1800108948 | 60 | 2024-06-19 |  | 4200571460 | 50 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 85 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | XALD222 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
968 | 1126690520000 | CABEZA SETA EMERGENCIA GIRO AMARILLO | 1800108948 | 70 | 2024-06-19 |  | 4200571460 | 60 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AS55 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
969 | 1128900670000 | CUERPO DE FIJACION ZB4-BZ009 | 1800108948 | 80 | 2024-06-19 |  | 4200571460 | 70 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 45 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB4-BZ009 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
970 | 1128901240800 | CONTROL BOX 22MM GRAY POLYCARBONATE XAL | 1800108948 | 90 | 2024-06-19 |  | 4200571460 | 80 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 85 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | XALD01H7 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
971 | 1128910112001 | BLOQUE CONTACTO AUX 1NO 22MM CLAMP ZBE | 1800108948 | 100 | 2024-06-19 |  | 4200571460 | 90 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 85 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZBE1015 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
972 | 1128910113001 | BLOQUE CONTAC 1NC 22MM BORNA RESORT ZBE | 1800108948 | 110 | 2024-06-19 |  | 4200571460 | 100 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 85 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZBE1025 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
973 | 1128912180000 | CABEZA SELECTOR 2POS 90° D22MM NEGRA XB5 | 1800108948 | 120 | 2024-06-19 |  | 4200571460 | 110 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AD2 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
974 | 1128990028000 | CABEZA SETA EMERG RO P/PULS D=22MM IP66 | 1800108948 | 130 | 2024-06-19 |  | 4200571460 | 120 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AS844 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
975 | 1128990760000 | CUERPO COLLARIN P/BLOQUE CONTACTO/LUZ | 1800108948 | 140 | 2024-06-19 |  | 4200571557 | 160 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 85 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 609-3143 |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
976 | 1128991450000 | CABEZAL BOTON PULSADOR RETORNO/ RESORTE | 1800108948 | 150 | 2024-06-19 |  | 4200571460 | 130 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 85 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AA0 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
977 | 1128991608200 | CABEZA PULSADOR D22MM EMPOTRADO ROJO | 1800108948 | 160 | 2024-06-19 |  | 4200571460 | 140 | 2024-07-19 | 2024-07-28 |  | 2024-07-26 | 85 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB4BA46 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
978 | 1130622470402 | RELE PLUG-IN 24VD 12A 4PDT 1W NO-LATCH | 1800108948 | 170 | 2024-06-19 |  | 4200571230 | 20 | 2024-07-18 | 2024-07-18 |  | 2024-07-26 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | FINDER | 56.34.9.024.0040 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
979 | 1130622471000 | RELE DPDT 12A MINI PLUG-IN 24VDC | 1800108948 | 180 | 2024-06-19 |  | 4200571230 | 30 | 2024-07-18 | 2024-07-18 |  | 2024-07-26 | 80 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | FINDER | 56.32.9.024.0040 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
980 | 1135036060000 | CONTACTOR 0.5-10HP 9A TESYS K-LINE 600V | 1800108948 | 190 | 2024-06-19 |  | 4200571638 | 20 | 2024-07-22 | 2024-07-24 |  | 2024-07-29 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | TELEMECANIQUE | LP2K0910BD |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
981 | 1139022450400 | RELE INTERFACE 4PDT 24V/5A CO CARRIL SER | 1800108948 | 200 | 2024-06-19 |  | 4200571557 | 170 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 98 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 329-7358 |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
982 | 1139990091101 | ZOCALO C/BORNES DIN 35MM AZ P/RELE 56.32 | 1800108948 | 210 | 2024-06-19 |  | 4200572651 | 10 | 2024-07-29 | 2024-07-29 |  | 2024-07-31 | 80 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ARRAY ELECTRONICA PROFESIONAL, S.A. | FINDER | 96.72SMA |  | 0 | 0 |  | 7218¦JA2612_1001 | 2 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
983 | 1146093241000 | AVISADOR ACUSTICO 24VDC CAJA BLANCA | 1800108948 | 220 | 2024-06-19 |  | 4200571051 | 20 | 2024-07-17 | 2024-07-17 |  | 2024-07-26 | 54 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | E2S | SONF1DC24W |  | 0 | 0 |  | 7218¦JA2581_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
984 | 1237000289000 | PUENTE P/TERMINAL REGLETA 24A GRIS | 1800108948 | 230 | 2024-06-19 |  | 4200572680 | 10 | 2024-07-29 | 2024-07-29 |  | 2024-08-01 | 30 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | DICOMAT, S.L. | WAGO | 280-402 |  | 0 | 0 |  | 7218¦JA2581_1001 | 3 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
985 | 1237090351000 | PLACA FINAL/INTERM 0.8X33X70MM GRIS | 1800108948 | 240 | 2024-06-19 |  | 4200572680 | 20 | 2024-07-29 | 2024-07-29 |  | 2024-08-01 | 30 | 8 | Liberado | 110 | 110 | 110 | 0 | 110 | 0 | X | 0.00 |  | DICOMAT, S.L. | WAGO | 2002-1491 |  | 0 | 0 |  | 7218¦JA2581_1001 | 3 | - |  | YES | 110 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
986 | 1237090959001 | BLOQUE TERMINAL DE CONEXION GRIS CARRIL | 1800108948 | 250 | 2024-06-19 |  | 4200572680 | 30 | 2024-07-29 | 2024-07-29 |  | 2024-08-19 | 85 | 8 | Liberado | 150 | 150 | 150 | 0 | 150 | 0 | X | 0.00 |  | DICOMAT, S.L. | WAGO | 2002-1401 |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 150 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
987 | 1238514160202 | TERMINAL PREAISL RED M4 AWG22-16 ROJO | 1800108948 | 260 | 2024-06-19 |  | 4200570653 | 150 | 2024-07-15 | 2025-03-28 |  | 2024-07-27 | 45 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 841-968 |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -635 | 0
988 | 1263511601900 | F.A. CNM 90-264VAC/12VDC 5A 60W DIN-RAIL | 1800108948 | 270 | 2024-06-19 |  | 4200568000 | 10 | 2024-06-20 | 2024-06-21 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ELECTRONICA OLFER, S.L. | MEAN WELL | DRA-60-12 |  | 0 | 0 |  | 7218¦JA2612_1001 | 25 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
989 | 1283500040000 | INTERRUPTOR DE PROXIMIDAD MAGNETICO 230V | 1800108948 | 280 | 2024-06-19 |  | 4200579711 | 10 | 2024-10-03 | 2024-10-03 |  | 2024-07-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | AMIDATA, S.A. | RS AMIDATA | 361-4911 |  | 0 | 0 |  | 7218¦JA2581_1001 | -80 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
990 | 1283500040100 | IMAN P/INTERRUPTOR DE PROXIMIDAD | 1800108948 | 290 | 2024-06-19 |  | 4200579711 | 20 | 2024-10-03 | 2024-10-03 |  | 2024-07-15 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | AMIDATA, S.A. | RS AMIDATA | 361-4927 |  | 0 | 0 |  | 7218¦JA2581_1001 | -80 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
991 | 1289902150200 | SENSOR CAUDAL 100-1000CM3/S 24VDC D=23MM | 1800108948 | 300 | 2024-06-19 |  | 4200579746 | 10 | 2024-10-03 | 2024-10-03 | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 177.24 |  | INGENIEURGEMEINSCHAT FUER MESSTECHN | IFM ELECTRONIC | SL5101 |  | 0 | 0 |  | 7218¦JA2581_1001 | -80 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
992 | 1289902150200 | SENSOR CAUDAL 100-1000CM3/S 24VDC D=23MM | 1800108948 | 300 | 2024-06-19 |  | 4200589596 | 10 | 2024-12-11 | 2024-12-11 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | IFM ELECTRONIC | SL5101 |  | 0 | 0 |  | 7218¦JA2581_1001 | -149 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
993 | 1580130060000 | SEPARADOR EXA H/H M3X20MM E/C=5MM LATON/ | 1800108948 | 310 | 2024-06-19 |  | 4200574947 | 30 | 2024-08-21 | 2024-08-22 |  | 2024-09-02 | 42 | 8 | Liberado | 10 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | RS | 222-424 |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
994 | 1702002510000 | CAJA COMPACT AE IP66 760X600X210MM GRIS | 1800108948 | 320 | 2024-06-19 |  | 4200578616 | 10 | 2024-09-25 | 2024-09-27 |  | 2024-10-04 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | RITTAL, S.A | RS AMIDATA | 499-6084 |  | 0 | 0 |  | 7218¦JA2581_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
995 | 7851107360000 | LLAVE TUERCA 22MM HARMONY-XB5 P/ZB5AZ901 | 1800108948 | 330 | 2024-06-19 |  | 4200575233 | 10 | 2024-08-26 | 2024-08-26 |  | 2024-09-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AZ905 |  | 1 | 1 |  | 7218¦JA2581_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -590 | 0
996 | 1585003060000 | CIERRE MAGNET 24V 150MA PS | 1800108949 | 10 | 2024-06-19 |  | 4200587237 | 10 | 2024-11-25 | 2024-11-25 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | DIOCHE | N0FH15QUBM |  | 0 | 0 |  | 7218¦JA2581_1001 | -133 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
997 | 0972881220000 | SMOKE DET,TEMP SENSOR SUPPORT PLATE | 1800108953 | 10 | 2024-06-20 |  | 4200570491 | 10 | 2024-07-12 | 2024-07-12 |  | 2025-01-31 | 90 | 8 | Liberado | 7 | 7 | 7 | 0 | 7 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0972881220000 |  | 3 | 3 |  | 7218¦JA2582_1001 | 203 | - |  | YES | 7 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -447 | 0
998 | 1126690440000 | PULSADOR ALARMA REARM ANALOG C/AISLADOR | 1800108953 | 20 | 2024-06-20 |  | 4200584136 | 10 | 2024-11-04 | 2024-11-11 | BORR | 2024-12-02 | 35 | 8 |  | 3 | 3 | 0 | 3 | 0 | 0 |  | 177.12 |  | HONEYWELL LIFE SAFETY IBERIA, S.L. | HONEYWELL | M5A-RP02FF-N026-41 |  | 1 | 1 |  | 7218¦JA2582_1001 | 28 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -507 | 0
999 | 1126690440000 | PULSADOR ALARMA REARM ANALOG C/AISLADOR | 1800108953 | 20 | 2024-06-20 |  | 4200585889 | 20 | 2024-11-15 | 2024-11-20 |  | 2024-11-29 | 35 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | HONEYWELL | M5A-RP02FF-N026-41 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -510 | 0
1000 | 1146002242500 | SIRENA DIRECC C/FLASH TRANSP 97DB IP24 | 1800108953 | 30 | 2024-06-20 |  | 4200573002 | 140 | 2024-07-31 | 2024-08-05 |  | 2024-07-15 | 30 | 8 | Liberado | 3 | 3 | 6 | 0 | 3 | 3 | X | 0.00 |  | HONEYWELL LIFE SAFETY IBERIA, S.L. | HONEYWELL | WSS-PC-I02 |  | 0 | 0 |  | 7218¦JA2582_1001 | -16 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1001 | 1204800300000 | CNC RECT AEREO 2P+E (M) 32A 230V IP44 AZ | 1800108953 | 40 | 2024-06-20 |  | 4200571557 | 180 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 464-6228 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1002 | 1204800305000 | CNC UNION 3P AER CBL 6-8MM IP68 NEGRA | 1800108953 | 50 | 2024-06-20 |  | 4200574509 | 100 | 2024-08-14 | 2024-08-14 |  | 2024-08-30 | 85 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | LUJISA, S.A. | BULGIN | PX0777 |  | 0 | 0 |  | 7218¦JA2582_1001 | 16 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -601 | 0
1003 | 1207000640100 | CNC RJ11 6P4C PLUG RECT CBL-MNT AU ROHS | 1800108953 | 60 | 2024-06-20 |  | 4200571557 | 190 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 40 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 331-6342 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1004 | 1208000300300 | CNC RECT IEC C20 3P (M) 16A 250V | 1800108953 | 70 | 2024-06-20 |  | 4200571112 | 10 | 2024-07-17 | 2024-07-17 |  | 2024-07-23 | 85 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | ELCOM INTERNATIONAL PVT LTD | 776-9125 |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -639 | 0
1005 | 1208000322100 | CNC ALIMENT 2P+T 16A/250VAC CBL LATERAL | 1800108953 | 80 | 2024-06-20 |  | 4200570653 | 160 | 2024-07-15 | 2025-03-28 |  | 2024-07-27 | 80 | 8 | Liberado | 1 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 849-6115 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -635 | 0
1006 | 1208000323400 | CNC RED 2P+T M 230V 60HZ 16A PLUG IP44 | 1800108953 | 90 | 2024-06-20 |  | 4200572519 | 10 | 2024-07-28 | 2024-08-20 |  | 2024-08-30 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MENNEKES ELECT. | 248 |  | 1 | 1 |  | 7218¦JA2582_1001 | 33 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -601 | 0
1007 | 1208000324100 | CNC CLAVIJA 2P+T/M ACOD 250VAC 16A BLANC | 1800108953 | 100 | 2024-06-20 |  | 4200573516 | 10 | 2024-08-05 | 2024-08-05 |  | 2024-08-12 | 30 | 8 | Liberado | 25 | 25 | 25 | 0 | 25 | 0 | X | 0.00 |  | LUJISA, S.A. | SOLERA | 6566 |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -619 | 0
1008 | 1208000325700 | CNC ALIMENT IEC C14 3M RECT TOR 250V 10A | 1800108953 | 110 | 2024-06-20 |  | 4200571557 | 200 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 85 | 8 | Liberado | 60 | 60 | 70 | 0 | 60 | 10 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 776-9113 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 70 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1009 | 1218000325100 | CNC RED 2P+T H 230V 32A JACK IP44 AZUL | 1800108953 | 120 | 2024-06-20 |  | 4200572519 | 20 | 2024-07-28 | 2024-08-20 |  | 2024-10-04 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MENNEKES ELECT. | 522 |  | 2 | 1 |  | 7218¦JA2582_1001 | 68 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
1010 | 1218000325200 | CNC RED 2P+T H 230V 16A JACK IP44 AZUL | 1800108953 | 130 | 2024-06-20 |  | 4200572519 | 30 | 2024-07-28 | 2024-08-20 |  | 2024-08-30 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MENNEKES ELECT. | 510 |  | 1 | 1 |  | 7218¦JA2582_1001 | 33 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -601 | 0
1011 | 1218000520700 | CNC RED 5P (H) 400V AEREO 16A IP67 | 1800108953 | 140 | 2024-06-20 |  | 4200572519 | 40 | 2024-07-28 | 2024-08-20 |  | 2024-08-30 | 30 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MENNEKES ELECT. | 550 |  | 1 | 1 |  | 7218¦JA2582_1001 | 33 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -601 | 0
1012 | 1218000523200 | CNC RED AEREO 3P+N+T 32A 400V ROJO IP44 | 1800108953 | 150 | 2024-06-20 |  | 4200572843 | 10 | 2024-07-30 | 2024-07-30 |  | 2024-08-06 | 85 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | LEWDEN | PM32/2800FPB |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
1013 | 1218000523210 | CNC RED AEREA 5P H 400V 32A IP44 ROJO | 1800108953 | 160 | 2024-06-20 |  | 4200572519 | 50 | 2024-07-28 | 2024-08-20 |  | 2024-08-30 | 30 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | MENNEKES ELECT. | 3976 |  | 1 | 1 |  | 7218¦JA2582_1001 | 33 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -601 | 0
1014 | 1220115045000 | CBL FLEX 1X50MM2 H07Z1-K 750V HFLS AZ RH | 1800108953 | 170 | 2024-06-20 |  | 4200572832 | 20 | 2024-07-30 | 2024-07-30 |  | 2024-08-07 | 35 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | EPIRSA | GENERAL CABLE | 1656114AZ |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -624 | 0
1015 | 1220115100000 | CBL FLX 1X10MM2 H07Z1-K AST2 750V POL AV | 1800108953 | 180 | 2024-06-20 |  | 4200572832 | 30 | 2024-07-30 | 2024-07-30 |  | 2024-08-07 | 50 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | EPIRSA | GENERAL CABLE | 1656110AVP |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -624 | 0
1016 | 1220115163700 | CBL FLX 1X16MM2 450/750V H07Z1-K AS VEAM | 1800108953 | 190 | 2024-06-20 |  | 4200571780 | 10 | 2024-07-23 | 2024-07-24 |  | 2024-07-29 | 85 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | LUJISA, S.A. | TOP CABLE | 151V016.R100 |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
1017 | 1220115356000 | CBL FLX 1X35MM2 H07Z1-K(AS) 750V POL A/V | 1800108953 | 200 | 2024-06-20 |  | 4200572832 | 40 | 2024-07-30 | 2024-07-30 |  | 2024-08-07 | 35 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | EPIRSA | GENERAL CABLE | 1656113AVP |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -624 | 0
1018 | 1220115502001 | CBL FLEX 1X50MM2 NE H07Z1-K 750V CU Z1 | 1800108953 | 210 | 2024-06-20 |  | 4200573355 | 30 | 2024-08-02 | 2024-08-13 |  | 2024-08-12 | 85 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | TELKRON, S.A. | INPLASNU | INPLASNU H07Z1-K/1X50MM2 NEGRO |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -619 | 0
1019 | 1220115502002 | CBL FLEX 1X50MM2 AV H07Z1-K 750V CU Z1 | 1800108953 | 220 | 2024-06-20 |  | 4200573355 | 40 | 2024-08-02 | 2024-08-13 |  | 2024-08-12 | 85 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | TELKRON, S.A. | INPLASNU | INPLASNU H07Z1-K/1X50MM2 AMARILLO/VERDE |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -619 | 0
1020 | 1220314154502 | CBL FLEX 3X1,5MM2 RZ1-K 0,6/1KV POLIOLE | 1800108953 | 230 | 2024-06-20 |  | 4200571770 | 10 | 2024-07-23 | 2024-09-18 |  | 2024-07-29 | 30 | 8 | Liberado | 600 | 600 | 600 | 0 | 600 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MIGUELEZ | RZ1-K (AS) 0,6/1KV 3X1,5MM2 VER |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
1021 | 1220314254505 | CBL FLEX 5X2,5MM2 RZ1-K 0,6/1KV POLIOLE | 1800108953 | 240 | 2024-06-20 |  | 4200571770 | 20 | 2024-07-23 | 2024-09-18 |  | 2024-07-29 | 30 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MIGUELEZ | RZ15025 |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
1022 | 1220314254508 | CBL FLEX 3X2,5MM2 RZ1-K 0,6/1KV POLIOLE | 1800108953 | 250 | 2024-06-20 |  | 4200571770 | 30 | 2024-07-23 | 2024-09-18 |  | 2024-07-29 | 85 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MIGUELEZ | RZ1-K (AS) 0,6/1KV 3X2,5MM2 VER |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -633 | 0
1023 | 1220314404100 | CBL FLEX 3X4MM2 RZ1-K 0,6/1KV POLIOLE NE | 1800108953 | 260 | 2024-06-20 |  | 4200571770 | 40 | 2024-07-23 | 2024-09-18 |  | 2024-12-05 | 30 | 8 | Liberado | 300 | 300 | 600 | 0 | 300 | 300 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MIGUELEZ | RZ1-K (AS) 0,6/1KV CU 3X4MM2 NE |  | 1 | 1 |  | 7218¦JA2582_1001 | 135 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -504 | 0
1024 | 1220315404000 | CBL RZ1-K 0,6/1KV CU 5X4MM2 BAJO HALOGEN | 1800108953 | 270 | 2024-06-20 |  | 4200571250 | 10 | 2024-07-18 | 2024-07-18 |  | 2024-07-23 | 85 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CABELTE CABOS ELECTR | RZ1-K 0,6/1KV CU 5X4MM2 |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -639 | 0
1025 | 1222700280000 | CBL PAR 4X2X28AWG 7/0.127MM 80V PE NEG | 1800108953 | 280 | 2024-06-20 |  | 4200571148 | 60 | 2024-07-17 | 2024-07-18 |  | 2024-08-01 | 85 | 8 | Liberado | 2 | 50 | 150 | 0 | 50 | 100 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | DECELECT | SPE191354 |  | 0 | 0 |  | 7218¦JA2582_1001 | 15 | - |  | YES | 150 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -630 | 0
1026 | 1229500280000 | CBL PLANO 6XAWG28 FCC68 3M PVC GRIS | 1800108953 | 290 | 2024-06-20 |  | 4200571557 | 210 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 105 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 446-664 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1027 | 1229500280101 | CBL EQ TELEFONO RJ12/RJ12 6P4C GRIS L=6M | 1800108953 | 300 | 2024-06-20 |  | 4200573125 | 180 | 2024-08-01 | 2024-12-12 |  | 2024-08-19 | 105 | 8 | Liberado | 12 | 12 | 12 | 0 | 12 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | ROLINE | 11.04.1906-10 |  | 1 | 1 |  | 7218¦JA2582_1001 | 18 | - |  | YES | 12 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
1028 | 1229590001001 | CBL EQ ALIM C13-IEC/CNC-B 250V NG L=2M | 1800108953 | 310 | 2024-06-20 |  | 4200571557 | 220 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 105 | 8 | Liberado | 30 | 30 | 90 | 0 | 30 | 60 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 731-6153 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 90 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1029 | 1229591010007 | CBL EQ IEC C13/NO CNC (H/H) 250V 10A PVC | 1800108953 | 320 | 2024-06-20 |  | 4200571557 | 230 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 105 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 901-0753 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1030 | 1237525872000 | CAJA MNTJE SUPERF 87X93X32MM P/PULS KAC | 1800108953 | 330 | 2024-06-20 |  | 4200584136 | 20 | 2024-11-04 | 2024-11-11 | BORR | 2024-12-02 | 55 | 8 |  | 3 | 3 | 0 | 3 | 0 | 0 |  | 12.84 |  | HONEYWELL LIFE SAFETY IBERIA, S.L. | HONEYWELL | PS031W |  | 1 | 1 |  | 7218¦JA2582_1001 | 28 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -507 | 0
1031 | 1237525872000 | CAJA MNTJE SUPERF 87X93X32MM P/PULS KAC | 1800108953 | 330 | 2024-06-20 |  | 4200585889 | 30 | 2024-11-15 | 2024-11-20 |  | 2024-11-29 | 55 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | HONEYWELL | PS031W |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -510 | 0
1032 | 1238000022000 | TERMINAL RED DESNUDO AWG=2 S=35MM2 SERIE | 1800108953 | 340 | 2024-06-20 |  | 4200572594 | 10 | 2024-07-29 | 2024-07-29 |  | 2024-08-08 | 110 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | LUJISA, S.A. | CEMBRE | A7-P20 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1033 | 1238000070300 | TERM CERRADO AMPOWER-R 7AWG TOR M6 | 1800108953 | 350 | 2024-06-20 |  | 4200571579 | 140 | 2024-07-22 | 2024-07-24 |  | 2024-07-31 | 60 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TE CONNECTIVITY | 710031-4 |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1034 | 1238015350100 | TERMINAL DESNUDO 35MM2 CRIMP CU | 1800108953 | 360 | 2024-06-20 |  | 4200571557 | 240 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 110 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 531-885 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1035 | 1238015350400 | TERMINAL RED DESNUDO M8 35MM2 D8MM CU/SN | 1800108953 | 370 | 2024-06-20 |  | 4200572594 | 20 | 2024-07-29 | 2024-07-29 |  | 2024-08-08 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | LUJISA, S.A. | CEMBRE | A7-M8 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1036 | 1238015500100 | TERMINAL RED DESNUDO M8 50MM2 D8MM CU/SN | 1800108953 | 380 | 2024-06-20 |  | 4200572594 | 30 | 2024-07-29 | 2024-07-29 |  | 2024-08-08 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | LUJISA, S.A. | CEMBRE | A10-M8 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1037 | 1238015500102 | TERM RED DESNUDO 50MM2 CRIMP SN/CU XCT | 1800108953 | 390 | 2024-06-20 |  | 4200571579 | 150 | 2024-07-22 | 2024-07-24 |  | 2024-07-31 | 110 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TE CONNECTIVITY | 710025-5 |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1038 | 1238025102000 | PUNTERA S/AISL D=10X45MM 50MM2 CRIMP CU | 1800108953 | 400 | 2024-06-20 |  | 4200572594 | 40 | 2024-07-29 | 2024-07-29 |  | 2024-08-08 | 65 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | LUJISA, S.A. | CEMBRE | A10-P25 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1039 | 1238500100409 | TERM PREAISL REDONDO AWG12-10 NYLON AMAR | 1800108953 | 410 | 2024-06-20 |  | 4200571557 | 250 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 110 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 267-6441 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1040 | 1238514350100 | TERMINAL PREAIS PUNTERA 35MM2 BEIGE | 1800108953 | 420 | 2024-06-20 |  | 4200572594 | 50 | 2024-07-29 | 2024-07-29 |  | 2024-08-08 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | LUJISA, S.A. | CEMBRE | PKC 35016 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1041 | 1261121205001 | BATERIA RECARG 6CELDAS 12V 14AH | 1800108953 | 430 | 2024-06-20 |  | 4200573595 | 10 | 2024-08-05 | 2024-08-05 |  | 2024-08-20 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | RENOBAT OPTIMIZATION | POWER SONIC | PS-1212 |  | 0 | 0 |  | 7218¦JA2582_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -611 | 0
1042 | 1263011000903 | F.A. 85-264VAC/24VDC 630MA 15,2W DIN RAI | 1800108953 | 440 | 2024-06-20 |  | 4200568000 | 20 | 2024-06-20 | 2024-06-21 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ELECTRONICA OLFER, S.L. | MEAN WELL | HDR-15-24 |  | 0 | 0 |  | 7218¦JA2582_1001 | 25 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1043 | 1263011080700 | F.A. 100/115/200/230VAC +/-12V/0,75A 15W | 1800108953 | 450 | 2024-06-20 |  | 4200568531 | 10 | 2024-06-27 | 2024-06-27 |  | 2024-07-15 | 90 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TDK-LAMBDA CORP | NND15-1212 |  | 0 | 0 |  | 7218¦JA2582_1001 | 18 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1044 | 1263011603300 | F.A. VE=90-264VAC VS=12VDC 6W CNC-P1J | 1800108953 | 460 | 2024-06-20 |  | 4200568000 | 30 | 2024-06-20 | 2024-06-21 |  | 2024-07-15 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ELECTRONICA OLFER, S.L. | MEAN WELL | GS06E-3P1J |  | 0 | 0 |  | 7218¦JA2582_1001 | 25 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1045 | 1263011604400 | F.A. VE=90-264VAC VS=12VDC 18W 1.5A | 1800108953 | 470 | 2024-06-20 |  | 4200568093 | 20 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | XP POWER | 121-7147 |  | 0 | 0 |  | 7218¦JA2582_1001 | 24 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1046 | 1263511130400 | F.A CONM VE=85-264V 1000W SMPS | 1800108953 | 480 | 2024-06-20 |  | 4200568256 | 10 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 40 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XCC |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1047 | 1263516109000 | MOD SALIDA F.A. 3.2-6VDC 40A 200W XGEN | 1800108953 | 490 | 2024-06-20 |  | 4200568256 | 20 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 98 | 8 | Liberado | 16 | 16 | 16 | 0 | 16 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XG2 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 16 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1048 | 1263516109001 | MOD SALIDA F.A. 6-15VDC 20A 240W XGEN | 1800108953 | 500 | 2024-06-20 |  | 4200568256 | 30 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 115 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XG3 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1049 | 1263516109002 | MOD SALIDA F.A. 12-30VDC 10A 240W XGEN | 1800108953 | 510 | 2024-06-20 |  | 4200568256 | 40 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 85 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XG4 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1050 | 1263516109005 | T.PWRMOD 85-264VAC/2,5VDC 50A 125W XLITE | 1800108953 | 520 | 2024-06-20 |  | 4200568256 | 50 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 34 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XG1 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1051 | 1263516109006 | ACC BUS BAR PARALLEL | 1800108953 | 530 | 2024-06-20 |  | 4200568256 | 60 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XP1 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1052 | 1263516109007 | ACC BUS BAR SERIES | 1800108953 | 540 | 2024-06-20 |  | 4200568256 | 70 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 30 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | EXCELSYS TECHNOLOGIES | XS1 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1053 | 1282001480200 | SENSOR TEMP 1U RACK 2XRJ11 | 1800108953 | 550 | 2024-06-20 |  | 4200581755 | 10 | 2024-10-17 | 2024-10-17 |  | 2024-10-25 | 30 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | 600329 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -545 | 0
1054 | 1282001480400 | TEMPERATURA SENSOR CBL EQ RJ11 IP67 3M | 1800108953 | 560 | 2024-06-20 |  | 4200581755 | 20 | 2024-10-17 | 2024-10-17 |  | 2024-10-25 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | 600585 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -545 | 0
1055 | 1285000449000 | BASE STD SUPERFICIE P/DET NFX PC/ABS BL | 1800108953 | 570 | 2024-06-20 |  | 4200582054 | 10 | 2024-10-21 | 2024-10-28 |  | 2024-07-15 | 35 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | BY DEMES, S.L. | NOTIFIER | B501AP |  | 0 | 0 |  | 7218¦JA2582_1001 | -98 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1056 | 1285001000100 | DETECTOR HUMO ALTA SENSIBILIDAD 32VDC BL | 1800108953 | 580 | 2024-06-20 |  | 4200582054 | 20 | 2024-10-21 | 2024-10-28 |  | 2024-07-15 | 40 | 8 | Liberado | 15 | 15 | 15 | 0 | 0 | 0 | X | 0.00 |  | BY DEMES, S.L. | NOTIFIER | NFXI-VIEW |  | 0 | 0 |  | 7218¦JA2582_1001 | -98 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1057 | 1289980760100 | SENSOR HUMEDAD 100%HR P/INT RJ11 CBL 3M | 1800108953 | 590 | 2024-06-20 |  | 4200581755 | 30 | 2024-10-17 | 2024-10-17 |  | 2024-10-25 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | HUMID-1WIRE 3M |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -545 | 0
1058 | 1309005060200 | SPLITTER HUB 1/5 SENSOR 5XRJ11 10CM | 1800108953 | 600 | 2024-06-20 |  | 4200578067 | 10 | 2024-09-20 | 2024-09-20 |  | 2024-10-01 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | HW GROUP | 600356 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -569 | 0
1059 | 1351202410200 | MOD TERM 16SALIDA DIGI 24VDC 3C 500KBPS | 1800108953 | 610 | 2024-06-20 |  | 4200578070 | 10 | 2024-09-20 | 2024-09-23 |  | 2024-09-30 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | PHOENIX CONTACT | 2861292 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -570 | 0
1060 | 1351202410300 | MOD TERM 16ENTRADA DIGI 24VDC 3C 500KBPS | 1800108953 | 620 | 2024-06-20 |  | 4200578070 | 20 | 2024-09-20 | 2024-09-23 |  | 2024-09-30 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | PHOENIX CONTACT | 2861250 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -570 | 0
1061 | 1351705469000 | KIT MONTAJE P/ ID3000 2 LAZOS CAB STAND | 1800108953 | 630 | 2024-06-20 |  | 4200582054 | 30 | 2024-10-21 | 2024-10-28 |  | 2024-07-15 | 80 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | BY DEMES, S.L. | NOTIFIER | ID3004-2-001 |  | 0 | 0 |  | 7218¦JA2582_1001 | -98 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1062 | 1351708680400 | MOD POSEIDON 3468 48VDC 4XDI 2XDO 230V 1 | 1800108953 | 640 | 2024-06-20 |  | 4200581755 | 40 | 2024-10-17 | 2024-10-17 |  | 2024-10-25 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | 600570 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -545 | 0
1063 | 1351800390000 | T MEMORIA FLASH SD 512MB PROGRAM&CONFIG | 1800108953 | 650 | 2024-06-20 |  | 4200570504 | 10 | 2024-07-12 | 2024-07-12 |  | 2024-07-26 | 45 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | PHOENIX CONTACT | 2988146 |  | 0 | 0 |  | 7218¦JA2582_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
1064 | 1390800921000 | MODULO MONITOR 1ENTRADA 15-30VDC 93X94X2 | 1800108953 | 660 | 2024-06-20 |  | 4200582054 | 40 | 2024-10-21 | 2024-10-28 |  | 2024-07-15 | 95 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | BY DEMES, S.L. | NOTIFIER | M710 |  | 0 | 0 |  | 7218¦JA2582_1001 | -98 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1065 | 1390800921002 | MODULO CONTROL 1SALIDA 15-30VDC 93X94X23 | 1800108953 | 670 | 2024-06-20 |  | 4200582054 | 50 | 2024-10-21 | 2024-10-28 |  | 2024-07-15 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | BY DEMES, S.L. | NOTIFIER | M701 |  | 0 | 0 |  | 7218¦JA2582_1001 | -98 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1066 | 1807901190100 | PROBADOR DETECT HUMOS SOLO A10 AER 150ML | 1800108953 | 680 | 2024-06-20 |  | 4200571765 | 10 | 2024-07-23 | 2024-07-24 |  | 2024-07-15 | 35 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | AMIDATA, S.A. | NO CLIMB PRODUCTS LTD | SOLO A10-001 |  | 0 | 0 |  | 7218¦JA2582_1001 | -8 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1067 | G1824224106P2 | CLAVIJA DE ENCHUFE AEREA SOCKET AMERICAN | 1800108953 | 690 | 2024-06-20 |  | 4200571557 | 260 | 2024-07-19 | 2024-07-24 |  | 2024-07-31 | 80 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 488-208 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -631 | 0
1068 | 0918630000000 | CANIF-DIO32 TIPO11A | 1800108957 | 10 | 2024-06-20 |  | 4200569037 | 10 | 2024-07-02 | 2024-07-08 |  | 2024-08-15 | 30 | 8 | Liberado | 45 | 45 | 45 | 0 | 45 | 0 | X | 0.00 |  | ELATE,S.A. | INDRA SISTEMAS S.A. | 0918630000000 |  | 0 | 0 |  | 7218¦JA2586_1001 | 44 | - |  | YES | 45 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -616 | 0
1069 | 0918630010000 | CANIF-DIO32_TIPO21A | 1800108957 | 20 | 2024-06-20 |  | 4200569037 | 20 | 2024-07-02 | 2024-07-08 |  | 2024-08-15 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | ELATE,S.A. | INDRA SISTEMAS S.A. | 0918630010000 |  | 0 | 0 |  | 7218¦JA2586_1001 | 44 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -616 | 0
1070 | 0972828190100 | RTIO SUBRACK MECH | 1800108957 | 30 | 2024-06-20 |  | 4200574772 | 10 | 2024-08-19 | 2024-10-09 |  | 2024-11-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ACOM SISTEMAS, S.L. | INDRA SISTEMAS S.A. | 0972828190100 |  | 1 | 1 |  | 7218¦JA2586_1001 | 100 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -512 | 0
1071 | 0972828203300 | AUDIO MIXER ASSY | 1800108958 | 10 | 2024-06-20 | BORR | 4200569494 | 20 | 2024-07-05 | 2024-07-23 | BORR | 2024-09-10 | 30 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 689.59 |  | AUXITEL, S.L. | INDRA SISTEMAS S.A. | 0972828203300 |  | 0 | 0 |  | 7218¦JA2584_1001 | 67 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -590 | 0
1072 | 1214205530022 | CNC CIR 23-55S/H PLUG RECT AL ZN/NI R-A | 1800108981 | 10 | 2024-06-20 |  | 4200569161 | 380 | 2024-07-02 | 2024-07-04 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZH55SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1073 | 1214205530022 | CNC CIR 23-55S/H PLUG RECT AL ZN/NI R-A | 1800108981 | 10 | 2024-06-20 |  | 4200569022 | 440 | 2024-07-02 |  | BORR | 2024-07-15 | 40 | 8 |  | 2 | 2 | 0 | 2 | 0 | 0 |  | 366.98 |  | ICOMPPLUS ELECTRONICS S.L | MILITARY SPECS. | D38999/26ZH55SA |  | 0 | 0 |  | 7218¦JA2581_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
1074 | 1264611110000 | CONVERT FREQ 220V 45-66HZ 115/200V 400HZ | 1800108985 | 10 | 2024-06-20 |  | 4200568575 | 10 | 2024-06-27 | 2024-07-01 |  | 2024-07-23 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ENELEC, S.L. | MAGNUS POWER | LF3-400 |  | 0 | 0 |  | 7218¦JA2582_1001 | 26 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -639 | 0
1075 | 1232525308000 | CINT ADH ESPUM ACR VHB 4930P 30MM 33M BL | 1800108986 | 10 | 2024-06-20 |  | 4200568827 | 10 | 2024-06-28 | 2024-07-02 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | 3M | 4930P/30MM |  | 0 | 0 |  | 7218¦JA2578_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0 |  | X
1076 | 1509011010190 | TORN PHILIPS M3X10MM C/JUNTA L2615 | 1800108986 | 30 | 2024-06-20 |  | 4200610629 | 10 | 2025-05-13 | 2025-05-14 |  | 2025-05-30 | 60 | 8 | Liberado | 4 | 625 | 625 | 0 | 625 | 0 | X | 0.00 |  | GIZA TECHNOLOGIES, INC | APM-HEXSEAL | RM3X0.5-10MM-L2615 |  | 0 | 0 |  | 7218¦JA2578_1001 | 17 | - |  | YES | 625 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -328 | 0
1077 | 1805710000000 | IMPRIMACION 94 AMBAR APROX 6% SOLIDOS | 1800108986 | 40 | 2024-06-20 |  | 4200562629 | 20 | 2024-05-13 | 2024-07-02 |  | 2024-07-15 | 30 | 8 | Liberado | 3 | 3 | 4 | 0 | 3 | 1 | X | 0.00 |  | Technipol Suministros, S.L. | 3M | 70-0160-5477-0 |  | 0 | 0 |  | 7218¦JA2578_1001 | 63 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1078 | 3210104720300 | LATIGUILLO ETHERNET UTP CAT.6 RJ45 M/M, | 1800108986 | 50 | 2024-06-20 |  | 4200568809 | 10 | 2024-06-28 | 2024-07-01 |  | 2024-07-05 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-10M |  | 0 | 0 |  | 7218¦JA2578_1001 | 7 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
1079 | 3210104720700 | LATIGUILLO ETHERNET UTP CAT.6 RJ45 M/M, | 1800108986 | 60 | 2024-06-20 |  | 4200568809 | 20 | 2024-06-28 | 2024-07-01 |  | 2024-07-05 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-50M |  | 0 | 0 |  | 7218¦JA2578_1001 | 7 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
1080 | 3210104721600 | CBL PATCHCORD ETH CAT6 UTP RJ45 8M BL | 1800108986 | 70 | 2024-06-20 |  | 4200568809 | 30 | 2024-06-28 | 2024-07-01 |  | 2024-07-05 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-8 |  | 0 | 0 |  | 7218¦JA2578_1001 | 7 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
1081 | 3210104722200 | CBL PATCHCORD ETH CAT6 UTP RJ45 15M BL | 1800108986 | 80 | 2024-06-20 |  | 4200568809 | 40 | 2024-06-28 | 2024-07-01 |  | 2024-07-05 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-15 |  | 0 | 0 |  | 7218¦JA2578_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
1082 | 3210104722600 | CBL EQ PATCHCORD ETH RJ-45 LSZH VRD 2M | 1800108986 | 90 | 2024-06-20 |  | 4200568809 | 50 | 2024-06-28 | 2024-07-01 |  | 2024-07-05 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6VR-2 |  | 0 | 0 |  | 7218¦JA2578_1001 | 7 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
1083 | 3210104723400 | CBL EQ PATCHCORD CAT7 RJ45 AMP LSZH 50M | 1800108986 | 100 | 2024-06-20 |  | 4200568809 | 60 | 2024-06-28 | 2024-07-01 |  | 2024-07-05 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT7F-50 |  | 0 | 0 |  | 7218¦JA2578_1001 | 7 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -657 | 0
1084 | 949901050-05 | REGLETA DE TERMINALES MS27212-1-5 | 1800108986 | 110 | 2024-06-20 |  | 4200584548 | 20 | 2024-11-06 | 2024-11-07 |  | 2024-11-18 | 80 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | AMALFI TRADING, INC | MILITARY STANDARDS | MS27212-1-5 |  | 0 | 0 |  | 7218¦JA2578_1001 | 12 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -521 | 0
1085 | M151300125LA6 | ARA PLANA P/M3 INOX ISO7089 | 1800108986 | 120 | 2024-06-20 |  | 4200574689 | 120 | 2024-08-18 | 2024-08-19 |  | 2024-09-05 | 60 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | ELT | M3 DIN 125A A4 |  | 0 | 0 |  | 7218¦JA2578_1001 | 18 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -595 | 0
1086 | 1229598250100 | CBL EQ DP 1.4-M/M 8K DP PRO P/150 L45.7M | 1800108987 | 10 | 2024-06-20 |  | 4200569137 | 40 | 2024-07-02 | 2024-07-05 |  | 2024-07-15 | 40 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | INGE VIDEO, S.A. | EXTRON ELECTRONICS | 26-727-150 |  | 0 | 0 |  | 7218¦JA2578_1001 | 13 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1087 | 1580160080000 | SEPARADOR DE LATON ROSCADO Y TORNILLO PR | 1800108987 | 30 | 2024-06-20 |  | 4200574693 | 70 | 2024-08-18 | 2024-09-05 |  | 2024-09-02 | 42 | 8 | Liberado | 4 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | RS | 221-162 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
1088 | 1586690870000 | ABRAZADERA TUBO 50MM HEX-RANURADO INOX | 1800108987 | 40 | 2024-06-20 |  | 4200574693 | 80 | 2024-08-18 | 2024-09-05 |  | 2024-09-02 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | JCS HI-TORQUE | HTJ50P |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
1089 | 1750100820000 | TUBO FLEX POLIURETANO DINT=45MM E=1,8MM | 1800108987 | 50 | 2024-06-20 |  | 4200571726 | 20 | 2024-07-22 | 2024-07-22 |  | 2024-08-14 | 42 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | ESPIROFLEX | 87100045010 |  | 0 | 0 |  | 7218¦JA2578_1001 | 23 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -617 | 0
1090 | 1753000990000 | VALV MARIPOSA DN40 WAFER/GG25/304/EPDM | 1800108987 | 60 | 2024-06-20 |  | 4200568865 | 10 | 2024-07-01 | 2024-07-04 |  | 2024-08-06 | 75 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | EFFEBI | EA2AA THESIS |  | 1 | 1 |  | 7218¦JA2578_1001 | 36 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
1091 | 1759990510300 | KIT ACTUADOR P/VALVULA DPS 20-85 | 1800108987 | 70 | 2024-06-20 |  | 4200569611 | 20 | 2024-07-05 | 2024-07-09 |  | 2024-08-08 | 65 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | J.J BCN INTEN | KIT DPS J4C 20 -85 |  | 1 | 1 |  | 7218¦JA2578_1001 | 34 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1092 | 1351710230200 | T. 8XRELES 12V 16A SPCO ETH RJ45 TCP/IP | 1800108988 | 10 | 2024-06-20 |  | 4200575347 | 10 | 2024-08-27 | 2024-08-28 |  | 2024-09-04 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORSHOP, S.L. | DEVANTECH | ETH008-B |  | 0 | 0 |  | 7218¦JA2578_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -596 | 0
1093 | 1279990680000 | LUMINACIMETRO MOD. LS-150 | 1800108989 | 10 | 2024-06-20 |  | 4200568610 | 10 | 2024-06-27 | 2024-06-27 |  | 2024-07-15 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AQUATEKNICA, S.A. | KONICA MINOLTA | LS-150 |  | 0 | 0 |  | 7218¦JA2578_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1094 | 1533035000001 | TUERCA EX 0,138-32UNC-2B MS35649-264 CRE | 1800108989 | 20 | 2024-06-20 |  | 4200574691 | 30 | 2024-08-18 | 2024-09-05 |  | 2024-09-02 | 30 | 8 | Liberado | 15 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY STANDARDS | MS35649-264 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
1095 | 1544336000119 | ARA DENT INT #6 CRES MS35333-72 | 1800108989 | 30 | 2024-06-20 |  | 4200574691 | 40 | 2024-08-18 | 2024-09-05 |  | 2024-09-02 | 30 | 8 | Liberado | 15 | 250 | 250 | 0 | 250 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | MS35333-71 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
1096 | 1546129000001 | ARA PLAN #6 D=0.149X0.375" E=0.032" CRES | 1800108989 | 40 | 2024-06-20 |  | 4200574690 | 30 | 2024-08-18 | 2025-04-07 |  | 2024-10-28 | 60 | 8 | Liberado | 15 | 112 | 112 | 0 | 112 | 0 | X | 0.00 |  | AMF MADRID SL | MILITARY STANDARDS | AN960C6 |  | 1 | 1 |  | 7218¦JA2578_1001 | 71 | - |  | YES | 112 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -542 | 0
1097 | 1807300100000.VO | LIMP USO GRAL LOCTITE SF7063 AERO 400ML | 1800108989 | 50 | 2024-06-20 |  | 4200572473 | 10 | 2024-07-26 | 2024-07-29 |  | 2024-08-05 | 80 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | HENKEL CORP. | 2098813 |  | 0 | 0 |  | 7218¦JA2578_1001 | 10 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -626 | 0
1098 | 3010200471700 | MOD SERV LAN 8P RS232/422/485 | 1800108989 | 60 | 2024-06-20 |  | 4200569550 | 10 | 2024-07-05 | 2024-07-05 |  | 2024-08-02 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TEMPEL, S.A. | MOXA | NPORT 6650-8 |  | 0 | 0 |  | 7218¦JA2578_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -629 | 0
1099 | 3140301350000 | PROYECTOR DLP 4K P10 WQXGA 100-240V | 1800108989 | 70 | 2024-06-20 |  | 4200568673 | 20 | 2024-06-27 | 2024-06-27 |  | 2024-09-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | NORXE AS | NORXE | 101-1112 |  | 1 | 1 |  | 7218¦JA2578_1001 | 80 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -585 | 0
1100 | 3140390474100 | LENS PROYECTOR GRANDE 1.20-1.60:1 WQ | 1800108989 | 80 | 2024-06-20 |  | 4200568673 | 10 | 2024-06-27 | 2024-06-27 |  | 2024-09-15 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | NORXE AS | NORXE | N2 |  | 0 | 0 |  | 7218¦JA2578_1001 | 80 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -585 | 0
1101 | 3170100060400 | SWITCH 8-PUERTOS RJ45 10/100/1000 GB | 1800108989 | 90 | 2024-06-20 |  | 4200568831 | 60 | 2024-06-28 | 2024-07-09 | BORR | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 122.00 |  | S-CONNECT SL | NETGEAR | GS308PP |  | 0 | 0 |  | 7218¦JA2578_1001 | 17 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 6 | 100% |  | -647 | 0
1102 | 3170100060400 | SWITCH 8-PUERTOS RJ45 10/100/1000 GB | 1800108989 | 90 | 2024-06-20 |  | 4200569722 | 20 | 2024-07-08 | 2024-07-09 |  | 2024-07-26 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | NETGEAR | GS308PP |  | 1 | 1 |  | 7218¦JA2578_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
1103 | 3170103090800 | SWITCH 16P GIGABIT PROSAFE DESKTOP | 1800108989 | 100 | 2024-06-20 |  | 4200569722 | 10 | 2024-07-08 | 2024-07-09 |  | 2024-07-26 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | NETGEAR | GS116 |  | 1 | 1 |  | 7218¦JA2578_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
1104 | 1587080790400 | ETIQUETA ADH 35X18MM PE BL BMP71 | 1800108998 | 10 | 2024-06-20 |  | 4200569417 | 40 | 2024-07-04 | 2024-07-11 |  | 2024-07-15 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | BRADY | M71EP-7-7593-SL |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1105 | 1587080790700 | ETIQ ADH 27X12,5MM PLATA PE TRASNF TERMI | 1800108998 | 20 | 2024-06-20 |  | 4200569417 | 50 | 2024-07-04 | 2024-07-11 |  | 2024-07-15 | 40 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | BRADY | M71EP-2-7593-SL |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1106 | 1587090070000 | ETIQUETA ADH POLIESTER AMARILLA CIL 9300 | 1800108998 | 30 | 2024-06-20 |  | 4200569417 | 100 | 2024-07-04 | 2024-07-11 |  | 2024-07-15 | 35 | 8 | Liberado | 10 | 10 | 20 | 0 | 10 | 10 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | CILS | 44-LA1786 |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1107 | 1587090080000 | ETIQUETA ADH POLIESTER METALIZAD CIL9200 | 1800108998 | 40 | 2024-06-20 |  | 4200569417 | 110 | 2024-07-04 | 2024-07-11 |  | 2024-07-15 | 42 | 8 | Liberado | 50 | 50 | 100 | 0 | 50 | 50 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | CILS | 44-LA1416 |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1108 | 1130622410200 | MOD RELE SPDT 24VDC 9MA RIF-0-RPT ROHS | 1800109000 | 10 | 2024-06-20 |  | 4200569375 | 20 | 2024-07-04 | 2024-07-04 |  | 2024-08-16 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | PHOENIX CONTACT | 2903359 |  | 0 | 0 |  | 7218¦JA2578_1001 | 43 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -615 | 0
1109 | 1204300420400 | CNC CIR M12/4M RECEPT RECT TOR POLIAMADA | 1800109000 | 20 | 2024-06-20 |  | 4200575495 | 400 | 2024-08-28 | 2024-09-27 |  | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | T4111002041-000 |  | 0 | 0 |  | 7218¦JA2578_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -589 | 0
1110 | 1208000381500 | CNC ALIMEN IEC C14 3M 250VAC 4.8MM PANEL | 1800109000 | 30 | 2024-06-20 |  | 4200573125 | 160 | 2024-08-01 | 2024-12-12 |  | 2024-08-19 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | SCHURTER | 6100.3200 |  | 1 | 1 |  | 7218¦JA2578_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
1111 | 1208000381700 | CNC ALIM C14/3M IEC320 250V/10A C/CNM 2P | 1800109000 | 40 | 2024-06-20 |  | 4200569426 | 20 | 2024-07-04 | 2024-07-05 |  | 2024-07-15 | 85 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | SCHURTER | DC11.0001.001 |  | 0 | 0 |  | 7218¦JA2578_1001 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1112 | 1209996806400 | CBL ACTUATOR ROBOTIC 8M FOR STEP MOTOR | 1800109000 | 50 | 2024-06-20 |  | 4200571614 | 30 | 2024-07-22 | 2024-07-24 |  | 2024-07-26 | 75 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SMC ESPAÑA, S.A. | SMC | LE-CP-8 |  | 0 | 0 |  | 7218¦JA2578_1001 | 4 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
1113 | 1214300420500 | CNC CIR M12/4H RECEPT RECT SOLD ZN-NI | 1800109000 | 60 | 2024-06-20 |  | 4200571560 | 10 | 2024-07-19 | 2024-10-11 |  | 2024-08-02 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 1838891-2 |  | 0 | 0 |  | 7218¦JA2578_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -629 | 0
1114 | 1217000100002 | CNC RJ45 1/1H CAT6 RECT APANT ROHS | 1800109000 | 70 | 2024-06-20 |  | 4200570653 | 180 | 2024-07-15 | 2025-03-28 |  | 2024-07-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 175-0145 |  | 0 | 0 |  | 7218¦JA2578_1001 | 12 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -635 | 0
1115 | 1229513250800 | CBL EQ SENSOR M8-4H/EXT 0.25MM2 GRIS L5M | 1800109000 | 80 | 2024-06-20 |  | 4200572420 | 40 | 2024-07-26 | 2024-09-10 |  | 2024-08-09 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | PEPPERL+FUCHS | V31-GM-5M-PVC |  | 0 | 0 |  | 7218¦JA2578_1001 | 14 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -622 | 0
1116 | 1229599330200 | CBL EQ CONVERSION L300MM P/CONTROL JXC91 | 1800109000 | 90 | 2024-06-20 |  | 4200571614 | 40 | 2024-07-22 | 2024-07-24 |  | 2024-07-26 | 75 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SMC ESPAÑA, S.A. | SMC | P5062-5 |  | 0 | 0 |  | 7218¦JA2578_1001 | 4 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -636 | 0
1117 | 1237000289001 | BORNE DE PASO GRIS 2,5MM2 0,08/4MM2 | 1800109000 | 100 | 2024-06-20 |  | 4200569375 | 30 | 2024-07-04 | 2024-07-04 |  | 2024-07-15 | 110 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | PHOENIX CONTACT | 3031306 |  | 0 | 0 |  | 7218¦JA2578_1001 | 11 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1118 | 1240100630300 | CONTROLADOR SERVO 24V 64P LEFS16R C150MM | 1800109000 | 110 | 2024-06-20 |  | 4200568513 | 10 | 2024-06-27 | 2024-06-27 |  | 2024-07-18 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SMC ESPAÑA, S.A. | SMC | JXC617-LEFS16RB-150-XZ34 |  | 0 | 0 |  | 7218¦JA2578_1001 | 21 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -644 | 0
1119 | 1241300250900 | ACTUADOR ELECTRICO 150MM MOTOR DER 24VDC | 1800109000 | 120 | 2024-06-20 |  | 4200568513 | 20 | 2024-06-27 | 2024-06-27 |  | 2024-07-18 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SMC ESPAÑA, S.A. | SMC | LEFS16RB-150 |  | 0 | 0 |  | 7218¦JA2578_1001 | 21 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -644 | 0
1120 | 1263511140101 | FA CNM 100-240V/24VDC 5/6A 120W P-BOOST | 1800109000 | 130 | 2024-06-20 |  | 4200568104 | 10 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 45 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | OMRON CORPORATION | S8VK-G12024 |  | 0 | 0 |  | 7218¦JA2578_1001 | 24 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1121 | 1289900000001 | SENSOR ULTRASONICO EEPROM 18-30VCC 50MA | 1800109000 | 140 | 2024-06-20 |  | 4200575347 | 30 | 2024-08-27 | 2024-08-28 |  | 2024-09-13 | 70 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORSHOP, S.L. | PEPPERL+FUCHS | UC400-F77-IU-IO-V31 |  | 1 | 0 |  | 7218¦JA2578_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -587 | 0
1122 | 1309006400000 | MOD COM CPU ETH S7-1200 230V PROFINET | 1800109000 | 150 | 2024-06-20 |  | 4200571839 | 40 | 2024-07-23 | 2024-07-23 |  | 2024-08-19 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | SIEMENS | 6ES7215-1BG40-0XB0 |  | 0 | 0 |  | 7218¦JA2578_1001 | 27 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
1123 | 1309006400100 | MOD COM E/S PLC 4IN ANALOG 24V SIMATIC | 1800109000 | 160 | 2024-06-20 |  | 4200571839 | 50 | 2024-07-23 | 2024-07-23 |  | 2024-08-19 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | SIEMENS | 6ES7234-4HE32-0XB0 |  | 0 | 0 |  | 7218¦JA2578_1001 | 27 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
1124 | 1309006400200 | MOD COM E/S PLC 2IN DIGI 5V SIMATIC | 1800109000 | 170 | 2024-06-20 |  | 4200571839 | 60 | 2024-07-23 | 2024-07-23 |  | 2024-08-19 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | SIEMENS | 6ES7223-3AD30-0XB0 |  | 0 | 0 |  | 7218¦JA2578_1001 | 27 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -612 | 0
1125 | 1549011000790 | ARANDELA GROWER M3 INOX A4 | 1800109000 | 180 | 2024-06-20 |  | 4200574693 | 90 | 2024-08-18 | 2024-09-05 |  | 2024-09-02 | 45 | 8 | Liberado | 4 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | RS PRO | 189-686 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -598 | 0
1126 | 1759990311000 | BRIDA DN-40 C/ESP P/MANG 45M/M AC | 1800109000 | 190 | 2024-06-20 |  | 4200568635 | 10 | 2024-06-27 | 2024-07-04 |  | 2024-07-30 | 55 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | VOSS SA | PORTAS EURORAPID | 145040045 |  | 1 | 1 |  | 7218¦JA2578_1001 | 33 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -632 | 0
1127 | 3210300120200 | F.A EQ INTER 36W 50/60HZ 12VDC 2A | 1800109000 | 200 | 2024-06-20 |  | 4200575349 | 10 | 2024-08-27 | 2024-08-28 |  | 2024-09-04 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | POWERPAX | SW4047D |  | 0 | 0 |  | 7218¦JA2578_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -596 | 0
1128 | 1232525506100 | CINTA AMERICANA ADH A50MM G0.18MM PE NEG | 1800109003 | 10 | 2024-06-20 |  | 4200569248 | 10 | 2024-07-03 | 2024-07-05 |  | 2025-03-07 | 85 | 8 | Liberado | 2 | 1200 | 2400 | 0 | 1200 | 1200 | X | 0.00 |  | COMERCIAL DE INDUSTRIA Y | TESA | 4615 BLACK |  | 2 | 1 |  | 7218¦JA2578_1001 | 247 | - |  | YES | 2400 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -412 | 0
1129 | 1263511005000 | F.A. CONM 120-375VAC/24V 21A 504W ROHS | 1800109003 | 20 | 2024-06-20 |  | 4200568117 | 10 | 2024-06-21 | 2024-06-21 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TDK-LAMBDA CORP | GWS500-24 |  | 0 | 0 |  | 7218¦JA2578_1001 | 24 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1130 | 1312600040400 | PANTALLA RETROPROYECCION 6306X2305MM AER | 1800109003 | 30 | 2024-06-20 |  | 4200559664 | 20 | 2024-04-17 | 2024-07-24 |  | 2024-08-29 | 64 | 8 | Liberado | 1 | 4 | 5 | 0 | 4 | 1 | X | 0.00 |  | TECCO, S.L. | STEWART FILMSCREEN C | CUTM2249CAV10 |  | 0 | 0 |  | 7218¦JA2578_1001 | 134 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -602 | 0
1131 | 1800600900000 | ADHESIVO CONTACTO TEROKAL 2444 | 1800109003 | 40 | 2024-06-20 |  | 4200572976 | 10 | 2024-07-31 | 2024-07-31 |  | 2024-08-16 | 90 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | Technipol Suministros, S.L. | HENKEL CORP. | 238403 |  | 0 | 0 |  | 7218¦JA2578_1001 | 16 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -615 | 0
1132 | 1807990092800 | PIEZA RECORTADA ADH GANCHO 25X25MM NEGRO | 1800109003 | 50 | 2024-06-20 |  | 4200569312 | 10 | 2024-07-03 | 2024-07-07 |  | 2024-07-15 | 61 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | FERRETERIA FERAYU SL | VELCRO | EB51025330118476 |  | 0 | 0 |  | 7218¦JA2578_1001 | 12 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1133 | 7279902590000 | TEODOLITO DIGITAL 30X PREC 2" LASER 100M | 1800109003 | 60 | 2024-06-20 |  | 4200569553 | 10 | 2024-07-05 | 2024-07-05 |  | 2024-07-15 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | GIS IBERICA, S.L. | TSINGTAO | DE2A-L |  | 0 | 0 |  | 7218¦JA2578_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1134 | 1390705440000 | CAMARA CALIBRA GIGE FISHEYE 165X165 FOV | 1800109004 | 10 | 2024-06-20 |  | 4200568259 | 10 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ST ENGINEERING ANTYCIP SAS | ST ENGINEERING | GIGE CALIBRATION CAM/GA/SU/202207-070VB |  | 0 | 0 |  | 7218¦JA2578_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1135 | 1390705449000 | SERVICIO SOPORT/MANT 1AÑO OBLIGATORIO | 1800109004 | 20 | 2024-06-20 |  | 4200568259 | 20 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ST ENGINEERING ANTYCIP SAS | ST ENGINEERING | 1YR SUPPORT AND MAINT/GA/SU/202207-070VB |  | 0 | 0 |  | 7218¦JA2578_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1136 | 3166092900000 | LIC SW SIMULADOR SCALABLE DISP MANAGER | 1800109004 | 30 | 2024-06-20 |  | 4200568259 | 30 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 60 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | ST ENGINEERING ANTYCIP SAS | ST ENGINEERING | SCALABLE DISP MANAGER/GA/SU/202207-070VB |  | 0 | 0 |  | 7218¦JA2578_1001 | 21 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1137 | 3210500130300 | USB MEMORIA | 1800109004 | 40 | 2024-06-20 |  | 4200568259 | 40 | 2024-06-24 | 2024-06-26 |  | 2024-07-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ST ENGINEERING ANTYCIP SAS | ANTYCIP | SDINDRA |  | 0 | 0 |  | 7218¦JA2578_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -647 | 0
1138 | 1390705610100 | FILTROS BLENDING OPTICO INACSYS 45 | 1800109005 | 10 | 2024-06-20 |  | 4200577920 | 10 | 2024-09-19 | 2024-09-19 |  | 2024-09-30 | 70 | 8 | Liberado | 1 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | TALLERES XUQUER | 29116 |  | 0 | 0 |  | 7218¦JA2578_1001 | 11 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -570 | 0
1139 | 1702003980000 | CAJA CONTROL VACIO S/OF | 1800109005 | 20 | 2024-06-20 |  | 4200577920 | 20 | 2024-09-19 | 2024-09-19 |  | 2024-09-30 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | XUQUER | 22651 |  | 0 | 0 |  | 7218¦JA2578_1001 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -570 | 0
1140 | 1219000691400 | CAJA PORTACONTACTOS 6H RECT 2,54MM P/POS | 1800109443 | 10 | 2024-06-30 |  | 4200574946 | 30 | 2024-08-21 | 2024-08-26 |  | 2024-08-28 | 80 | 8 | Liberado | 8 | 8 | 16 | 0 | 8 | 8 | X | 0.00 |  | ARISTOS INDUSTRIAL, S.L.U. | ARISTON | CO 3406 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 16 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -603 | 0
1141 | 1149900090500 | CABEZA PILOTO D=22MM PLASTIC BLANCO | 1800109444 | 10 | 2024-06-30 |  | 4200569888 | 40 | 2024-07-09 | 2024-07-10 |  | 2024-07-17 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AV01 |  | 0 | 0 |  | 7218¦JA2612_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -645 | 0
1142 | 0972828200000 | SMOKE DETEC TEMP SENSOR AND AACC ASSY | 1800109445 | 10 | 2024-06-30 |  | 4200571121 | 10 | 2024-07-17 | 2024-07-17 |  | 2024-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AUXITEL, S.L. | INDRA SISTEMAS S.A. | 0972828200000 |  | 1 | 0 |  | 7218¦JA2582_1001 | 106 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -539 | 0
1143 | 0972885290100 | SOPORTE CAMARA | 1800109446 | 10 | 2024-06-30 |  | 4200570620 | 10 | 2024-07-15 | 2024-07-23 |  | 2024-08-07 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0972885290100 |  | 0 | 0 |  | 7218¦JA2578_1001 | 23 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -624 | 0
1144 | 1229590956500 | CBL EQ ETH RJ45/M-M UTP LSZH VERD L300MM | 1800109447 | 10 | 2024-06-30 |  | 4200572714 | 120 | 2024-07-29 | 2024-07-31 |  | 2024-08-02 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | ROLINE | 21.15.3931-100 |  | 1 | 1 |  | 7218¦JA2578_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -629 | 0
1145 | 1706090904000 | RAIL DIN PERF 755X35X7.5MM AC/GALV PLATA | 1800109448 | 10 | 2024-06-30 |  | 4200571961 | 20 | 2024-07-23 | 2024-07-24 |  | 2024-08-08 | 40 | 8 | Liberado | 1 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | LUJISA, S.A. | PHOENIX CONTACT | 1207640 |  | 0 | 0 |  | 7218¦JA2578_1001 | 16 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -623 | 0
1146 | 1520520120012 | VARILLA ROSC M12X120 AC GEOMET 500 DIN91 | 1800109449 | 10 | 2024-06-30 |  | 4200576908 | 10 | 2024-09-11 | 2024-09-11 |  | 2024-10-04 | 40 | 8 | Liberado | 4 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN913-M12X120-AC-12,9-GEOMET B500 |  | 0 | 0 |  | 7218¦JA2578_1001 | 23 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -566 | 0
1147 | 1540220000102 | ARA GROWER M12 DIN127 INOX A4-70 | 1800109449 | 20 | 2024-06-30 |  | 4200572571 | 30 | 2024-07-29 | 2025-01-09 |  | 2024-08-06 | 40 | 8 | Liberado | 8 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | INOX IBERICA, S.A. | DIN | DIN127-M12-INOX-A4-70 |  | 1 | 1 |  | 7218¦JA2578_1001 | 8 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -625 | 0
1148 | 0124880013500 | VARILLA ROSCADA M6X40 | 1800109450 | 10 | 2024-06-30 |  | 4200570042 | 30 | 2024-07-10 | 2024-07-11 |  | 2024-09-20 | 1 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ELGAMA DE MECANIZADOS SA | INDRA SISTEMAS S.A. | 0124880013500 |  | 2 | 1 |  | 7218¦JA2578_1001 | 72 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -580 | 0
1149 | 1209090010320 | PUENTE REGLETA TERM 10P MS25226-2-10 | 1800109451 | 10 | 2024-06-30 |  | 4200592966 | 20 | 2025-01-14 | 2025-01-17 |  | 2025-01-24 | 56 | 0 | Liberado | 1 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MILITARY STANDARDS | MS25226-2-10 |  | 1 | 1 |  | 7218¦JA2578_1001 | 10 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -454 | 0
1150 | 0917488032000 | SOPORTE TEODOLITO | 1800109452 | 10 | 2024-06-30 |  | 4200569529 | 10 | 2024-07-05 | 2024-09-05 |  | 2024-09-27 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0917488032000 |  | 0 | 0 |  | 7218¦JA2578_1001 | 84 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -573 | 0
1151 | 1212000931300 | CNC SUB-D 9H 2.74MM SHELL-E CRIMP ROHS | 1800109470 | 10 | 2024-07-01 |  | 4200578865 | 90 | 2024-09-26 | 2024-12-12 |  | 2025-01-10 | 40 | 8 | Liberado | 35 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL CORP | L177RRE09S |  | 1 | 0 |  | 7218¦JA2581_1001 | 106 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -468 | 0
1152 | 1212000931300 | CNC SUB-D 9H 2.74MM SHELL-E CRIMP ROHS | 1800109470 | 10 | 2024-07-01 |  | 4200571592 | 80 | 2024-07-22 | 2024-09-27 | BORR | 2024-08-12 | 40 | 8 | Liberado | 35 | 35 | 0 | 35 | 0 | 0 |  | 10.15 |  | PEI GENESISUK LTD | AMPHENOL CORP | L177RRE09S |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -619 | 0
1153 | 1138022410200 | SIST CONTROL PROG 24VDC ETH RJ45 IP20 | 1800109478 | 10 | 2024-07-01 |  | 4200570119 | 20 | 2024-07-10 | 2024-07-11 |  | 2024-07-17 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | PHOENIX CONTACT | 2700975 |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -645 | 0
1154 | 1390705220800 | MOT KIT GEN3 MB-E-6DOF-60-14000KG COTS | 1800109484 | 10 | 2024-07-02 | BORR | 4600003976 | 20 | 2024-06-21 | 2024-09-11 | BORR | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 385000.00 |  | MOOG, B.V. | MOOG | CD45841-000A-075-0 |  | 0 | 0 |  | 7218¦JA2612_1001 | 82 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -589 | 0
1155 | 1390705220900 | DAP SHIPMENT OF THE MS | 1800109484 | 20 | 2024-07-02 | BORR | 4600003976 | 60 | 2024-06-21 | 2024-09-11 | BORR | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 8850.00 |  | MOOG, B.V. | MOOG | DM-NL-FRT-NC |  | 0 | 0 |  | 7218¦JA2612_1001 | 82 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -589 | 0
1156 | 1390705220901 | MS INSTALLATION ASSISTANCE | 1800109484 | 30 | 2024-07-02 | BORR | 4600003976 | 70 | 2024-06-21 | 2024-09-11 | BORR | 2024-11-12 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 5720.00 |  | MOOG, B.V. | MOOG | DM-NL-IN-AS-NC |  | 1 | 0 |  | 7218¦JA2612_1001 | 144 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -527 | 0
1157 | 1390705220902 | MS TUNING | 1800109484 | 40 | 2024-07-02 | BORR | 4600003976 | 80 | 2024-06-21 | 2024-09-11 | BORR | 2025-01-13 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 7220.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA90 |  | 1 | 0 |  | 7218¦JA2612_1001 | 206 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -465 | 0
1158 | 1390705220903 | CLS TUNING | 1800109484 | 50 | 2024-07-02 | BORR | 4600003976 | 90 | 2024-06-21 | 2024-09-11 | BORR | 2025-03-15 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 13820.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA130 |  | 1 | 0 |  | 7218¦JA2612_1001 | 267 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -404 | 0
1159 | 1390705220904 | PROJECT MANAGEMENT | 1800109484 | 60 | 2024-07-02 | BORR | 4600003976 | 100 | 2024-06-21 | 2024-09-11 | BORR | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 11710.00 |  | MOOG, B.V. | MOOG | DM-NL-SVCS-NC |  | 0 | 0 |  | 7218¦JA2612_1001 | 82 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -589 | 0
1160 | 1390705220905 | TRAVEL & SUBS.TUNING MS | 1800109484 | 70 | 2024-07-02 | BORR | 4600003976 | 110 | 2024-06-21 | 2024-09-11 | BORR | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 4520.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA150 |  | 0 | 0 |  | 7218¦JA2612_1001 | 82 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -589 | 0
1161 | 1390705220906 | TRAVEL & SUBS. INSTALLATION MS | 1800109484 | 80 | 2024-07-02 | BORR | 4600003976 | 120 | 2024-06-21 | 2024-09-11 | BORR | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 4520.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA160 |  | 0 | 0 |  | 7218¦JA2612_1001 | 82 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -589 | 0
1162 | 1390705220907 | TRAVEL & SUBS.TUNING CLS | 1800109484 | 90 | 2024-07-02 | BORR | 4600003976 | 130 | 2024-06-21 | 2024-09-11 | BORR | 2024-09-11 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 5890.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA170 |  | 0 | 0 |  | 7218¦JA2612_1001 | 82 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -589 | 0
1163 | 1390705220200 | JOINT ASSY BASE 3RD GEN | 1800109516 | 10 | 2024-07-02 |  | 4600003976 | 30 | 2024-06-21 | 2024-09-11 |  | 2024-11-19 | 40 | 8 | Liberado | 1 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | CC81345-001 |  | 1 | 1 |  | 7218¦JA2612_1001 | 151 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -520 | 0
1164 | 1390705220300 | TOP JOINT ASSEMBLY | 1800109516 | 20 | 2024-07-02 |  | 4600003976 | 40 | 2024-06-21 | 2024-09-11 |  | 2024-11-19 | 40 | 8 | Liberado | 1 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | CC82004-001 |  | 1 | 1 |  | 7218¦JA2589_1001 | 151 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -520 | 0
1165 | 1390705220400 | ACC KIT 6-DOF EM/EP GN3 LONG | 1800109516 | 30 | 2024-07-02 |  | 4600003976 | 50 | 2024-06-21 | 2024-09-11 |  | 2025-02-20 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | CB44562-307-1 |  | 1 | 1 |  | 7218¦JA2589_1001 | 244 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -427 | 0
1166 | 1128991608201 | CABEZA PULSADOR D22MM EMPOTRADO AMARIL | 1800110152 | 10 | 2024-07-14 |  | 4200572561 | 80 | 2024-07-29 | 2024-08-05 | BORR | 2024-08-11 | 85 | 8 | Liberado | 6 | 6 | 0 | 6 | 0 | 0 |  | 83.52 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB4BA56 |  | 0 | 0 |  | 7218¦JA2612_1001 | 13 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 7 | 100% |  | -620 | 0
1167 | 1128991608201 | CABEZA PULSADOR D22MM EMPOTRADO AMARIL | 1800110152 | 10 | 2024-07-14 |  | 4200573511 | 10 | 2024-08-05 | 2024-08-05 |  | 2024-08-12 | 85 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | SCHNEIDER ELECTRIC | ZB4BA56 |  | 0 | 0 |  | 7218¦JA2612_1001 | 7 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -619 | 0
1168 | 1530116000003 | TUERCA EX. M6 DIN-934 A4-80 | 1800110153 | 10 | 2024-07-14 |  | 4200575527 | 60 | 2024-08-28 | 2024-08-29 |  | 2024-09-11 | 90 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | EUROPEAN AGENCY MENK | DIN | DIN934-M6-A4-80 |  | 1 | 1 |  | 7218¦JA2578_1001 | 14 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -589 | 0
1169 | 1212090240000 | PIN CNC SUB-D H 20-24AWG (ROLLO 400UD | 1800110154 | 10 | 2024-07-14 |  | 4200572876 | 470 | 2024-07-30 | 2024-10-07 |  | 2024-08-16 | 30 | 8 | Liberado | 15 | 400 | 400 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL CORP | 17RRD1F11400 |  | 0 | 0 |  | 7218¦JA2581_1001 | 17 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -615 | 0
1170 | 1238514160201 | TERM PREAISL REDON TOR 0,25-1,6MM2 M8 NY | 1800110154 | 20 | 2024-07-14 |  | 4200572558 | 10 | 2024-07-29 | 2024-07-29 |  | 2024-08-16 | 110 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | AMP INC | 320572 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -615 | 0
1171 | 1540112000001 | ARA PLANA P/M3.5 INOX DIN125 | 1800110155 | 10 | 2024-07-14 |  | 4200572571 | 20 | 2024-07-29 | 2025-01-09 |  | 2024-08-20 | 35 | 8 | Liberado | 400 | 10000 | 10000 | 0 | 10000 | 0 | X | 0.00 |  | INOX IBERICA, S.A. | DIN | DIN125-A3,7-A2-70 |  | 0 | 0 |  | 7218¦JA2583_1001 | 22 | - |  | YES | 10000 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -611 | 0
1172 | 0917447970000 | NPORT TO MASK CONTROLLERS BUNDLES | 1800110156 | 10 | 2024-07-14 |  | 4200574237 | 10 | 2024-08-12 | 2024-08-13 |  | 2024-11-15 | 45 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INTEGRAL DE CONEXIÓN Y MONTAJES S.L | INDRA SISTEMAS S.A. | 0917447970000 |  | 1 | 1 |  | 7218¦JA2578_1001 | 95 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -524 | 0
1173 | 0917447970400 | CBL PWR CONTROLADORA MASCARAS | 1800110156 | 20 | 2024-07-14 |  | 4200574237 | 20 | 2024-08-12 | 2024-08-13 |  | 2025-03-31 | 60 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INTEGRAL DE CONEXIÓN Y MONTAJES S.L | INDRA SISTEMAS S.A. | 0917447970400 |  | 5 | 5 |  | 7218¦JA2578_1001 | 231 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -388 | 0
1174 | 3210104720300 | LATIGUILLO ETHERNET UTP CAT.6 RJ45 M/M, | 1800110156 | 70 | 2024-07-14 |  | 4200570880 | 50 | 2024-07-16 | 2024-07-18 |  | 2024-07-31 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-10M |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -631 | 0
1175 | 3210104721600 | CBL PATCHCORD ETH CAT6 UTP RJ45 8M BL | 1800110156 | 80 | 2024-07-14 |  | 4200570880 | 60 | 2024-07-16 | 2024-07-18 |  | 2024-07-31 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-8 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -631 | 0
1176 | 3210104722200 | CBL PATCHCORD ETH CAT6 UTP RJ45 15M BL | 1800110156 | 90 | 2024-07-14 |  | 4200570880 | 70 | 2024-07-16 | 2024-07-18 |  | 2024-07-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-15 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -631 | 0
1177 | 3210104722600 | CBL EQ PATCHCORD ETH RJ-45 LSZH VRD 2M | 1800110156 | 100 | 2024-07-14 |  | 4200570880 | 80 | 2024-07-16 | 2024-07-18 |  | 2024-07-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6VR-2 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -631 | 0
1178 | 3210104723400 | CBL EQ PATCHCORD CAT7 RJ45 AMP LSZH 50M | 1800110156 | 110 | 2024-07-14 |  | 4200570880 | 90 | 2024-07-16 | 2024-07-18 |  | 2024-07-31 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT7F-50 |  | 0 | 0 |  | 7218¦JA2578_1001 | 15 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -631 | 0
1179 | 1229500260611 | CBL EQ ETH 2XRJ45/M CAT6A LSZH AZL L0.5M | 1800110200 | 50 | 2024-07-15 |  | 4200572679 | 60 | 2024-07-29 | 2025-02-21 |  | 2024-08-14 | 105 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 778-5149 |  | 0 | 0 |  | 7218¦JA2578_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -617 | 0
1180 | 1289900000001 | SENSOR ULTRASONICO EEPROM 18-30VCC 50MA | 1800110200 | 90 | 2024-07-15 |  | 4200575347 | 40 | 2024-08-27 | 2024-08-28 |  | 2024-09-13 | 70 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORSHOP, S.L. | PEPPERL+FUCHS | UC400-F77-IU-IO-V31 |  | 1 | 0 |  | 7218¦JA2578_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -587 | 0
1181 | 1263511005000 | F.A. CONM 120-375VAC/24V 21A 504W ROHS | 1800110201 | 70 | 2024-07-15 |  | 4200571192 | 10 | 2024-07-18 | 2024-07-21 |  | 2024-08-14 | 40 | 8 | Liberado | 3 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TDK-LAMBDA CORP | GWS500-24 | X | 0 | 0 |  | 7218¦JA2578_1001 | 27 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -617 | 0 |  | X
1182 | 1246001770100 | VENT CENTRIFUGO MULTIETAP 240V 1PH 00069 | 1800110416 | 10 | 2024-07-17 |  | 4200571243 | 10 | 2024-07-18 | 2024-07-21 |  | 2024-08-30 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | AIR CONTROL INDUSTRI | 2MS8-00069 |  | 0 | 0 |  | 7218¦JA2578_1001 | 43 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -601 | 0
1183 | 1000234703030 | RST PELMET 470R00 5% 1/4W 100PPM 0207 | 1800110417 | 10 | 2024-07-17 |  | 4200584478 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-18 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | MILITARY SPECS. | RLR07C4700JR |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -521 | 0
1184 | 1000245621010 | RST PELMET 5K62 1% 1/4W RLR07C5621F | 1800110417 | 20 | 2024-07-17 |  | 4200580493 | 670 | 2024-10-09 | 2024-10-09 |  | 2024-10-30 | 50 | 0 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | MILITARY SPECS. | RLR07C5621F |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -540 | 0
1185 | 1060273000000 | LED 5MM AZUL 465NM 2700MCD 3,3V 2P TH | 1800110417 | 40 | 2024-07-17 |  | 4200579301 | 140 | 2024-10-01 | 2024-10-22 |  | 2024-10-19 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | KINGBRIGHT | L-7113QBC-D |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -551 | 0
1186 | 1060283000000 | LED 5MM BLANCO 2300MCD 3,2V 65G 515D TH | 1800110417 | 50 | 2024-07-17 |  | 4200579301 | 300 | 2024-10-01 | 2024-10-22 |  | 2024-10-19 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | NICHIA | NSPW515DS |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -551 | 0
1187 | 1060900210000 | SOPORTE LED T-1 3/4 5MM PLASTIC NEGRO | 1800110417 | 60 | 2024-07-17 |  | 4200579301 | 10 | 2024-10-01 | 2024-10-22 |  | 2024-10-19 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | AGILENT TECHNOLOGIES | HLMP-0103 |  | 0 | 0 |  | 7218¦JA2581_1001 | 18 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -551 | 0
1188 | 1130115010701 | RELE MINI SPDT 5V 0,3A DIL-6 DR-SDS | 1800110417 | 70 | 2024-07-17 |  | 4200580009 | 10 | 2024-10-04 | 2024-10-07 |  | 2024-10-28 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | NAIS/MASUSHITA | DR-5V-SDS |  | 0 | 0 |  | 7218¦JA2581_1001 | 24 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -542 | 0
1189 | 1204100633620 | CNC CIR 10-6 6P (M) MS3470L10-6P | 1800110417 | 80 | 2024-07-17 |  | 4200580192 | 30 | 2024-10-07 | 2024-10-21 |  | 2024-10-19 | 41 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3470L10-6P |  | 0 | 0 |  | 7218¦JA2581_1001 | 12 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -551 | 0
1190 | 1209994000109 | ACC CARCASA P/CNC SUB-D ZINC | 1800110417 | 90 | 2024-07-17 |  | 4200583052 | 730 | 2024-10-25 | 2025-02-08 |  | 2025-01-17 | 80 | 8 | Liberado | 50 | 100 | 0 | 100 | 0 | 0 |  | 1650.00 |  | TTI INC. | TE CONNECTIVITY | 1-2308346-6 |  | 0 | 0 |  | 7218¦JA2581_1001 | 84 | - | [5 empty] | 1 |  | 0% | 4200583052 |  |  |  | 7 | 100% |  | -461 | 0
1191 | 1219990020620 | CONTACTO HEMBRA SIZE 20 M39029/57-357 | 1800110417 | 100 | 2024-07-17 |  | 4200579010 | 10 | 2024-09-27 | 2024-10-01 |  | 2024-10-19 | 80 | 8 | Liberado | 80 | 80 | 80 | 0 | 80 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | M39029/57-357 |  | 0 | 0 |  | 7218¦JA2581_1001 | 22 | - |  | YES | 80 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -551 | 0
1192 | 1237090082100 | BORNA RAIL 21P #22 5A TYP4 | 1800110417 | 110 | 2024-07-17 |  | 4200585921 | 30 | 2024-11-15 | 2024-11-22 |  | 2025-02-10 | 30 | 8 | Liberado | 5 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | SOURIAU | SOURIAU | 8559N2204B |  | 0 | 0 |  | 7218¦JA2581_1001 | 87 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -437 | 0
1193 | 1220114402004 | CBL FLEX 1X4MM2 750V H07V-K VERDE/AMARIL | 1800110418 | 10 | 2024-07-17 |  | 4200574196 | 190 | 2024-08-09 | 2025-12-18 |  | 2024-08-25 | 85 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 902-8432 |  | 1 | 1 |  | 7218¦JA2582_1001 | 16 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -606 | 0
1194 | 1220114602013 | VBL FLEX 1X6MM2 750V H07V-K VERDE/AMARIL | 1800110418 | 20 | 2024-07-17 |  | 4200574196 | 200 | 2024-08-09 | 2025-12-18 |  | 2024-08-25 | 85 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 902-8451 |  | 1 | 1 |  | 7218¦JA2582_1001 | 16 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -606 | 0
1195 | 1000242711000 | RST PELMET 2K74 1% 1/4W 50PPM 0207 ROHS | 1800110423 | 10 | 2024-07-17 |  | 4200572167 | 140 | 2024-07-24 | 2024-07-24 |  | 2024-08-19 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | ROYAL OHM | MF 1/4W 1% 50PPM T/B-1000 2K74 |  | 0 | 0 |  | 7218¦JA2584_1001 | 26 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1196 | 1206500321500 | CNC AUDIO XLR 3M 16A PLUG ACOD SOLD RX | 1800110423 | 20 | 2024-07-17 |  | 4200572835 | 10 | 2024-07-30 | 2024-09-10 |  | 2024-08-19 | 85 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | NEUTRIK | NC3MRX |  | 0 | 0 |  | 7218¦JA2584_1001 | 20 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1197 | 1206500328000 | CNC JACK PLUG(M) STEREO 3,5MM RECT SOLD | 1800110423 | 30 | 2024-07-17 |  | 4200574843 | 10 | 2024-08-20 | 2024-09-27 |  | 2024-10-14 | 85 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | LUMBERG CONNECT GMBH | KLS 40 |  | 1 | 0 |  | 7218¦JA2584_1001 | 55 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -556 | 0
1198 | 1208000220002 | CNC ENCHUFE ALIM 2P 250VAC TYPE F 16A RO | 1800110423 | 40 | 2024-07-17 |  | 4200574196 | 210 | 2024-08-09 | 2025-12-18 |  | 2024-08-25 | 80 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 8496112 |  | 1 | 1 |  | 7218¦JA2584_1001 | 16 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -606 | 0
1199 | 1209001020000 | CNC HEADER 10P (M) PASO 3,96MM S/PCB SER | 1800110423 | 50 | 2024-07-17 |  | 4200573533 | 10 | 2024-08-05 | 2024-08-05 |  | 2024-08-19 | 85 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | CENVALSA, S.L. | CONEXCON | 3968-2101 |  | 0 | 0 |  | 7218¦JA2584_1001 | 14 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1200 | 1218000320500 | CNC RED 3H RECT 240V 10A IEC320-C13 SCRW | 1800110423 | 60 | 2024-07-17 |  | 4200574196 | 220 | 2024-08-09 | 2025-12-18 |  | 2024-08-25 | 35 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 488-208 |  | 1 | 1 |  | 7218¦JA2584_1001 | 16 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -606 | 0
1201 | 1218000320501 | CNC RED 3H 250VAC 10A ACOD IEC | 1800110423 | 70 | 2024-07-17 |  | 4200574509 | 120 | 2024-08-14 | 2024-08-14 |  | 2024-08-30 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | LUJISA, S.A. | BULGIN | PX0587/SE |  | 0 | 0 |  | 7218¦JA2584_1001 | 16 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -601 | 0
1202 | 1229502470000 | CBL EQ EXTENSION CCP BNC-BNC 50R L=3M | 1800110423 | 80 | 2024-07-17 |  | 4200574397 | 10 | 2024-08-13 | 2024-08-14 |  | 2024-08-28 | 70 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | GRAS SOUND & VIBRATI | AA0035 |  | 0 | 0 |  | 7218¦JA2584_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -603 | 0
1203 | 1229508980000 | CBL EQ BNC-M/M 75R RG59/U PVC L=0.5M | 1800110423 | 90 | 2024-07-17 |  | 4200574196 | 230 | 2024-08-09 | 2025-12-18 |  | 2024-08-25 | 105 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 122-2147 |  | 1 | 1 |  | 7218¦JA2584_1001 | 16 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -606 | 0
1204 | 1229591920606 | CBL EQ USB(A/B) 3M AZ | 1800110423 | 100 | 2024-07-17 |  | 4200574196 | 240 | 2024-08-09 | 2025-12-18 |  | 2024-08-25 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | RS PRO | 182-8838 |  | 1 | 1 |  | 7218¦JA2584_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -606 | 0
1205 | 1239024369000 | MANG AUTOSOLD DI=3.68MM L=18.25MM PVDF R | 1800110423 | 110 | 2024-07-17 |  | 4200572876 | 800 | 2024-07-30 | 2024-10-07 |  | 2024-08-23 | 30 | 8 | Liberado | 400 | 400 | 400 | 0 | 400 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL CORP | SO96-2-00 |  | 1 | 1 |  | 7218¦JA2584_1001 | 24 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -608 | 0
1206 | 1250100210700 | ALTAVOZ BI-AMPED 54HZ-30KHZ 70W NEGR MDF | 1800110423 | 120 | 2024-07-17 |  | 4200573620 | 10 | 2024-08-05 | 2024-08-05 |  | 2024-10-31 | 65 | 8 | Liberado | 6 | 6 | 6 | 0 | 0 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. | YAMAHA | HS5I |  | 1 | 1 |  | 7218¦JA2584_1001 | 87 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -539 | 0
1207 | 1250100870100 | ALTAVOZ AUTO AMPLI 132-20000HZ 40W 230VA | 1800110423 | 130 | 2024-07-17 |  | 4200578629 | 10 | 2024-09-25 | 2024-09-25 |  | 2024-09-30 | 55 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | FONESTAR SISTEMAS, S.A. | FONESTAR | AMBIENT-20A |  | 0 | 0 |  | 7218¦JA2584_1001 | 5 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -570 | 0
1208 | 1250200510200 | PREAMPLIFICADOR MIC 12CH DIGI AVB/MADI | 1800110423 | 140 | 2024-07-17 |  | 4200576815 | 10 | 2024-09-11 | 2024-09-11 |  | 2024-09-25 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | RME INTELLIGENT AUDI | 12MIC |  | 0 | 0 |  | 7218¦JA2584_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -575 | 0
1209 | 1251000100200 | CAPSULA MICROFONICA DINAMICA 2204-I | 1800110423 | 150 | 2024-07-17 |  | 4200573414 | 10 | 2024-08-02 | 2024-08-03 |  | 2024-10-18 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | FOX ELECTRONICS | 2204-I |  | 1 | 1 |  | 7218¦JA2584_1001 | 77 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -552 | 0
1210 | 1251000380100 | MICROFONO PRESION 1/2” 3.5HZ-20KHZ CCP | 1800110423 | 160 | 2024-07-17 |  | 4200578472 | 10 | 2024-09-24 | 2024-09-24 |  | 2024-10-02 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SOUND OF NUMBERS SL | GRAS SOUND & VIBRATI | 46AO |  | 0 | 0 |  | 7218¦JA2584_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -568 | 0
1211 | 1252500140000 | SISTEMA MEZCLA AURICULAR 6-CANALES | 1800110423 | 170 | 2024-07-17 |  | 4200574241 | 10 | 2024-08-12 | 2024-08-13 |  | 2024-08-19 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PRESONUS AUDIO | HP60 |  | 0 | 0 |  | 7218¦JA2584_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1212 | 1263011094800 | FA 85-264VAC 12(12-16)VDC 2.5A 30W C-DIN | 1800110423 | 180 | 2024-07-17 |  | 4200571846 | 10 | 2024-07-23 | 2024-07-23 |  | 2024-08-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 58.46 |  | AMIDATA, S.A. | TRACO POWER | TBL 030-112 |  | 0 | 0 |  | 7218¦JA2584_1001 | 27 | - | [5 empty] | 1 |  | 0% | 4200571846 |  |  |  | 7 | 100% |  | -612 | 0
1213 | 1263011992600 | F.A. CCP 2XAA/3-6VDC 28V 4MA BNC | 1800110423 | 190 | 2024-07-17 |  | 4200572023 | 10 | 2024-07-24 | 2024-07-24 |  | 2024-09-19 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | GRAS SOUND & VIBRATI | 12AL |  | 0 | 0 |  | 7218¦JA2584_1001 | 57 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -581 | 0
1214 | 1312702890000 | MOD PROCESADO 12ENT/8SAL SOUNDWEB LONDON | 1800110423 | 200 | 2024-07-17 |  | 4200573417 | 10 | 2024-08-02 | 2024-08-03 |  | 2024-08-19 | 45 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | HARMAN INTERNATIONAL | BLU-100 12X8 |  | 0 | 0 |  | 7218¦JA2584_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1215 | 1312704910100 | MOD CONV D/A 32CH 192KHZ I/O MADI/ADAT | 1800110423 | 210 | 2024-07-17 |  | 4200573419 | 10 | 2024-08-02 | 2024-08-03 |  | 2024-09-04 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | RME INTELLIGENT AUDI | M-32 DA |  | 1 | 1 |  | 7218¦JA2584_1001 | 33 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -596 | 0
1216 | 1351709000800 | MOD INTERFAZ AUDIO 192KHZ 188-CH USB3.0 | 1800110423 | 220 | 2024-07-17 |  | 4200577053 | 10 | 2024-09-12 | 2024-09-12 |  | 2024-09-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | REBOUND ELECTRONICS (UK) LTD | RME INTELLIGENT AUDI | FIREFACE UFX III |  | 0 | 0 |  | 7218¦JA2584_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -572 | 0
1217 | 1390400090100 | PREAMPLIFICADOR 6-18V MONO P/MICROFONO | 1800110423 | 230 | 2024-07-17 |  | 4200572601 | 10 | 2024-07-29 | 2024-07-31 |  | 2024-08-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | CEBEK | PM-1 |  | 0 | 0 |  | 7218¦JA2584_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1218 | 1589903549000 | ADAPT P/MICRO 1/2-1/4 CAB GIR P/TRIP 1/4 | 1800110423 | 240 | 2024-07-17 |  | 4200583542 | 10 | 2024-10-29 | 2024-10-31 |  | 2024-11-13 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | GRAS SOUND & VIBRATI | AL0003 |  | 0 | 0 |  | 7218¦JA2584_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -526 | 0
1219 | 1589991012301 | ANCLAJE 16MM HEX M5 1/4" P/13-55MM NE | 1800110423 | 250 | 2024-07-17 |  | 4200583543 | 10 | 2024-10-29 | 2024-10-31 |  | 2024-11-08 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MANFROTTO | MAN035 |  | 0 | 0 |  | 7218¦JA2584_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -531 | 0
1220 | 1589991012400 | PASADOR CORTO REV M/M 3/8"-1/4" BRONCE | 1800110423 | 260 | 2024-07-17 |  | 4200583543 | 20 | 2024-10-29 | 2024-10-31 |  | 2024-11-08 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MANFROTTO | MAN037 |  | 0 | 0 |  | 7218¦JA2584_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -531 | 0
1221 | 3170412070000 | MOD SFP MADI MULTIMOD C/CBL2M/ACOP-SC-SC | 1800110423 | 270 | 2024-07-17 |  | 4200573419 | 20 | 2024-08-02 | 2024-08-03 |  | 2024-09-04 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | RME INTELLIGENT AUDI | 1001059 |  | 1 | 1 |  | 7218¦JA2584_1001 | 33 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -596 | 0
1222 | 7279902131200 | CALIBRADOR ACUSTICO 94-114DB 1KHZ | 1800110423 | 280 | 2024-07-17 |  | 4200574241 | 20 | 2024-08-12 | 2024-08-13 |  | 2024-08-19 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | GRAS SOUND & VIBRATI | 42AG |  | 0 | 0 |  | 7218¦JA2584_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1223 | 7279902131290 | ACC ADAPT CALIBRADOR/PREAMPLIFICADOR XLR | 1800110423 | 290 | 2024-07-17 |  | 4200574241 | 30 | 2024-08-12 | 2024-08-13 |  | 2024-08-19 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | GRAS SOUND & VIBRATI | AG0003 |  | 0 | 0 |  | 7218¦JA2584_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -612 | 0
1224 | 3010201822301 | WS Z4 RACK G5 2X 675W RTXA6000 RCTO S/OF | 1800111048 | 10 | 2024-07-26 |  | 4200573319 | 40 | 2024-08-02 | 2024-08-02 |  | 2024-09-30 | 40 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | 52258736/7178862 |  | 1 | 1 |  | 7218¦JA2585_1001 | 59 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -570 | 0
1225 | 3010201822302 | WS Z4 RACK G5 2X 675W T1000 RCTO S/OF | 1800111048 | 20 | 2024-07-26 |  | 4200573319 | 50 | 2024-08-02 | 2024-08-02 |  | 2024-09-30 | 40 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | 52258775/7178862 |  | 1 | 1 |  | 7218¦JA2585_1001 | 59 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -570 | 0
1226 | 3170408510000 | MOD ETH I350-T4 4P 10/100/1000MBPS 1GB N | 1800111111 | 10 | 2024-07-26 |  | 4200573319 | 100 | 2024-08-02 | 2024-08-02 |  | 2024-09-06 | 40 | 8 | Liberado | 14 | 14 | 14 | 0 | 0 | 0 | X | 0.00 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | W8X25AA |  | 0 | 0 |  | 7218¦JA2585_1001 | 35 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -594 | 0
1227 | 3010201822302 | WS Z4 RACK G5 2X 675W T1000 RCTO S/OF | 1800111329 | 10 | 2024-07-30 |  | 4200573319 | 130 | 2024-08-02 | 2024-08-02 |  | 2024-09-30 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | 52258775/7178862 |  | 1 | 1 |  | 7218¦JA2585_1001 | 59 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -570 | 0
1228 | 1229599576000 | CBL EQ P/MOD SERV INTERFACE KVM | 1800111380 | 10 | 2024-07-31 |  | 4200574815 | 50 | 2024-08-20 | 2024-08-23 |  | 2024-09-14 | 135 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | DELL COMPUTER | DMPUIQ-VMCHS-G01 |  | 0 | 0 |  | 7218¦JA2585_1001 | 25 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -586 | 0
1229 | 1706201180000 | KIT SOPORTE MJE. RED 1U P/ KVM FPM185 | 1800111380 | 20 | 2024-07-31 |  | 4200574079 | 10 | 2024-08-08 | 2024-08-08 |  | 2024-08-31 | 105 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | DELL COMPUTER, S.A. | DELL COMPUTER | DRMK-77 |  | 1 | 1 |  | 7218¦JA2585_1001 | 23 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -600 | 0
1230 | 3120201290701 | RACK VX IT 80X200X120CM RAL7035 S/OF | 1800111380 | 30 | 2024-07-31 |  | 4200574840 | 20 | 2024-08-20 | 2024-09-23 |  | 2024-10-30 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | RITTAL, S.A | RITTAL | 5311099/1080079921 |  | 2 | 1 |  | 7218¦JA2585_1001 | 71 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -540 | 0
1231 | 3170107821000 | SWITCH P/RACK KVM 8P 1600X1200P | 1800111380 | 40 | 2024-07-31 |  | 4200573684 | 20 | 2024-08-06 | 2024-08-07 |  | 2024-08-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | DAKOTA COMPUTER SOLUTIONS, S.L. | AVOCENT CORPORATION | AV3108 |  | 1 | 1 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -604 | 0
1232 | 3170107821090 | CBL EQ PARA SWITCH KVM 4,572MM | 1800111380 | 50 | 2024-07-31 |  | 4200574863 | 10 | 2024-08-20 | 2024-09-25 |  | 2024-10-04 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | DAKOTA COMPUTER SOLUTIONS, S.L. | EMERSON NETWORK POWE | USBIAC-15 |  | 1 | 1 |  | 7218¦JA2585_1001 | 45 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -566 | 0
1233 | 3170108870000 | MOD SWITCH KVM ANALOG 16-PORT S/OFERTA | 1800111380 | 60 | 2024-07-31 |  | 4200574079 | 20 | 2024-08-08 | 2024-08-08 |  | 2024-08-31 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | DELL COMPUTER, S.A. | DELL COMPUTER | DAV2216-G01/16745028-4 |  | 1 | 1 |  | 7218¦JA2585_1001 | 23 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -600 | 0
1234 | 3170108880000 | CONSOLA KVM-USB-18,5" 1U | 1800111380 | 70 | 2024-07-31 |  | 4200574079 | 30 | 2024-08-08 | 2024-08-08 |  | 2024-08-31 | 135 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | DELL COMPUTER, S.A. | DELL COMPUTER | A7485910 |  | 1 | 1 |  | 7218¦JA2585_1001 | 23 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -600 | 0
1235 | 3210505150000 | CBL EQ SERV INTERF DISP USB MED-VIRT CAC | 1800111380 | 80 | 2024-07-31 |  | 4200573684 | 30 | 2024-08-06 | 2024-08-07 |  | 2024-08-27 | 40 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | DAKOTA COMPUTER SOLUTIONS, S.L. | AVOCENT CORPORATION | MPUIQ-VMCDP |  | 1 | 1 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -604 | 0
1236 | 3210505160000 | MODULO SERV INTERF DVI USB MED-VIRT CAC | 1800111380 | 90 | 2024-07-31 |  | 4200573684 | 40 | 2024-08-06 | 2024-08-07 |  | 2024-08-27 | 75 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | DAKOTA COMPUTER SOLUTIONS, S.L. | AVOCENT CORPORATION | MPUIQ-VMCDV |  | 1 | 1 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -604 | 0
1237 | 3210512000200 | ADAPT USB-C/DISPLAYPORT 4K 60HZ CBL=14CM | 1800111380 | 100 | 2024-07-31 |  | 4200575188 | 10 | 2024-08-26 | 2024-08-26 |  | 2024-09-23 | 40 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. | STARTECH.COM LTD | CDP2DP |  | 0 | 0 |  | 7218¦JA2585_1001 | 28 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -577 | 0
1238 | 1218000070000 | REGLETA RED 9 TOMAS 2P+T 250VAC 10/16A L | 1800111381 | 10 | 2024-07-31 |  | 4200574096 | 10 | 2024-08-08 | 2024-08-20 |  | 2024-09-08 | 35 | 8 | Liberado | 12 | 12 | 12 | 0 | 12 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 60110-202 |  | 0 | 0 |  | 7218¦JA2585_1001 | 31 | - |  | YES | 12 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -592 | 0
1239 | 1214003233731 | CNC CIR 18-32 32P/H PLUG MS3476L18-32SX | 1800111382 | 10 | 2024-07-31 |  | 4200579210 | 40 | 2024-09-30 | 2024-10-04 |  | 2024-10-11 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L18-32SX |  | 0 | 0 |  | 7218¦JA2581_1001 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -559 | 0
1240 | 1214103233621 | CNC CIR 18-32 32P (H) MS3470L18-32SW | 1800111382 | 20 | 2024-07-31 |  | 4200578014 | 20 | 2024-09-19 | 2024-10-04 |  | 2024-10-10 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3470L18-32SW |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -560 | 0
1241 | 1214103233627 | CNC CIR 18-32 32P/H CRIMP RECEPT MS3470 | 1800111382 | 30 | 2024-07-31 |  | 4200578014 | 30 | 2024-09-19 | 2024-10-04 |  | 2024-10-10 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3470L18-32S |  | 0 | 0 |  | 7218¦JA2581_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -560 | 0
1242 | 1214003132620 | CNC CIR 18-31 31P (H) PLUG M83723/75R183 | 1800111383 | 10 | 2024-07-31 |  | 4200574818 | 500 | 2024-08-20 | 2024-08-23 |  | 2024-09-14 | 56 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M83723/75R1831N |  | 0 | 0 |  | 7218¦JA2581_1001 | 25 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -586 | 0
1243 | 1232025385900 | MANG IDENTIF TERMO 1-1/2" 3:1 POLIO BLAN | 1800111383 | 20 | 2024-07-31 |  | 4200578517 | 300 | 2024-09-24 | 2025-07-01 |  | 2024-11-05 | 40 | 8 | Liberado | 1 | 250 | 250 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | TMS-SCE-1-1/2-2.0-9 |  | 0 | 0 |  | 7218¦JA2581_1001 | 42 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -534 | 0
1244 | 1204206631120 | CNC CIR 19-35 66M STRAIGHT PLUG D38999 | 1800111384 | 10 | 2024-07-31 |  | 4200574818 | 510 | 2024-08-20 | 2024-08-23 |  | 2024-09-14 | 55 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | D38999/26ZF35PN |  | 0 | 0 |  | 7218¦JA2584_1001 | 25 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -586 | 0
1245 | 1214306631920 | CNC CIR 19-35 66H RECPT CRMP ZN/NI ROT-N | 1800111384 | 20 | 2024-07-31 |  | 4200574818 | 520 | 2024-08-20 | 2024-08-23 |  | 2024-09-14 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | D38999/20ZF35SN |  | 0 | 0 |  | 7218¦JA2584_1001 | 25 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -586 | 0
1246 | 1581200080000 | NIVELADOR PIES 30-80MM C/AJUSTE INTERIOR | 1800111385 | 10 | 2024-07-31 |  | 4200573990 | 50 | 2024-08-08 | 2024-08-08 |  | 2024-09-03 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | RITTAL, S.A | RITTAL | VX 5301.326 |  | 0 | 0 |  | 7218¦JA2585_1001 | 26 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -597 | 0
1247 | 1706700040700 | KIT/GUIA MONTAJE P/RACK NAS INSTALACION | 1800111385 | 20 | 2024-07-31 |  | 4200573989 | 30 | 2024-08-08 | 2024-08-09 |  | 2024-09-03 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | V-VALLEY ADVANCED SOLUTIONS | QNAP SYSTEMS, INC | RAIL-B02 |  | 0 | 0 |  | 7218¦JA2585_1001 | 26 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -597 | 0
1248 | 1709904970600 | MOD C/RUEDAS P/800MM VX IT | 1800111385 | 30 | 2024-07-31 |  | 4200573990 | 60 | 2024-08-08 | 2024-08-08 |  | 2024-09-03 | 75 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | RITTAL, S.A | RITTAL | 5301.518 |  | 0 | 0 |  | 7218¦JA2585_1001 | 26 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -597 | 0
1249 | 3030700470000 | PROCESADOR INTEL XEON D-1622 3.2GHZ 32GB | 1800111385 | 40 | 2024-07-31 |  | 4200575187 | 20 | 2024-08-26 | 2024-08-26 |  | 2024-10-11 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. | QNAP SYSTEMS, INC | TS-H1886XU-RP-R2-D1622-32G |  | 1 | 1 |  | 7218¦JA2585_1001 | 46 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -559 | 0
1250 | 3060301930600 | DISCO DURO SSD 2TB SATA3 2.5" 870QVO NEG | 1800111385 | 50 | 2024-07-31 |  | 4200574133 | 10 | 2024-08-09 | 2024-08-09 |  | 2024-08-30 | 40 | 8 | Liberado | 24 | 24 | 24 | 0 | 24 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | SAMSUNG | MZ-77Q2T0BW |  | 1 | 1 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 24 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -601 | 0
1251 | 3170408510000 | MOD ETH I350-T4 4P 10/100/1000MBPS 1GB N | 1800111385 | 60 | 2024-07-31 |  | 4200575061 | 10 | 2024-08-22 | 2024-08-22 |  | 2024-09-03 | 40 | 8 | Liberado | 14 | 14 | 14 | 0 | 0 | 0 | X | 0.00 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | W8X25AA |  | 0 | 0 |  | 7218¦JA2585_1001 | 12 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -597 | 0
1252 | 3170101514700 | SWICHT 28 PORT 10-GB PRO 4 SFP+ | 1800111813 | 10 | 2024-08-13 |  | 4200575920 | 10 | 2024-09-03 | 2024-10-10 |  | 2024-10-31 | 50 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | NETGEAR | XS728T-100NES |  | 1 | 1 |  | 7218¦JA2585_1001 | 58 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -539 | 0
1253 | 3170102910900 | SWITCH 24 PORT 10X100X1000BASE-T SFP+ | 1800111813 | 20 | 2024-08-13 |  | 4200575920 | 20 | 2024-09-03 | 2024-10-10 |  | 2024-10-31 | 45 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | NETGEAR | GSM4328S-100NES |  | 1 | 1 |  | 7218¦JA2585_1001 | 58 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -539 | 0
1254 | 3170106020100 | SWITCH 52P 176GBPS 10/1000GBASE US/EU | 1800111813 | 30 | 2024-08-13 |  | 4200575920 | 30 | 2024-09-03 | 2024-10-10 |  | 2024-10-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | NETGEAR | GSM4352S-100NES |  | 1 | 1 |  | 7218¦JA2585_1001 | 58 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -539 | 0
1255 | 1390706230000 | A320 UPDATE DATA PACKAGE AND SIMULATOR S | 1800111872 | 10 | 2024-08-19 |  | 4200577940 | 10 | 2024-09-19 | 2024-10-23 |  | 2024-11-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AIRBUS OPERATIONS SAS | AIRBUS INDUSTRIE | UPDATE DATA PACK/SIM SW PACK A320/ CT240 |  | 1 | 0 |  | 7218¦JA2576_1001 | 57 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -524 | 0
1256 | 1390706240000 | A320 DOCUMENTATION AND PERFORMANCE PACKA | 1800111872 | 20 | 2024-08-19 |  | 4200577940 | 50 | 2024-09-19 | 2024-10-23 | BORR | 2025-03-19 | 40 | 8 | Liberado | 2 | 1 | 0 | 1 | 0 | 0 |  | 11600.00 |  | AIRBUS OPERATIONS SAS | AIRBUS INDUSTRIE | DOC/PERFOR PACKAGE A320/ CT2402857_V1 | X | 0 | 0 |  | 7218¦JA2576_1001 | 181 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 8 | 100% |  | -400 | 0 |  | X
1257 | 1390706240000 | A320 DOCUMENTATION AND PERFORMANCE PACKA | 1800111872 | 20 | 2024-08-19 |  | 4200577940 | 20 | 2024-09-19 | 2024-10-23 |  | 2024-11-15 | 40 | 8 | Liberado | 2 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AIRBUS OPERATIONS SAS | AIRBUS INDUSTRIE | DOC/PERFOR PACKAGE A320/ CT2402857_V1 | X | 1 | 0 |  | 7218¦JA2576_1001 | 57 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -524 | 0 |  | X
1258 | 1390706250000 | A320 HARDWARE COMPLETE KIT | 1800111872 | 30 | 2024-08-19 |  | 4200577940 | 30 | 2024-09-19 | 2024-10-23 | BORR | 2025-03-19 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 38300.00 |  | AIRBUS OPERATIONS SAS | AIRBUS INDUSTRIE | HARDWARE COMPLETE KIT A320/ D24022442_V1 |  | 0 | 0 |  | 7218¦JA2576_1001 | 181 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 8 | 100% |  | -400 | 0
1259 | 1390706250000 | A320 HARDWARE COMPLETE KIT | 1800111872 | 30 | 2024-08-19 |  | 4200582116 | 10 | 2024-10-21 | 2024-10-21 |  | 2025-03-19 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AIRBUS OPERATIONS SAS | AIRBUS INDUSTRIE | HARDWARE COMPLETE KIT A320/ D24022442_V1 |  | 0 | 0 |  | 7218¦JA2576_1001 | 149 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -400 | 0
1260 | 1390706270000 | A320 SUPPLEMENTARY ENGINE | 1800111872 | 40 | 2024-08-19 |  | 4200577940 | 40 | 2024-09-19 | 2024-10-23 |  | 2024-11-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AIRBUS OPERATIONS SAS | AIRBUS INDUSTRIE | SUPPLEMENTARY ENGINE A320/ D24022442_V1 |  | 1 | 0 |  | 7218¦JA2576_1001 | 57 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -524 | 0
1261 | 1580160200000 | SEPARADOR HEXAG M3X25MM LATON M/H | 1800111887 | 10 | 2024-08-20 |  | 4200576702 | 10 | 2024-09-10 | 2024-09-10 |  | 2024-09-30 | 42 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | RS | 606-709 |  | 0 | 0 |  | 7218¦JA2583_1001 | 20 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -570 | 0
1262 | 1000242000103 | RST PELMET AXI 2K00 0.1% 15PPM 1/4W ROHS | 1800111888 | 10 | 2024-08-20 |  | 4200575813 | 530 | 2024-09-02 | 2024-09-03 |  | 2024-10-21 | 100 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TE CONNECTIVITY | YR1B2K0CC |  | 1 | 0 |  | 7218¦JA2581_1001 | 49 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -549 | 0
1263 | 1004743006009 | TERMISTOR NTC 3K0 +-0.2K 60MW 2.41X6.5MM | 1800111888 | 20 | 2024-08-20 |  | 4200575669 | 20 | 2024-08-29 | 2024-08-29 |  | 2024-09-13 | 100 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | EPCOS AG | B57863S0302F040 |  | 0 | 0 |  | 7218¦JA2581_1001 | 15 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -587 | 0
1264 | 1231024570900 | TAPA TERMO 4:1 POLEO 5,72-1,27MM L=30MM | 1800111888 | 30 | 2024-08-20 |  | 4200577486 | 50 | 2024-09-16 | 2024-09-25 | BORR | 2024-09-21 | 60 | 8 | Liberado | 500 | 500 | 0 | 500 | 0 | 0 |  | 61.35 |  | FARNELL COMPONENTS, S.L. | TE CONNECTIVITY | ES-CAP-NO.1-C1-X-30MM |  | 0 | 0 |  | 7218¦JA2581_1001 | 5 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 8 | 100% |  | -579 | 0
1265 | 1231024570900 | TAPA TERMO 4:1 POLEO 5,72-1,27MM L=30MM | 1800111888 | 30 | 2024-08-20 |  | 4200579563 | 490 | 2024-10-02 | 2024-10-15 |  | 2024-10-16 | 60 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | ES-CAP-NO.1-C1-X-30MM |  | 0 | 0 |  | 7218¦JA2581_1001 | 14 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -554 | 0
1266 | 1501233006000 | TOR ALOM CRUC 4-40UNCX6 INOX DIN7985 | 1800111888 | 40 | 2024-08-20 |  | 4200589242 | 10 | 2024-12-10 | 2024-12-11 |  | 2025-01-07 | 30 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | DIN | DIN7985-4-40UNCX6-A2-70 |  | 0 | 0 |  | 7218¦JA2581_1001 | 28 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -471 | 0
1267 | 1540915000001 | ARA ABA EXT P/M5 INOX DIN 6798A | 1800111888 | 50 | 2024-08-20 |  | 4200585891 | 10 | 2024-11-15 | 2024-11-25 |  | 2024-11-25 | 30 | 8 | Liberado | 150 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN6798-A5,1-A2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 10 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -514 | 0
1268 | 1209994000011 | ACC P/CNC SUB-D 4-40UNC ROHS | 1800111889 | 10 | 2024-08-20 |  | 4200576577 | 20 | 2024-09-09 | 2024-09-10 |  | 2025-04-10 | 85 | 8 | Liberado | 200 | 210 | 210 | 0 | 210 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | ITT CANNON | D20420-158 |  | 0 | 0 |  | 7218¦JA2581_1001 | 213 | - |  | YES | 210 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -378 | 0
1269 | 1130115020300 | RELE SPDT 5V/2A 1/8W S/PCB DIL-6 SELLADO | 1800111910 | 10 | 2024-08-20 |  | 4200577265 | 250 | 2024-09-13 | 2025-01-08 | BORR | 2024-09-20 | 29 | 0 | Liberado | 10 | 10 | 0 | 10 | 0 | 0 |  | 50.00 |  | TELKRON, S.A. | RS AMIDATA | 217-3087 |  | 1 | 1 |  | 7218¦JA2581_1001 | 7 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 8 | 100% |  | -580 | 0
1270 | 1130115020300 | RELE SPDT 5V/2A 1/8W S/PCB DIL-6 SELLADO | 1800111910 | 10 | 2024-08-20 |  | 4200579213 | 60 | 2024-09-30 | 2024-10-02 |  | 2024-10-07 | 29 | 0 | Liberado | 10 | 10 | 20 | 0 | 10 | 10 | X | 0.00 |  | TELKRON, S.A. | RS AMIDATA | 217-3087 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -563 | 0
1271 | 1351001440100 | T. CPU COMPACTPCI 3U E-2276ML 16GB-DDR4 | 1800111911 | 10 | 2024-08-20 |  | 4200577916 | 10 | 2024-09-19 | 2024-09-20 |  | 2024-11-29 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | QNV, S.L. | ADLINK TECHNOLOGY/NU | CPCI-3520/2276ML/M16/S128 |  | 0 | 0 |  | 7218¦JA2586_1001 | 71 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -510 | 0
1272 | 1206500321400 | CNC AUDIO 1/4” 3M PLUG RECT S/CBL PX | 1800111912 | 10 | 2024-08-20 |  | 4200576736 | 80 | 2024-09-10 | 2024-10-11 |  | 2024-09-23 | 30 | 8 | Liberado | 35 | 35 | 35 | 0 | 35 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | NEUTRIK | NP3X |  | 0 | 0 |  | 7218¦JA2584_1001 | 13 | - |  | YES | 35 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -577 | 0
1273 | 1219000292300 | CAJA PORTACONTACTOS 10P (H) PASO 3,96MM | 1800111912 | 20 | 2024-08-20 |  | 4200577705 | 300 | 2024-09-18 | 2025-02-24 |  | 2024-10-02 | 80 | 8 | Liberado | 10 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | CONEXCON | 3940-2101 |  | 1 | 1 |  | 7218¦JA2584_1001 | 14 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -568 | 0
1274 | 1221100222010 | CBL APANT 1XAWG22 PVDF 600V BL-BL | 1800111912 | 30 | 2024-08-20 |  | 4200579563 | 180 | 2024-10-02 | 2024-10-15 |  | 2024-10-30 | 45 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A1111-22-9-9 |  | 0 | 0 |  | 7218¦JA2584_1001 | 28 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -540 | 0
1275 | 1221200222221 | CBL APAN 2XAWG22 PVDF 600V CUSN NE/BL-BL | 1800111912 | 40 | 2024-08-20 |  | 4200576351 | 30 | 2024-09-06 | 2025-01-20 |  | 2024-10-28 | 55 | 8 | Liberado | 500 | 500 | 500 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | TE CONNECTIVITY | 44A1121-22-0/9-9 |  | 1 | 0 |  | 7218¦JA2584_1001 | 52 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -542 | 0
1276 | 1230524620000 | FUND CBL 1/4" CBL 1/8-1/2" FR POLIES NEG | 1800111912 | 50 | 2024-08-20 |  | 4200578313 | 70 | 2024-09-23 | 2024-11-14 |  | 2024-12-02 | 50 | 8 | Liberado | 300 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | WESTERN FILAMENT, INC | FR0250BK |  | 0 | 0 |  | 7218¦JA2584_1001 | 70 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -507 | 0
1277 | 1230590020000.LO | FUNDA CABLE EXPAND-A-FLEX 1/2" NEGRA | 1800111912 | 60 | 2024-08-20 |  | 4200578313 | 10 | 2024-09-23 | 2024-11-14 |  | 2024-10-14 | 45 | 8 | Liberado | 100 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | WESTERN FILAME | FR 1/2" NEGRA |  | 0 | 0 |  | 7218¦JA2584_1001 | 21 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -556 | 0
1278 | 1250101570000 | ALTAVOZ SUBWOOFER 170W 20-200HZ SUB/HPF | 1800111913 | 10 | 2024-08-20 |  | 4200579160 | 10 | 2024-09-30 | 2024-09-30 |  | 2024-10-08 | 85 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PRESONUS AUDIO | TEMBLOR T10 |  | 0 | 0 |  | 7218¦JA2584_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -562 | 0
1279 | 1251000590000 | MICROFONO COND UNIDIREC C/CBL 105DB | 1800111913 | 20 | 2024-08-20 |  | 4200580721 | 10 | 2024-10-10 | 2024-10-10 |  | 2024-10-21 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | KASILH TELECOM, SL | AUDIO-TECHNICA | PRO42 |  | 0 | 0 |  | 7218¦JA2584_1001 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -549 | 0
1280 | 1580160080000 | SEPARADOR DE LATON ROSCADO Y TORNILLO PR | 1800111913 | 30 | 2024-08-20 |  | 4200587937 | 30 | 2024-11-29 | 2025-03-06 |  | 2025-01-13 | 42 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | AMIDATA, S.A. | RS | 221-162 |  | 1 | 1 |  | 7218¦JA2584_1001 | 45 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -465 | 0
1281 | 1580160090000 | SEPARADOR HEXAG M3 M/H L=5MM LATON NI | 1800111914 | 10 | 2024-08-20 |  | 4200587937 | 40 | 2024-11-29 | 2025-03-06 |  | 2025-01-13 | 30 | 8 | Liberado | 400 | 400 | 400 | 0 | 400 | 0 | X | 0.00 |  | AMIDATA, S.A. | RS | 606-670 |  | 1 | 1 |  | 7218¦JA2583_1001 | 45 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -465 | 0
1282 | 1237700220000 | TERM PREAISL RED AWG20-16 P/M4 NYLON ROJ | 1800111915 | 10 | 2024-08-20 |  | 4200577642 | 110 | 2024-09-17 | 2024-09-23 |  | 2024-09-25 | 65 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | LUJISA, S.A. | XB | EF-15043 |  | 0 | 0 |  | 7218¦JA2581_1001 | 8 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -575 | 0
1283 | 1220114152601 | CBL FLEX 1X1,5MM2 750V TIPO E AZUL LH | 1800112244 | 10 | 2024-09-02 |  | 4200580284 | 10 | 2024-10-07 | 2024-10-07 |  | 2024-10-14 | 55 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | TE CONNECTIVITY | 100G0111-1.50-6 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -556 | 0
1284 | 1238000183100 | TERMINAL FASTON H AWG22-18 RECT CRIMP | 1800112244 | 20 | 2024-09-02 |  | 4200579565 | 170 | 2024-10-02 | 2024-10-03 |  | 2025-04-09 | 40 | 8 | Liberado | 200 | 20000 | 20000 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 42510-2 |  | 0 | 0 |  | 7218¦JA2581_1001 | 189 | - |  | YES | 20000 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -379 | 0
1285 | 1220114152003 | CBL FLEX 1X1,5MM2 750V TIPO E NEGRO LH | 1800112245 | 10 | 2024-09-02 |  | 4200579565 | 180 | 2024-10-02 | 2024-10-03 |  | 2024-10-09 | 60 | 8 | Liberado | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | 100G0111-1.50-0 |  | 0 | 0 |  | 7218¦JA2581_1001 | 7 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -561 | 0
1286 | 1390704692500 | PANEL EMERGENCIA IOS 135X60MM AL 6061T6 | 1800112246 | 10 | 2024-09-02 |  | 4200576574 | 10 | 2024-09-09 | 2024-09-10 |  | 2024-11-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40401 |  | 0 | 0 |  | 7218¦JA2588_1001 | 79 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -512 | 0
1287 | 1390705220800 | MOT KIT GEN3 MB-E-6DOF-60-14000KG COTS | 1800112332 | 10 | 2024-09-04 |  | 4600003976 | 140 | 2024-06-21 | 2024-09-11 |  | 2024-10-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | CD45841-000A-075-0 |  | 1 | 1 |  | 7218¦JA2612_1001 | 116 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -555 | 0
1288 | 1390705220900 | DAP SHIPMENT OF THE MS | 1800112332 | 20 | 2024-09-04 |  | 4600003976 | 150 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | DM-NL-FRT-NC |  | 2 | 2 |  | 7218¦JA2612_1001 | 283 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -388 | 0
1289 | 1390705220901 | MS INSTALLATION ASSISTANCE | 1800112332 | 30 | 2024-09-04 |  | 4600003976 | 160 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | DM-NL-IN-AS-NC |  | 2 | 2 |  | 7218¦JA2612_1001 | 283 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -388 | 0
1290 | 1390705220902 | MS TUNING | 1800112332 | 40 | 2024-09-04 |  | 4600003976 | 170 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 7216.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA90 |  | 1 | 1 |  | 7218¦JA2612_1001 | 283 | - | [5 empty] | 1 |  | 0% | 4600003976 |  |  |  | 9 | 100% |  | -388 | 0
1291 | 1390705220903 | CLS TUNING | 1800112332 | 50 | 2024-09-04 |  | 4600003976 | 180 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 13825.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA130 |  | 2 | 1 |  | 7218¦JA2612_1001 | 283 | - | [5 empty] | 1 |  | 0% | 4600003976 |  |  |  | 9 | 100% |  | -388 | 0
1292 | 1390705220904 | PROJECT MANAGEMENT | 1800112332 | 60 | 2024-09-04 |  | 4600003976 | 190 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | DM-NL-SVCS-NC |  | 2 | 2 |  | 7218¦JA2612_1001 | 283 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -388 | 0
1293 | 1390705220905 | TRAVEL & SUBS.TUNING MS | 1800112332 | 70 | 2024-09-04 |  | 4600003976 | 200 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 4520.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA150 |  | 2 | 2 |  | 7218¦JA2612_1001 | 283 | - | [5 empty] | 1 |  | 0% | 4600003976 |  |  |  | 9 | 100% |  | -388 | 0
1294 | 1390705220906 | TRAVEL & SUBS. INSTALLATION MS | 1800112332 | 80 | 2024-09-04 |  | 4600003976 | 210 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA160 |  | 2 | 2 |  | 7218¦JA2612_1001 | 283 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -388 | 0
1295 | 1390705220907 | TRAVEL & SUBS.TUNING CLS | 1800112332 | 90 | 2024-09-04 |  | 4600003976 | 220 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 5895.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA170 |  | 2 | 2 |  | 7218¦JA2612_1001 | 283 | - | [5 empty] | 1 |  | 0% | 4600003976 |  |  |  | 9 | 100% |  | -388 | 0
1296 | 1390704693802 | DISPLAY UNITS AIRBUS DU S/OF | 1800112394 | 10 | 2024-09-05 |  | 4200576289 | 10 | 2024-09-06 | 2024-09-11 |  | 2025-02-08 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ47701 |  | 1 | 1 |  | 7218¦JA2583_1001 | 155 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -439 | 0
1297 | 1237090092100 | BORNA RAIL 10P #20 7,5A TYP11 | 1800112395 | 10 | 2024-09-05 |  | 4200581619 | 10 | 2024-10-16 | 2025-04-07 |  | 2025-01-03 | 30 | 8 | Liberado | 6 | 50 | 50 | 50 | 0 | 50 |  | 837.00 |  | SOURIAU | SOURIAU | 8559N2011B |  | 0 | 0 |  | 7218¦JA2581_1001 | 79 | - | [5 empty] | 1 |  | 0% | 4200581619 |  |  |  | 9 | 100% |  | -475 | 0
1298 | 0973588030000 | PLACA UNION | 1800112396 | 10 | 2024-09-05 |  | 4200577157 | 10 | 2024-09-13 | 2024-09-16 |  | 2024-11-01 | 1 | 8 | Liberado | 3 | 3 | 6 | 0 | 3 | 3 | X | 0.00 |  | ACOM SISTEMAS, S.L. | INDRA SISTEMAS S.A. | 0973588030000 |  | 0 | 0 |  | 7218¦JA2580_1001 | 49 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -538 | 0
1299 | 1253000430700 | HEADSET DINAMICO 600R XLR AIRMAN750 | 1800112685 | 10 | 2024-09-17 |  | 4200578156 | 10 | 2024-09-20 | 2024-09-20 |  | 2024-10-07 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | TELEX COMMUNICATIONS | 64300-210 |  | 0 | 0 |  | 7218¦JA2584_1001 | 17 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -563 | 0
1300 | 1237790902000 | TERM PUNT P/CDTOR FLEX 70 D=25 | 1800112686 | 10 | 2024-09-17 |  | 4200581503 | 40 | 2024-10-16 | 2024-10-18 |  | 2024-10-23 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CEMBRE | A14-P30 |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -547 | 0
1301 | 1750101350000 | TUBERIA FLEX DE=90MM DS=98MM -10/60C PVC | 1800112686 | 20 | 2024-09-17 |  | 4200592269 | 10 | 2025-01-08 | 2025-01-09 |  | 2025-01-17 | 50 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | FERRETERIA FERAYU SL | URARTU | 122090 |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -461 | 0
1302 | 1311006740100 | CAMARA PLANO MOV NW 2MP 1920X1080P H.265 | 1800112687 | 10 | 2024-09-17 |  | 4200577930 | 10 | 2024-09-19 | 2024-09-19 |  | 2024-10-18 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HANWHA TECHWIN EUROPA | XNV-6012 |  | 0 | 0 |  | 7218¦JA2587_1001 | 29 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -552 | 0
1303 | 1589990170000 | ESTUCHE P/IPAD 10TH GEN POLICARB ATLAS | 1800113048 | 10 | 2024-09-26 |  | 4200593363 | 10 | 2025-01-16 | 2025-01-17 |  | 2025-02-06 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORSHOP, S.L. | PIVOT CASE | PC-A22A-BLU |  | 0 | 0 |  | 7218¦JA2588_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -441 | 0
1304 | 1589990179000 | ACC MONT PERMANENTE INOX P/ESTUCHE PIVOT | 1800113048 | 20 | 2024-09-26 |  | 4200593363 | 20 | 2025-01-16 | 2025-01-17 |  | 2025-02-06 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORSHOP, S.L. | PIVOT CASE | S8FB700 |  | 0 | 0 |  | 7218¦JA2588_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -441 | 0
1305 | 3140301350000 | PROYECTOR DLP 4K P10 WQXGA 100-240V | 1800113115 | 10 | 2024-09-27 |  | 4200579103 | 10 | 2024-09-30 | 2024-10-02 |  | 2024-11-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | NORXE AS | NORXE | 101-1112 |  | 0 | 0 |  | 7218¦JA2578_1001 | 59 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -511 | 0
1306 | 3140390474100 | LENS PROYECTOR GRANDE 1.20-1.60:1 WQ | 1800113115 | 20 | 2024-09-27 |  | 4200579103 | 20 | 2024-09-30 | 2024-10-02 |  | 2024-11-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | NORXE AS | NORXE | N2 |  | 0 | 0 |  | 7218¦JA2578_1001 | 59 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -511 | 0
1307 | 1390701501301 | SOPORTE ESPEJO | 1800113121 | 10 | 2024-09-29 | BORR | 4600004111 | 10 | 2024-10-09 |  | BORR | 2024-11-10 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 60665.00 |  | TALLERES XUQUER, SL | XUQUER | 0712061000001 |  | 0 | 0 |  | 7218¦JA2578_1001 | 32 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 9 | 100% |  | -529 | 0
1308 | 1390701501302 | CIERRE SUPERIOR | 1800113121 | 20 | 2024-09-29 | BORR | 4600004111 | 20 | 2024-10-09 |  | BORR | 2024-11-10 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 16655.00 |  | TALLERES XUQUER, SL | XUQUER | 0918686422200 |  | 0 | 0 |  | 7218¦JA2578_1001 | 32 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 9 | 100% |  | -529 | 0
1309 | 1390701501304 | CIERRE POSTERIOR SUPERIOR+ANILLO ADAPT | 1800113121 | 40 | 2024-09-29 | BORR | 4600004111 | 30 | 2024-10-09 |  | BORR | 2024-11-10 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 11802.00 |  | TALLERES XUQUER, SL | XUQUER | 0913385042700 |  | 0 | 0 |  | 7218¦JA2578_1001 | 32 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 9 | 100% |  | -529 | 0
1310 | 1390701501306 | PANEL POSTERIOR | 1800113121 | 60 | 2024-09-29 | BORR | 4600004111 | 40 | 2024-10-09 |  | BORR | 2024-11-10 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 19854.00 |  | TALLERES XUQUER, SL | XUQUER | 0712062000001 |  | 0 | 0 |  | 7218¦JA2578_1001 | 32 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 9 | 100% |  | -529 | 0
1311 | 1390701501308 | BPS MATIZADA | 1800113121 | 80 | 2024-09-29 | BORR | 4600004111 | 50 | 2024-10-09 |  | BORR | 2024-11-10 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 38605.00 |  | TALLERES XUQUER, SL | XUQUER | 0712064000001 |  | 0 | 0 |  | 7218¦JA2578_1001 | 32 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 9 | 100% |  | -529 | 0
1312 | 1250100210600 | ALTAVOZ COMPACT 67HZ-22KHZ 99DB SPL | 1800113122 | 10 | 2024-09-29 |  | 4200580209 | 10 | 2024-10-07 | 2024-10-07 |  | 2024-11-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | KASILH TELECOM, SL | YAMAHA | MSP3A |  | 1 | 0 |  | 7218¦JA2587_1001 | 39 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -524 | 0
1313 | 1500811004001 | TOR AV CRUC M3X4 INOX DIN965/ISO7046 | 1800113158 | 10 | 2024-09-30 |  | 4200592618 | 20 | 2025-01-10 | 2025-01-13 |  | 2025-01-21 | 60 | 8 | Liberado | 400 | 400 | 400 | 0 | 400 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | DIN | DIN965-M3X4-A2-70-H |  | 0 | 0 |  | 7218¦JA2583_1001 | 11 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -457 | 0
1314 | 1390701501303 | SOPORTE PANTALLA BPS | 1800113274 | 10 | 2024-10-02 | BORR | 4600004111 | 60 | 2024-10-09 |  | BORR | 2024-12-16 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 7941.00 |  | TALLERES XUQUER, SL | XUQUER | 0918686423300 |  | 0 | 0 |  | 7218¦JA2590_1001 | 68 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -493 | 0
1315 | 1390701501305 | CERRAMIENTO INFERIOR | 1800113274 | 20 | 2024-10-02 | BORR | 4600004111 | 70 | 2024-10-09 |  | BORR | 2024-12-16 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 3639.00 |  | TALLERES XUQUER, SL | XUQUER | 0918686403700 |  | 0 | 0 |  | 7218¦JA2590_1001 | 68 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -493 | 0
1316 | 1390701501307 | ESTRUCTURA PROY BANDEJA PROY SOPORT MASC | 1800113274 | 30 | 2024-10-02 | BORR | 4600004111 | 80 | 2024-10-09 |  | BORR | 2024-12-16 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 13236.00 |  | TALLERES XUQUER, SL | XUQUER | 0712063000001 |  | 0 | 0 |  | 7218¦JA2590_1001 | 68 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -493 | 0
1317 | 1000242431001 | RST PELMET AXI 2K43 1% 50PPM 3/5W 0207 R | 1800113277 | 10 | 2024-10-02 |  | 4200580190 | 60 | 2024-10-07 | 2024-10-08 |  | 2024-10-27 | 100 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | VISHAY | MBB02070C2431FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 20 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1318 | 1000251000003 | RST PELMET 10K 0,1% 1/4W 15PPM 0207 | 1800113277 | 20 | 2024-10-02 |  | 4200580190 | 70 | 2024-10-07 | 2024-10-08 |  | 2024-10-27 | 100 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RS AMIDATA | 166-728 |  | 0 | 0 |  | 7218¦JA2583_1001 | 20 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1319 | 1000252702001 | RST PELMET 27K00 2% 1/4W 50PPM 0207 SE | 1800113277 | 30 | 2024-10-02 |  | 4200584732 | 10 | 2024-11-07 | 2024-11-08 |  | 2024-11-18 | 138 | 0 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | VISHAY/DALE | RCMM02 27K 2% K3 |  | 0 | 0 |  | 7218¦JA2583_1001 | 11 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -521 | 0
1320 | 1000261802050 | RST PELMET 180K 1% 50PPM 0,6W 0207 ROHS | 1800113277 | 40 | 2024-10-02 |  | 4200580190 | 80 | 2024-10-07 | 2024-10-08 |  | 2024-10-27 | 100 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | VISHAY | MRS25000C1803FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 20 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1321 | 1000942801000 | RST PELMET 2K80 1% 1/4W 100PPM | 1800113277 | 50 | 2024-10-02 |  | 4200580190 | 90 | 2024-10-07 | 2024-10-08 |  | 2024-10-27 | 100 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | VISHAY | CCF-502801F |  | 0 | 0 |  | 7218¦JA2583_1001 | 20 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1322 | 1209500900300 | CNC HEADER 1X9M 2,54MM PCB RECT LAT/AU | 1800113277 | 60 | 2024-10-02 |  | 4200582207 | 230 | 2024-10-21 | 2025-04-30 |  | 2024-11-04 | 85 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 22.60 |  | FARNELL COMPONENTS, S.L. | MOLEX | 70543-0008 |  | 1 | 1 |  | 7218¦JA2583_1001 | 14 | - | [5 empty] | 1 |  | 0% | 4200582207 |  |  |  | 10 | 100% |  | -535 | 0
1323 | 1209501002300 | CNC HEADER 1X10M 2,54MM PCB RECT LAT/SN | 1800113277 | 70 | 2024-10-02 |  | 4200582207 | 240 | 2024-10-21 | 2025-04-30 |  | 2024-11-04 | 85 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 23.40 |  | FARNELL COMPONENTS, S.L. | MOLEX | 70543-0044 |  | 1 | 1 |  | 7218¦JA2583_1001 | 14 | - | [5 empty] | 1 |  | 0% | 4200582207 |  |  |  | 10 | 100% |  | -535 | 0
1324 | 1350100110100 | PCB TIPO MATRIZ 100X160MM EUROCARD SRBP | 1800113277 | 80 | 2024-10-02 |  | 4200580190 | 100 | 2024-10-07 | 2024-10-08 |  | 2024-10-27 | 95 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RS | 206-8648 |  | 0 | 0 |  | 7218¦JA2583_1001 | 20 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1325 | 3166097300005 | LIC SW FG FUNCTION ROYALTY/SIM C/DONGLE | 1800113362 | 10 | 2024-10-03 |  | 4200581313 | 20 | 2024-10-15 | 2024-10-22 |  | 2024-12-16 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | THALES AVS FRANCE SAS | THALES | FG FUNCTION ROYALTY |  | 0 | 0 |  | 7218¦JA2577_1001 | 62 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -493 | 0
1326 | 3166097300006 | LIC SW FG FUNCTION STANDARD FEE | 1800113362 | 20 | 2024-10-03 |  | 4200581313 | 30 | 2024-10-15 | 2024-10-22 |  | 2024-12-16 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | THALES AVS FRANCE SAS | THALES | FG FUNCTION STANDARD FEE |  | 0 | 0 |  | 7218¦JA2577_1001 | 62 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -493 | 0
1327 | 3166097300007 | LIC SW EIS 2 FUNCTION REPLICATION FEE | 1800113363 | 10 | 2024-10-03 |  | 4200581313 | 10 | 2024-10-15 | 2024-10-22 |  | 2024-12-16 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | THALES AVS FRANCE SAS | THALES | EIS 2 FUNCTION REPLICATION FEE |  | 0 | 0 |  | 7218¦JA2576_1001 | 62 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -493 | 0
1328 | 3166097300007 | LIC SW EIS 2 FUNCTION REPLICATION FEE | 1800113363 | 10 | 2024-10-03 |  | 4200580115 | 10 | 2024-10-04 | 2024-10-08 | BORR | 2024-12-16 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 99704.00 |  | THALES AVS FRANCE SAS | THALES | EIS 2 FUNCTION REPLICATION FEE |  | 0 | 0 |  | 7218¦JA2576_1001 | 73 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -493 | 0
1329 | 1000143302050 | RST PELMET 3K3 1% 0,4W 50PPM 0204 ROHS | 1800113419 | 10 | 2024-10-04 |  | 4200580590 | 450 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 100 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | VISHAY | MRS16000C3301FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1330 | 1000243901101 | RST PELMET AXI 3K90 1% 50PPM 3/5W 0207 R | 1800113419 | 20 | 2024-10-04 |  | 4200580523 | 720 | 2024-10-09 | 2024-10-09 |  | 2024-10-27 | 40 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | VISHAY | MRS25000C3901FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1331 | 1000245601001 | RST PELMET AXI 5K6 1% 50PPM 0.6W 0207 RH | 1800113419 | 30 | 2024-10-04 |  | 4200580523 | 730 | 2024-10-09 | 2024-10-09 |  | 2024-10-27 | 100 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | VISHAY | MRS25000C5601FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1332 | 1000251001301 | RST PELMET AXI 10K 1% 50PPM 0.6W 0207 RH | 1800113419 | 40 | 2024-10-04 |  | 4200580590 | 460 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 100 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | VISHAY | MRS25000C1002FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1333 | 1000252701001 | RST PELMET AXI 27K 1% 50PPM 0.6W 0207 RH | 1800113419 | 50 | 2024-10-04 |  | 4200580523 | 710 | 2024-10-09 | 2024-10-09 |  | 2024-10-27 | 100 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | VISHAY | MRS25000C2702FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1334 | 1040512701101 | DIO ZENER 2.4V 50UA 0.5W DO-35-2 ROHS | 1800113419 | 60 | 2024-10-04 |  | 4200580590 | 20 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 120 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | VISHAY | BZX55C2V4-TR |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1335 | 1142013110400 | LED AMBAR 115VAC 8MM IP67 | 1800113419 | 70 | 2024-10-04 |  | 4200584478 | 20 | 2024-11-06 | 2024-11-07 |  | 2024-11-18 | 40 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | APEM | Q8P1CXXY110E |  | 0 | 0 |  | 7218¦JA2583_1001 | 12 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -521 | 0
1336 | 1202090240000 | PIN CNC SUB-D M 20-24AWG (ROLLO 400UD) | 1800113419 | 80 | 2024-10-04 |  | 4200584974 | 60 | 2024-11-11 | 2025-07-31 |  | 2025-02-05 | 50 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | AMPHENOL CORP | 17RRD1M11400 |  | 0 | 0 |  | 7218¦JA2583_1001 | 86 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -442 | 0
1337 | 1229508280002 | CBL EQ UTP RJ45-M/M 10FT NEGRO CAT6 LSZH | 1800113520 | 10 | 2024-10-04 |  | 4200582604 | 30 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6K-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1338 | 1229508280302 | CBL EQ UTP RJ45-M/M 10FT BLANC CAT6 LSZH | 1800113520 | 20 | 2024-10-04 |  | 4200582605 | 30 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 45 | 8 | Liberado | 55 | 55 | 55 | 0 | 55 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6W-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 55 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1339 | 1229508280402 | CBL EQ UTP RJ45-M/M 10FT ROJO CAT6 LSZH | 1800113520 | 30 | 2024-10-04 |  | 4200582605 | 40 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 50 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6R-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1340 | 1229508280502 | CBL EQ UTP RJ45-M/M 10FT AMAR CAT6 LSZH | 1800113520 | 40 | 2024-10-04 |  | 4200582605 | 50 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 50 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6Y-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1341 | 1229508280504 | CBL EQ UTP RJ45-M/M 35FT AMAR CAT6 LSZH | 1800113520 | 50 | 2024-10-04 |  | 4200582604 | 40 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6Y-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1342 | 1229508280505 | CBL EQ UTP RJ45-M/M 50FT AMAR CAT6 LSZH | 1800113520 | 60 | 2024-10-04 |  | 4200582605 | 60 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 65 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6Y-50-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1343 | 1229591601105 | CBL EQ PC CAT6A F/UTP RJ45 LSZH NRJ 0.3M | 1800113520 | 70 | 2024-10-04 |  | 4200584216 | 10 | 2024-11-04 | 2024-11-04 |  | 2024-11-08 | 30 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | LAT-CAT6AF-NJ-0.3 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -531 | 0
1344 | 1229591601106 | CBL EQ PC CAT6A F/UTP RJ45 LSZH NRJ 1.5M | 1800113520 | 80 | 2024-10-04 |  | 4200584216 | 20 | 2024-11-04 | 2024-11-04 |  | 2024-11-08 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | LAT-CAT6AF-NJ-1.5 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -531 | 0
1345 | 1229598280203 | CBL EQ ASSY RJ45-M/M LSZH AZUL-OSC L10FT | 1800113520 | 90 | 2024-10-04 |  | 4200582605 | 70 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6T-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1346 | 3210104723503 | CBL EQ PATCHCORD CAT7 RJ45 LSZH WH L=45M | 1800113520 | 100 | 2024-10-04 |  | 4200580562 | 30 | 2024-10-09 | 2024-10-10 |  | 2024-11-18 | 40 | 8 | Liberado | 22 | 22 | 22 | 0 | 22 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT7F-45 |  | 0 | 0 |  | 7218¦JA2585_1001 | 40 | - |  | YES | 22 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -521 | 0
1347 | 0973525430000.00 | POWER CABINET | 1800113547 | 10 | 2024-10-07 |  | 4200582813 | 10 | 2024-10-24 | 2024-10-28 |  | 2024-11-09 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INGENIERIA Y SISTEMAS DEL CABLE, SL | INDRA SISTEMAS S.A. | 0973525430000.00 |  | 0 | 0 |  | 7218¦JA2582_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -530 | 0
1348 | 1390702000000 | SCREW/PLATES INST LIGHT CTR PEDEST Z210 | 1800113549 | 10 | 2024-10-07 |  | 4200582270 | 10 | 2024-10-22 | 2024-10-23 |  | 2024-11-27 | 98 | 8 | Liberado | 400 | 450 | 450 | 0 | 450 | 0 | X | 0.00 |  | GIZA TECHNOLOGIES, INC | RIVEX NILIC | ASNA2083BG2-10 |  | 0 | 0 |  | 7218¦JA2583_1001 | 36 | - |  | YES | 450 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -512 | 0
1349 | 1500811004002 | TOR AV CRUC M3X4 INOX DIN965 | 1800113549 | 20 | 2024-10-07 |  | 4200585851 | 160 | 2024-11-14 | 2024-11-15 |  | 2024-11-25 | 35 | 8 | Liberado | 400 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN965-M3X4-A4-70-H |  | 0 | 0 |  | 7218¦JA2583_1001 | 11 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -514 | 0
1350 | 1263511210200 | FTE CONM VE=100-240VAC VS=24VDC/2.5A 60W | 1800113561 | 10 | 2024-10-07 |  | 4200580920 | 10 | 2024-10-11 | 2024-10-11 |  | 2024-10-27 | 98 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | FARNELL ELECTR | 118-6529 |  | 0 | 0 |  | 7218¦JA2612_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1351 | 1135032482600 | CONTACTOR MOD ICT 2P/NO 24VAC 25A | 1800113568 | 10 | 2024-10-07 |  | 4200582531 | 120 | 2024-10-23 | 2024-10-24 |  | 2024-10-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | A9C21132 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -539 | 0
1352 | 1135032482700 | CONTACTOR MOD ICT 4P/NO 24VAC 25A | 1800113568 | 20 | 2024-10-07 |  | 4200582531 | 130 | 2024-10-23 | 2024-10-24 |  | 2024-10-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | A9C21134 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -539 | 0
1353 | 1136090086600 | INT MAGNETO AUTO 4P IC60H 16A CURVA-D | 1800113568 | 30 | 2024-10-07 |  | 4200582531 | 140 | 2024-10-23 | 2024-10-24 |  | 2024-10-31 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | A9F85416 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -539 | 0
1354 | 1136234080403 | INT DIFERENCIAL 3P+N 16A CURVA-C ICV40N | 1800113568 | 40 | 2024-10-07 |  | 4200582531 | 150 | 2024-10-23 | 2024-10-24 |  | 2024-10-31 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | A9DF3716 |  | 0 | 0 |  | 7218¦JA2582_1001 | 8 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -539 | 0
1355 | 1000242401000 | RST PELMET 2K4 1% 1/4W 100PPM 0207 ROHS | 1800113569 | 10 | 2024-10-07 |  | 4200580751 | 130 | 2024-10-10 | 2024-10-11 |  | 2024-10-27 | 35 | 0 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TE CONNECTIVITY | LR1 F2K4 |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1356 | 1217000920001 | CNC USB-A 3.0 9H RECEP PANEL IP20 | 1800113569 | 20 | 2024-10-07 |  | 4200582197 | 350 | 2024-10-21 | 2025-01-29 |  | 2024-11-04 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TTI INC. | HARTING | 09 45 452 1904 |  | 1 | 1 |  | 7218¦JA2583_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -535 | 0
1357 | 1229508280202 | CBL EQ UTP RJ45-M/M 10FT VERDE CAT6 LSZH | 1800113570 | 10 | 2024-10-07 |  | 4200582604 | 50 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 55 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6N-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1358 | 1229508280205 | CBL EQ UTP RJ45-M/M 50FT VERDE CAT6 LSZH | 1800113570 | 20 | 2024-10-07 |  | 4200582604 | 60 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 105 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6N-50-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1359 | 1229508280402 | CBL EQ UTP RJ45-M/M 10FT ROJO CAT6 LSZH | 1800113570 | 30 | 2024-10-07 |  | 4200582605 | 80 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 50 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6R-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1360 | 1229508280502 | CBL EQ UTP RJ45-M/M 10FT AMAR CAT6 LSZH | 1800113570 | 40 | 2024-10-07 |  | 4200582605 | 90 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 50 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6Y-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1361 | 1229508280504 | CBL EQ UTP RJ45-M/M 35FT AMAR CAT6 LSZH | 1800113570 | 50 | 2024-10-07 |  | 4200582604 | 70 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6Y-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1362 | 1229508280505 | CBL EQ UTP RJ45-M/M 50FT AMAR CAT6 LSZH | 1800113570 | 60 | 2024-10-07 |  | 4200582605 | 100 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 65 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6Y-50-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1363 | 1229598280203 | CBL EQ ASSY RJ45-M/M LSZH AZUL-OSC L10FT | 1800113570 | 70 | 2024-10-07 |  | 4200582605 | 110 | 2024-10-23 | 2024-10-24 |  | 2024-11-22 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6T-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 30 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -517 | 0
1364 | 3210104723503 | CBL EQ PATCHCORD CAT7 RJ45 LSZH WH L=45M | 1800113570 | 80 | 2024-10-07 |  | 4200580562 | 40 | 2024-10-09 | 2024-10-10 |  | 2024-11-18 | 40 | 8 | Liberado | 25 | 25 | 25 | 0 | 25 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT7F-45 |  | 0 | 0 |  | 7218¦JA2585_1001 | 40 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -521 | 0
1365 | 7883000582700 | ALFOMBRA SEGURIDAD RKP 1890X750MM CBL=2/ | 1800113571 | 10 | 2024-10-07 |  | 4200580607 | 10 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SAFEWORK, S.L. | SAFEWORK | RKP TBC 9/1890X750MM |  | 0 | 0 |  | 7218¦JA2612_1001 | 18 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1366 | 7883000582800 | ALFOMBRA SEGURIDAD RKP 1280X795MM CBL=2/ | 1800113571 | 20 | 2024-10-07 |  | 4200580607 | 20 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 0 | 0 | X | 0.00 |  | SAFEWORK, S.L. | SAFEWORK | RKP TBC 10/1280X795MM |  | 0 | 0 |  | 7218¦JA2612_1001 | 18 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1367 | 7883000582900 | ALFOMBRA SEGURIDAD RKP 2500X725MM CBL=2/ | 1800113571 | 30 | 2024-10-07 |  | 4200580607 | 30 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | SAFEWORK, S.L. | SAFEWORK | RKP TBC 11/2500X725MM |  | 0 | 0 |  | 7218¦JA2612_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1368 | 7883000583000 | ALFOMBRA SEGURIDAD RKP 1100X620MM CBL=5M | 1800113571 | 40 | 2024-10-07 |  | 4200580607 | 40 | 2024-10-09 | 2024-10-11 |  | 2024-10-27 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SAFEWORK, S.L. | SAFEWORK | RKP TBC 12/1100X620MM |  | 0 | 0 |  | 7218¦JA2612_1001 | 18 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1369 | 0917987000100 | LABEL, IDENTIFICATION | 1800113765 | 10 | 2024-10-10 |  | 4200582374 | 10 | 2024-10-22 | 2024-10-25 | BORR | 2025-06-16 | 50 | 8 |  | 7 | 7 | 0 | 7 | 0 | 0 |  | 210.00 |  | MARKABLE SOLUTIONS, S.L. | INDRA SISTEMAS S.A. | 0917987000100 |  | 3 | 1 |  | 7218¦JA2582_1001 | 237 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -311 | 0
1370 | 0917987000100 | LABEL, IDENTIFICATION | 1800113765 | 10 | 2024-10-10 |  | 4200614189 | 10 | 2025-06-04 | 2025-06-05 |  | 2025-06-16 | 50 | 8 | Liberado | 7 | 7 | 7 | 0 | 7 | 0 | X | 0.00 |  | TALLERES LITOMETAL LIMEL,S.L | INDRA SISTEMAS S.A. | 0917987000100 |  | 1 | 1 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 7 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -311 | 0
1371 | 1136032281208 | INT DIFERENCIAL 1PN C 16A 30MA ASI RCBO | 1800113765 | 20 | 2024-10-10 |  | 4200581670 | 20 | 2024-10-17 | 2024-10-21 |  | 2024-10-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | SCHNEIDER ELECTRIC | A9DF3616 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1372 | 0970785470500 | FIXING STEEL STICK | 1800113767 | 10 | 2024-10-10 | BORR | 4200585312 | 10 | 2024-11-12 | 2024-12-10 | BORR | 2024-12-27 | 40 | 8 | Liberado | 2 | 2 | 0 | 2 | 0 | 0 |  | 67.40 |  | PUNZOMET S.L. | INDRA SISTEMAS S.A. | 0970785470500 |  | 0 | 0 |  | 7218¦JA2583_1001 | 45 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -482 | 0
1373 | 0972128051800 | CLS SERVO DRIVES BOX MECH ASSY | 1800113769 | 10 | 2024-10-10 |  | 4200584352 | 20 | 2024-11-05 | 2024-11-06 | BORR | 2025-02-11 | 30 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 460.92 |  | CONSUEGRA SOC. COOP. LTD. | INDRA SISTEMAS S.A. | 0972128051800 |  | 0 | 0 |  | 7218¦JA2589_1001 | 98 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -436 | 0
1374 | 0972128051800 | CLS SERVO DRIVES BOX MECH ASSY | 1800113769 | 10 | 2024-10-10 |  | 4200593634 | 10 | 2025-01-20 | 2025-01-21 |  | 2025-02-07 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0972128051800 |  | 0 | 0 |  | 7218¦JA2589_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -440 | 0
1375 | 1130622471000 | RELE DPDT 12A MINI PLUG-IN 24VDC | 1800113816 | 10 | 2024-10-10 |  | 4200581444 | 20 | 2024-10-16 | 2024-10-17 |  | 2025-06-19 | 80 | 8 | Liberado | 14 | 14 | 14 | 0 | 14 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | FINDER | 56.32.9.024.0040 |  | 2 | 0 |  | 7218¦JA2582_1001 | 246 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -308 | 0
1376 | 1139990091100 | ZOCALO RELE CARRIL DIN P/RELE 4PCO | 1800113816 | 20 | 2024-10-10 |  | 4200581444 | 30 | 2024-10-16 | 2024-10-17 |  | 2025-06-19 | 30 | 8 | Liberado | 14 | 14 | 14 | 0 | 14 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | FINDER | 96.72 |  | 2 | 0 |  | 7218¦JA2582_1001 | 246 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -308 | 0
1377 | 1246003150000 | VENTILADOR CENTRIF 230VAC 115W 140X237MM | 1800113816 | 30 | 2024-10-10 |  | 4200581883 | 80 | 2024-10-18 | 2024-10-21 |  | 2024-12-13 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | EBM | G2E140-NS38-01 |  | 1 | 1 |  | 7218¦JA2582_1001 | 56 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -496 | 0
1378 | 1399901561000 | GENERADOR DE HUMO MOD. ETNA | 1800113816 | 40 | 2024-10-10 |  | 4200585668 | 10 | 2024-11-14 | 2024-12-17 |  | 2024-12-30 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | ITURRI, S.A. | Haagen S.L. | 017500 |  | 2 | 2 |  | 7218¦JA2582_1001 | 46 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -479 | 0
1379 | 1399901561100 | SET TUBO CONDUCTOR DE HUMO DE 5 MT | 1800113816 | 50 | 2024-10-10 |  | 4200585668 | 20 | 2024-11-14 | 2024-12-17 |  | 2024-12-30 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | ITURRI, S.A. | Haagen S.L. | 017800 |  | 2 | 2 |  | 7218¦JA2582_1001 | 46 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -479 | 0
1380 | 1807990300100 | HUMO LIQUIDO LION 20L | 1800113816 | 60 | 2024-10-10 |  | 4200593898 | 10 | 2025-01-21 | 2025-01-24 |  | 2025-03-18 | 55 | 8 | Liberado | 1 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | ITURRI, S.A. | LION PROTECTS B.V. | 010850 |  | 0 | 0 |  | 7218¦JA2582_1001 | 56 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -401 | 0
1381 | 1229593780102 | CBL EQ USB2.0 A-M/B-M 480MBPS NEGRO L=1M | 1800113817 | 10 | 2024-10-10 |  | 4200583931 | 10 | 2024-10-31 | 2024-11-04 |  | 2024-11-11 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | LANBERG | CA-USBA-15CU-0010-BK |  | 0 | 0 |  | 7218¦JA2586_1001 | 11 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -528 | 0
1382 | 1204200330020 | CNC CIR 9-98 3M PLUG CRIMP | 1800113826 | 10 | 2024-10-10 |  | 4200582242 | 140 | 2024-10-22 | 2024-10-23 |  | 2024-11-25 | 30 | 8 | Liberado | 2 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | AMALFI TRADING, INC | AMPHENOL CORP | D38999/26ZA98PN |  | 1 | 1 |  | 7218¦JA2582_1001 | 34 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -514 | 0
1383 | 1209994000023 | ACC CNC CIR BACKSHELL 15 ALU ROHS | 1800113826 | 20 | 2024-10-10 |  | 4200581036 | 60 | 2024-10-14 | 2024-10-21 |  | 2024-12-02 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | MILITARY SPECS. | M85049/38-15N |  | 1 | 0 |  | 7218¦JA2582_1001 | 49 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -507 | 0
1384 | 1209994130022 | STRAIN RELIEF #13 AL/NI M85049/38-13N | 1800113826 | 30 | 2024-10-10 |  | 4200581959 | 20 | 2024-10-18 | 2024-10-18 |  | 2024-11-08 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | SAE INC. | AS85049/38-13N |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -531 | 0
1385 | 1214200530720 | CNC CIR 15-5 5H PLUG RECT ZN/NI ROT-N | 1800113826 | 40 | 2024-10-10 |  | 4200581878 | 180 | 2024-10-18 | 2024-10-23 |  | 2024-11-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZD5SN |  | 1 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -524 | 0
1386 | 1238514152005 | TERM PREAIS PUNTERA S=1,5MM2 L=12MM NEGR | 1800113826 | 50 | 2024-10-10 |  | 4200581503 | 20 | 2024-10-16 | 2024-10-18 |  | 2024-10-27 | 110 | 8 | Liberado | 100 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CEMBRE | PKD-1512 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -543 | 0
1387 | 0973580310100 | CARRIL DIN | 1800113827 | 10 | 2024-10-10 |  | 4200585312 | 20 | 2024-11-12 | 2024-12-10 |  | 2025-07-28 | 0 | 8 | Liberado | 2 | 2 | 6 | 0 | 2 | 4 | X | 0.00 |  | PUNZOMET S.L. | INDRA SISTEMAS S.A. | 0973580310100 |  | 2 | 1 |  | 7218¦JA2583_1001 | 258 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -269 | 0
1388 | 0973581310100 | CARRIL DIN | 1800113827 | 20 | 2024-10-10 |  | 4200585312 | 30 | 2024-11-12 | 2024-12-10 |  | 2024-12-27 | 0 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | PUNZOMET S.L. | INDRA SISTEMAS S.A. | 0973581310100 |  | 0 | 0 |  | 7218¦JA2583_1001 | 45 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -482 | 0
1389 | 1002548203009 | RST PELCAR 8K205% 1/4W 0207 | 1800113827 | 30 | 2024-10-10 |  | 4200581080 | 100 | 2024-10-14 | 2024-10-16 |  | 2024-10-30 | 30 | 8 | Liberado | 40 | 40 | 40 | 0 | 40 | 0 | X | 0.00 |  | TCX MICRO, S.L.U |  |  |  | 0 | 0 |  | 7218¦JA2583_1001 | 16 | - |  | YES | 40 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -540 | 0
1390 | 1390700725500 | GEAR BOX A320 | 1800113827 | 40 | 2024-10-10 |  | 4600004155 | 10 | 2024-11-14 | 2024-11-14 | BORR | 2024-11-26 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 1470.00 |  | TOULOUSE AIR SPARES | AIRBUS INDUSTRIE | D3231007000100 |  | 0 | 0 |  | 7218¦JA2583_1001 | 12 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -513 | 0
1391 | 1390700725500 | GEAR BOX A320 | 1800113827 | 40 | 2024-10-10 |  | 4600004293 | 10 | 2025-01-20 | 2025-01-21 |  | 2025-01-29 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 1470.00 |  | TOULOUSE AIR SPARES | AIRBUS INDUSTRIE | D3231007000100 |  | 0 | 0 |  | 7218¦JA2583_1001 | 9 | - | [5 empty] | 1 |  | 0% | 4600004293 |  |  |  | 10 | 100% |  | -449 | 0
1392 | 1580160090000 | SEPARADOR HEXAG M3 M/H L=5MM LATON NI | 1800113828 | 10 | 2024-10-10 |  | 4200587937 | 50 | 2024-11-29 | 2025-03-06 |  | 2025-01-13 | 30 | 8 | Liberado | 400 | 400 | 400 | 0 | 400 | 0 | X | 0.00 |  | AMIDATA, S.A. | RS | 606-670 |  | 1 | 1 |  | 7218¦JA2584_1001 | 45 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -465 | 0
1393 | 3050501221300 | MEMORY RAM SODIMM 16GB 3200MHZ 1.2V DDR4 | 1800113829 | 10 | 2024-10-10 |  | 4200581704 | 10 | 2024-10-17 | 2024-10-18 |  | 2024-10-30 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | COMPUTER TRADING S. L. | CRUCIAL | CT16G4SFD832A |  | 0 | 0 |  | 7218¦JA2585_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -540 | 0
1394 | 3060303930200 | DISK SSD 250GB M.2 NVME PCIE G4X4 3D TLC | 1800113829 | 20 | 2024-10-10 |  | 4200581716 | 10 | 2024-10-17 | 2024-10-18 |  | 2024-10-30 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. | KINGSTON | SNV2S/250G |  | 0 | 0 |  | 7218¦JA2585_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -540 | 0
1395 | 0972881240300 | IOS CNC BOX PLATE 1 | 1800113830 | 10 | 2024-10-10 |  | 4200585312 | 40 | 2024-11-12 | 2024-12-10 |  | 2024-12-27 | 90 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | PUNZOMET S.L. | INDRA SISTEMAS S.A. | 0972881240300 |  | 0 | 0 |  | 7218¦JA2588_1001 | 45 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -482 | 0
1396 | 0972882240300 | IOS CNC BOX PLATE 2 | 1800113830 | 20 | 2024-10-10 |  | 4200585312 | 50 | 2024-11-12 | 2024-12-10 |  | 2025-09-22 | 90 | 8 | Liberado | 1 | 1 | 4 | 0 | 1 | 3 | X | 0.00 |  | PUNZOMET S.L. | INDRA SISTEMAS S.A. | 0972882240300 |  | 4 | 2 |  | 7218¦JA2588_1001 | 314 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -213 | 0
1397 | 1016072008902 | CON POLPNO 2U0 440V 10% D30X56MM ROHS | 1800114061 | 10 | 2024-10-15 |  | 4200581637 | 330 | 2024-10-17 | 2025-01-17 |  | 2024-11-10 | 40 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | LCR COMPONENTS | MR/P/440/2/B |  | 0 | 0 |  | 7218¦JA2582_1001 | 24 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1398 | 1135234080300 | KIT DISYUNTOR 20-80KW 400V VRLA GALAXYVS | 1800114061 | 20 | 2024-10-15 |  | 4200582531 | 80 | 2024-10-23 | 2024-10-24 |  | 2024-11-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | GVSBBK20K80H |  | 0 | 0 |  | 7218¦JA2582_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1399 | 1204200530620 | CNC CIR 15-5 5M PLUG RECT CRMP NI-ZN R-N | 1800114061 | 30 | 2024-10-15 |  | 4200582737 | 30 | 2024-10-24 | 2024-10-29 |  | 2024-11-10 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/26ZD5PN |  | 0 | 0 |  | 7218¦JA2582_1001 | 17 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1400 | 1209994090221 | ACC BACKSHELL #9 RECTO AL ELEC-NI | 1800114061 | 40 | 2024-10-15 |  | 4200582738 | 70 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M85049/38-9N |  | 0 | 0 |  | 7218¦JA2582_1001 | 17 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1401 | 1209994190024 | ABRAZADERA CNC CIR #19 RECT AL/EL-NI | 1800114061 | 50 | 2024-10-15 |  | 4200582738 | 80 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 45 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M85049/38-19N |  | 0 | 0 |  | 7218¦JA2582_1001 | 17 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1402 | 1209994240424 | ACC BACKSHELL 21 ALU MIL-DTL-38999III IV | 1800114061 | 60 | 2024-10-15 |  | 4200582738 | 90 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M85049/38-21N |  | 0 | 0 |  | 7218¦JA2582_1001 | 17 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1403 | 1214300330020 | CNC CIR 9-98S/3H RECEPT RECT CRIMP ZN/NI | 1800114061 | 70 | 2024-10-15 |  | 4200582738 | 100 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | D38999/20ZA98SN |  | 0 | 0 |  | 7218¦JA2582_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1404 | 1264011783100 | SAI 80KW 3F 400V PUESTA-5X8 GALAXY-VS | 1800114061 | 80 | 2024-10-15 |  | 4200582962 | 10 | 2024-10-25 | 2024-10-29 |  | 2024-12-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | GVSUPS80KHS |  | 1 | 1 |  | 7218¦JA2582_1001 | 46 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -499 | 0
1405 | 1264011789300 | SERVICIO 1YR EAA UPG 3P P/SAI 41-150KVA | 1800114061 | 90 | 2024-10-15 |  | 4200582962 | 20 | 2024-10-25 | 2024-10-29 |  | 2024-12-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | WUPGEAA-UG-02 |  | 1 | 1 |  | 7218¦JA2582_1001 | 46 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -499 | 0
1406 | 1264011789400 | SERVICIO INSTAL CONJ BATERIA VRLA 1X48 | 1800114061 | 100 | 2024-10-15 |  | 4200582962 | 30 | 2024-10-25 | 2024-10-29 |  | 2024-12-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | QBATT-01 |  | 1 | 1 |  | 7218¦JA2582_1001 | 46 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -499 | 0
1407 | 1351303410000 | T. RED GEST LCES2 C/MODBUS/ETH/SENS-AUX | 1800114061 | 110 | 2024-10-15 |  | 4200582962 | 40 | 2024-10-25 | 2024-10-29 |  | 2024-12-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | AP9644 |  | 1 | 1 |  | 7218¦JA2582_1001 | 46 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -499 | 0
1408 | 1700103180000 | ARMARIO BATERIA VACIO VRLA 197X110X85CM | 1800114061 | 120 | 2024-10-15 |  | 4200582261 | 10 | 2024-10-22 | 2024-10-22 |  | 2024-11-19 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | SCHNEIDER ELECTRIC | GVEBC11 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -520 | 0
1409 | 1751100080100 | BASE DE 8 ENCHUFES INTERRUPTOR RACK 19" | 1800114062 | 10 | 2024-10-15 |  | 4200585889 | 150 | 2024-11-15 | 2024-11-20 |  | 2024-11-25 | 60 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | SCHROFF | 60110-206 |  | 0 | 0 |  | 7218¦JA2585_1001 | 10 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -514 | 0
1410 | 3120301930000 | PANEL CONEX ACOP CAT6A 1U 24P P/RACK 19" | 1800114062 | 20 | 2024-10-15 |  | 4200581720 | 10 | 2024-10-17 | 2024-10-18 |  | 2024-11-13 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | KASILH TELECOM, SL | FS.COM | C6AP-S24FT1U |  | 1 | 1 |  | 7218¦JA2585_1001 | 27 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -526 | 0
1411 | 3170405860300 | TRANSCEPTOR SFP+ 10GBASE-T RJ45 PROSAFE | 1800114062 | 30 | 2024-10-15 |  | 4200581949 | 10 | 2024-10-18 | 2024-10-18 |  | 2024-11-08 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | NETGEAR | AXM765 |  | 0 | 0 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -531 | 0
1412 | 1229500180300 | CBL EQ DIV ALIM C14/2XC13 18AWG 18" NEG | 1800114063 | 10 | 2024-10-15 |  | 4200594459 | 10 | 2025-01-24 | 2025-01-24 |  | 2025-02-28 | 40 | 8 | Liberado | 16 | 16 | 16 | 0 | 16 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | TRIPP-LITE | P004-18N-2C13 |  | 0 | 0 |  | 7218¦JA2585_1001 | 35 | - |  | YES | 16 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -419 | 0
1413 | 3210506330100 | ADAPT DP-MINI-M/HDMI-A-H 2K BLANCO L0.1M | 1800114063 | 30 | 2024-10-15 |  | 4200582095 | 10 | 2024-10-21 | 2024-10-21 |  | 2024-10-30 | 40 | 8 | Liberado | 11 | 11 | 11 | 0 | 11 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | ROLINE | 12.03.3129 |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 11 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -540 | 0
1414 | 1351708680400 | MOD POSEIDON 3468 48VDC 4XDI 2XDO 230V 1 | 1800114067 | 10 | 2024-10-15 |  | 4200584313 | 10 | 2024-11-05 | 2024-11-05 |  | 2024-11-11 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | 600570 |  | 0 | 0 |  | 7218¦JA2585_1001 | 6 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -528 | 0
1415 | 3120500540100 | PDU MANAGED 24XC13/6XC19 32A 22KW RACK | 1800114067 | 20 | 2024-10-15 |  | 4200582045 | 10 | 2024-10-21 | 2024-10-21 |  | 2024-11-08 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | RITTAL, S.A | RITTAL | DK 7979.437 |  | 0 | 0 |  | 7218¦JA2585_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -531 | 0
1416 | 1209994130022 | STRAIN RELIEF #13 AL/NI M85049/38-13N | 1800114171 | 10 | 2024-10-16 |  | 4200584417 | 20 | 2024-11-05 | 2024-11-06 |  | 2024-11-10 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | SAE INC. | AS85049/38-13N |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1417 | 1231024609900 | TUBO TERMO 1/4 2:1 L=1.219M PVDF CLARO R | 1800114171 | 20 | 2024-10-16 |  | 4200586375 | 1510 | 2024-11-19 | 2025-05-28 | BORR | 2024-11-10 | 60 | 8 | Liberado | 2 | 2 | 0 | 2 | 0 | 0 |  | 19.88 |  | TTI INC. | TE CONNECTIVITY | RW-175-1/4-X-STK |  | 0 | 0 |  | 7218¦JA2582_1001 | -9 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -529 | 0
1418 | 1231024609900 | TUBO TERMO 1/4 2:1 L=1.219M PVDF CLARO R | 1800114171 | 20 | 2024-10-16 |  | 4200587268 | 280 | 2024-11-25 | 2025-03-20 |  | 2025-03-10 | 60 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | TE CONNECTIVITY | RW-175-1/4-X-STK |  | 1 | 0 |  | 7218¦JA2582_1001 | 105 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -409 | 0
1419 | 1231025129901 | TUBO TERMO 1/2 2:1 L=1.219M PVDF CLARO R | 1800114171 | 30 | 2024-10-16 |  | 4200586375 | 1500 | 2024-11-19 | 2025-05-28 | BORR | 2024-11-10 | 60 | 8 | Liberado | 2 | 2 | 0 | 2 | 0 | 0 |  | 26.76 |  | TTI INC. | TE CONNECTIVITY | RW-175-1/2-X-STK |  | 0 | 0 |  | 7218¦JA2582_1001 | -9 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -529 | 0
1420 | 1231025129901 | TUBO TERMO 1/2 2:1 L=1.219M PVDF CLARO R | 1800114171 | 30 | 2024-10-16 |  | 4200601136 | 10 | 2025-03-06 | 2025-03-07 |  | 2025-03-27 | 60 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | TE CONNECTIVITY | RW-175-1/2-X-STK |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -392 | 0
1421 | 1231025193820 | TUBO TERMO 3/4" 2:1 FLUOPOLYMR CLEAR RHS | 1800114171 | 40 | 2024-10-16 |  | 4200583884 | 10 | 2024-10-31 | 2024-11-04 |  | 2025-03-24 | 30 | 8 | Liberado | 2 | 12.5 | 12.5 | 0 | 12.5 | 0 | X | 0.00 |  | TTI INC. | RAYCHEM LTD | RW-175-3/4-X |  | 1 | 0 |  | 7218¦JA2582_1001 | 144 | - |  | YES | 12.5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -395 | 0
1422 | 1235025400802 | CANALETA 40X40MM PVC GRIS RAL7035 U43X | 1800114171 | 50 | 2024-10-16 |  | 4200591307 | 10 | 2024-12-20 | 2025-02-18 |  | 2025-01-16 | 30 | 8 | Liberado | 18 | 18 | 18 | 0 | 18 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | UNEX | 40.40.88 |  | 0 | 0 |  | 7218¦JA2582_1001 | 27 | - |  | YES | 18 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -462 | 0
1423 | 1238510040000 | PUNTERA PREAISLA 4MM2 NARANJA | 1800114171 | 60 | 2024-10-16 |  | 4200591047 | 10 | 2024-12-19 | 2024-12-26 |  | 2025-01-22 | 110 | 8 | Liberado | 50 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SONEPAR SPAIN S.A.U. | BIZLINE | BIZ 000 925 |  | 0 | 0 |  | 7218¦JA2582_1001 | 34 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -456 | 0
1424 | 1002531203209 | RST PELCAR 120R 5% -500,350PPM 1/4W ROHS | 1800114173 | 10 | 2024-10-16 |  | 4200581768 | 160 | 2024-10-17 | 2024-10-23 |  | 2024-11-11 | 30 | 8 | Liberado | 18 | 18 | 18 | 0 | 18 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | YAGEO | CFR-25JR-52-120R |  | 1 | 1 |  | 7218¦JA2583_1001 | 25 | - |  | YES | 18 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -528 | 0
1425 | 1002551003509 | RST PELCAR AXI 10K0 5% 350PPM 1/4W ROHS | 1800114173 | 20 | 2024-10-16 |  | 4200581752 | 320 | 2024-10-17 | 2024-10-22 |  | 2024-11-11 | 30 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | RS PRO | 707-7745 |  | 1 | 1 |  | 7218¦JA2583_1001 | 25 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -528 | 0
1426 | 1124510125000 | SWITCH MAGNETICO SPDT 28VDC 200MA C/FUS | 1800114173 | 30 | 2024-10-16 |  | 4200591389 | 20 | 2024-12-20 | 2025-06-13 |  | 2025-02-14 | 55 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2B2 |  | 0 | 0 |  | 7218¦JA2583_1001 | 56 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -433 | 0
1427 | 1124510125400 | SWITCH MAGNETICO SPDT 28VDC 7.5A 200MA C | 1800114173 | 40 | 2024-10-16 |  | 4200591389 | 30 | 2024-12-20 | 2025-06-13 |  | 2025-02-14 | 39 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-7.5A |  | 0 | 0 |  | 7218¦JA2583_1001 | 56 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -433 | 0
1428 | 1124510126100 | SWITCH MAGNETICO SPDT 28VDC 3A 200MA C/D | 1800114173 | 50 | 2024-10-16 |  | 4200591389 | 40 | 2024-12-20 | 2025-06-13 |  | 2025-02-14 | 39 | 8 | Liberado | 5 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | 9510-G111-P1F1-Z0R2A2-3A |  | 0 | 0 |  | 7218¦JA2583_1001 | 56 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -433 | 0
1429 | 1128990400300 | INSERTO MARCAJE NEGRO 20A PULS CONFI A/B | 1800114173 | 60 | 2024-10-16 |  | 4200591389 | 50 | 2024-12-20 | 2025-06-13 |  | 2025-02-14 | 50 | 8 | Liberado | 2 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 13 |  | 0 | 0 |  | 7218¦JA2583_1001 | 56 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -433 | 0
1430 | 1128990400800 | INSERTO MARCAJE NEGRO 3A PULS CONFIG A/B | 1800114173 | 70 | 2024-10-16 |  | 4200591389 | 60 | 2024-12-20 | 2025-06-13 |  | 2025-02-14 | 60 | 8 | Liberado | 8 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 07 |  | 0 | 0 |  | 7218¦JA2583_1001 | 56 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -433 | 0
1431 | 1128990400900 | INSERTO MARCAJE NEGRO 5A PULS CONFIG A/B | 1800114173 | 80 | 2024-10-16 |  | 4200591389 | 70 | 2024-12-20 | 2025-06-13 |  | 2025-02-14 | 60 | 8 | Liberado | 8 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | E-T-A APARELLAJE ELECTRICO S.L.U. | E.T.A. | X 222 175 08 |  | 0 | 0 |  | 7218¦JA2583_1001 | 56 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -433 | 0
1432 | 1204206631120 | CNC CIR 19-35 66M STRAIGHT PLUG D38999 | 1800114173 | 90 | 2024-10-16 |  | 4200582738 | 130 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 55 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | D38999/26ZF35PN |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1433 | 1209990020620 | CONTACTO MACHO SIZE 20 M39029/58-363 | 1800114173 | 100 | 2024-10-16 |  | 4200582738 | 140 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 30 | 8 | Liberado | 600 | 600 | 600 | 0 | 600 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M39029/58-363 |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 600 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1434 | 1212090200020 | PIN H CRIMP CNC SUB-D #20 AWG20-24(0,2-0 | 1800114173 | 110 | 2024-10-16 |  | 4200582738 | 150 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 50 | 8 | Liberado | 100 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M39029/63-368 |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1435 | 1214090010420 | CONTACTO HEMBRA M39029/5-115 | 1800114173 | 120 | 2024-10-16 |  | 4200582738 | 160 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 85 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M39029/5-115 |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1436 | 1214101933621 | CNC CIR 14-19 (19H) MS3470L14-19S | 1800114173 | 130 | 2024-10-16 |  | 4200583866 | 40 | 2024-10-31 | 2024-11-04 |  | 2024-11-10 | 35 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3470L14-19S |  | 0 | 0 |  | 7218¦JA2583_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1437 | 1214306631920 | CNC CIR 19-35 66H RECPT CRMP ZN/NI ROT-N | 1800114173 | 140 | 2024-10-16 |  | 4200582738 | 170 | 2024-10-24 | 2024-11-19 |  | 2024-11-10 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | D38999/20ZF35SN |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1438 | 1219000292300 | CAJA PORTACONTACTOS 10P (H) PASO 3,96MM | 1800114173 | 150 | 2024-10-16 |  | 4200582519 | 10 | 2024-10-23 | 2024-10-24 |  | 2024-11-10 | 80 | 8 | Liberado | 6 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | CENVALSA, S.L. | CONEXCON | 3940-2101 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1439 | 1219001090100 | CAJA PORTACONTACTOS 10/H CRIMP SERIE SL | 1800114173 | 160 | 2024-10-16 |  | 4200583298 | 110 | 2024-10-28 | 2025-01-03 |  | 2024-11-10 | 80 | 8 | Liberado | 13 | 13 | 13 | 0 | 13 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | MOLEX | 50-57-9410 |  | 0 | 0 |  | 7218¦JA2583_1001 | 13 | - |  | YES | 13 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1440 | 1229590140400 | CBL EQ CAT6A LSZH RJ45-M/RJ45-M L=0.5M | 1800114173 | 170 | 2024-10-16 |  | 4200582629 | 30 | 2024-10-24 | 2024-10-28 |  | 2024-11-10 | 105 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | GITEC CONTROL, S.L. | OMRON CORPORATION | XS6W-6LSZH8SS50CM-Y |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1441 | 1230524620000 | FUND CBL 1/4" CBL 1/8-1/2" FR POLIES NEG | 1800114173 | 180 | 2024-10-16 |  | 4200582420 | 40 | 2024-10-22 | 2024-10-28 |  | 2024-12-30 | 50 | 8 | Liberado | 700 | 700 | 700 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | WESTERN FILAMENT, INC | FR0250BK |  | 0 | 0 |  | 7218¦JA2583_1001 | 69 | - |  | YES | 700 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -479 | 0
1442 | 1239990800000 | RAIL P/BORNEROS MODULARES 1M NSA937901 | 1800114173 | 190 | 2024-10-16 |  | 4200591058 | 10 | 2024-12-19 | 2025-01-08 |  | 2025-01-16 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | A2C AIR COST CONTROL | EADS NORMALISATION S | NSA937901RA1000 |  | 0 | 0 |  | 7218¦JA2583_1001 | 28 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -462 | 0
1443 | 0970785470800 | CARD SUPPORT 130VU | 1800114174 | 10 | 2024-10-16 |  | 4200582805 | 10 | 2024-10-24 | 2024-10-28 |  | 2025-01-24 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0970785470800 |  | 0 | 0 |  | 7218¦JA2583_1001 | 92 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -454 | 0
1444 | 1128912180000 | CABEZA SELECTOR 2POS 90° D22MM NEGRA XB5 | 1800114174 | 20 | 2024-10-16 |  | 4200582531 | 90 | 2024-10-23 | 2024-10-24 |  | 2024-11-10 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | LUJISA, S.A. | SCHNEIDER ELECTRIC | ZB5AD2 |  | 0 | 0 |  | 7218¦JA2583_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1445 | 1212090240000 | PIN CNC SUB-D H 20-24AWG (ROLLO 400UD | 1800114174 | 30 | 2024-10-16 |  | 4200583117 | 130 | 2024-10-28 | 2024-11-15 |  | 2024-11-10 | 30 | 8 | Liberado | 26 | 26 | 26 | 0 | 26 | 0 | X | 0.00 |  | TTI INC. | AMPHENOL CORP | 17RRD1F11400 |  | 0 | 0 |  | 7218¦JA2583_1001 | 13 | - |  | YES | 26 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1446 | 1214001933721 | CNC CIR AER 14-19 (19H) MS3476L14-19S | 1800114174 | 40 | 2024-10-16 |  | 4200583866 | 50 | 2024-10-31 | 2024-11-04 |  | 2024-12-05 | 35 | 8 | Liberado | 14 | 14 | 14 | 0 | 14 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L14-19S |  | 0 | 0 |  | 7218¦JA2583_1001 | 35 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -504 | 0
1447 | 1214001933722 | CNC CIR 14-19 (19H) MS3476L14-19SW | 1800114174 | 50 | 2024-10-16 |  | 4200583858 | 180 | 2024-10-31 | 2024-11-04 |  | 2025-06-30 | 56 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L14-19SW |  | 1 | 0 |  | 7218¦JA2583_1001 | 242 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -297 | 0
1448 | 1214002633727 | CNC CIR 16-26 26P/H PLUG MS3476L16-26S | 1800114174 | 60 | 2024-10-16 |  | 4200583866 | 60 | 2024-10-31 | 2024-11-04 |  | 2024-11-28 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L16-26S |  | 0 | 0 |  | 7218¦JA2583_1001 | 28 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -511 | 0
1449 | 1214002633742 | CNC CIR 16-26 (26H) MS3476L16-26SY | 1800114174 | 70 | 2024-10-16 |  | 4200583866 | 70 | 2024-10-31 | 2024-11-04 |  | 2024-11-28 | 56 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L16-26SY |  | 0 | 0 |  | 7218¦JA2583_1001 | 28 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -511 | 0
1450 | 1214003233721 | CNC CIR 18-32 32S (H) MS3476L18-32SN | 1800114174 | 80 | 2024-10-16 |  | 4200583858 | 190 | 2024-10-31 | 2024-11-04 |  | 2024-11-24 | 125 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L18-32SN |  | 0 | 0 |  | 7218¦JA2583_1001 | 24 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -515 | 0
1451 | 1214003233761 | CNC CIR 18-32 (32H) MS3476L18-32SW | 1800114174 | 90 | 2024-10-16 |  | 4200583866 | 80 | 2024-10-31 | 2024-11-04 |  | 2024-11-28 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L18-32SW |  | 0 | 0 |  | 7218¦JA2583_1001 | 28 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -511 | 0
1452 | 1214004133721 | CNC CIR 20-41 (41H) MS3476L20-41S | 1800114174 | 100 | 2024-10-16 |  | 4200583858 | 200 | 2024-10-31 | 2024-11-04 |  | 2024-11-24 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY STANDARDS | MS3476L20-41S |  | 0 | 0 |  | 7218¦JA2583_1001 | 24 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -515 | 0
1453 | 1214005533721 | CNC CIR 22-55 (55H) MS3476L22-55S | 1800114174 | 110 | 2024-10-16 |  | 4200583866 | 90 | 2024-10-31 | 2024-11-04 |  | 2024-11-10 | 56 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | TTI, INC. | MILITARY STANDARDS | MS3476L22-55S |  | 0 | 0 |  | 7218¦JA2583_1001 | 10 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1454 | 1219990340200 | ACC PIN H AWG22-24 CRIMP ORO/NIQU | 1800114174 | 120 | 2024-10-16 |  | 4200583292 | 90 | 2024-10-28 | 2024-10-29 |  | 2024-11-10 | 60 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | MOLEX | 16-02-0088 |  | 0 | 0 |  | 7218¦JA2583_1001 | 13 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1455 | 1232024245400 | MANG IDENTIF TERMO 3/32" 3:1 POLIOLE AMA | 1800114174 | 130 | 2024-10-16 |  | 4200583052 | 10 | 2024-10-25 | 2025-02-08 |  | 2024-11-06 | 45 | 8 | Liberado | 300 | 300 | 300 | 0 | 300 | 0 | X | 0.00 |  | TTI INC. | TE CONNECTIVITY | TMS-SCE-3/32-2.0-4 |  | 0 | 0 |  | 7218¦JA2583_1001 | 12 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -533 | 0
1456 | 1263516109001 | MOD SALIDA F.A. 6-15VDC 20A 240W XGEN | 1800114174 | 140 | 2024-10-16 |  | 4200582279 | 10 | 2024-10-22 | 2024-10-22 |  | 2024-11-10 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | EXCELSYS TECHNOLOGIES | XG3 |  | 0 | 0 |  | 7218¦JA2583_1001 | 19 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1457 | 1530116000003 | TUERCA EX. M6 DIN-934 A4-80 | 1800114174 | 150 | 2024-10-16 |  | 4200584526 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-13 | 90 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | EUROPEAN AGENCY MENK | DIN | DIN934-M6-A4-80 |  | 0 | 0 |  | 7218¦JA2583_1001 | 7 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -526 | 0
1458 | 1530120000001 | TUERCA EX M12 INOX A2 DIN934 | 1800114174 | 160 | 2024-10-16 |  | 4200584596 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-13 | 60 | 8 | Liberado | 4 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | DIN | DIN934-M12-A2-70 |  | 0 | 0 |  | 7218¦JA2583_1001 | 7 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -526 | 0
1459 | 1586690870000 | ABRAZADERA TUBO 50MM HEX-RANURADO INOX | 1800114174 | 170 | 2024-10-16 |  | 4200584535 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-18 | 40 | 8 | Liberado | 4 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | JCS HI-TORQUE | HTJ50P |  | 0 | 0 |  | 7218¦JA2583_1001 | 12 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -521 | 0
1460 | 1706500052500 | BANDEJA EST VENT 1U 7" AC NEG P/RACK 19" | 1800114174 | 180 | 2024-10-16 |  | 4200584810 | 10 | 2024-11-08 | 2024-11-11 |  | 2024-11-13 | 40 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | STARTECH.COM LTD | CABSHELF1U7V |  | 0 | 0 |  | 7218¦JA2583_1001 | 5 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -526 | 0
1461 | 1706500052600 | BANDEJA AJUST 1U 16-24" AC NEG P/RACK19" | 1800114174 | 190 | 2024-10-16 |  | 4200584810 | 20 | 2024-11-08 | 2024-11-11 |  | 2024-12-04 | 40 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | APC | AR8125 |  | 0 | 0 |  | 7218¦JA2583_1001 | 26 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -505 | 0
1462 | 1229590800100 | CB EQUIPADO ALIMENT M/H L=2MTRS /CNC IEC | 1800114176 | 10 | 2024-10-16 |  | 4200582317 | 60 | 2024-10-22 | 2024-10-23 |  | 2024-11-10 | 45 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 487-277 |  | 0 | 0 |  | 7218¦JA2585_1001 | 19 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1463 | 1231025193820 | TUBO TERMO 3/4" 2:1 FLUOPOLYMR CLEAR RHS | 1800114176 | 20 | 2024-10-16 |  | 4200583884 | 20 | 2024-10-31 | 2024-11-04 |  | 2025-03-24 | 30 | 8 | Liberado | 1 | 12.5 | 12.5 | 0 | 12.5 | 0 | X | 0.00 |  | TTI INC. | RAYCHEM LTD | RW-175-3/4-X |  | 1 | 0 |  | 7218¦JA2585_1001 | 144 | - |  | YES | 12.5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -395 | 0
1464 | 1587080790400 | ETIQUETA ADH 35X18MM PE BL BMP71 | 1800114176 | 30 | 2024-10-16 |  | 4200582294 | 80 | 2024-10-22 | 2024-11-18 |  | 2024-11-10 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | BRADY | M71EP-7-7593-SL |  | 0 | 0 |  | 7218¦JA2585_1001 | 19 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1465 | 1589906820000 | CHA IOT CARRIL DIN PERFORAD 955X35X7.5MM | 1800114176 | 40 | 2024-10-16 |  | 4200584536 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-10 | 60 | 8 | Liberado | 1 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | PHOENIX CONTACT S.A. | PHOENIX CONTACT | 1207653 |  | 0 | 0 |  | 7218¦JA2585_1001 | 4 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1466 | 1589990519000 | TOPE FINAL BAM4 CARR DIN POLIAM GRIS OSC | 1800114176 | 50 | 2024-10-16 |  | 4200584553 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-11 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | LUJISA, S.A. | TE CONNECTIVITY | 1SNK900001R0000 |  | 0 | 0 |  | 7218¦JA2585_1001 | 5 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -528 | 0
1467 | 1709904470000 | ACCESORIO MONTAJE NETSHELTER SX | 1800114176 | 60 | 2024-10-16 |  | 4200582687 | 10 | 2024-10-24 | 2024-10-24 |  | 2024-11-21 | 50 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. | APC | AR7711 |  | 0 | 0 |  | 7218¦JA2585_1001 | 28 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -518 | 0
1468 | 3120100170400 | KITT ACC MECANICA TUERCA/ARANDELA/TORNIL | 1800114176 | 70 | 2024-10-16 |  | 4200584581 | 10 | 2024-11-06 | 2024-11-21 |  | 2024-11-20 | 40 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | APC | AR8100 |  | 0 | 0 |  | 7218¦JA2585_1001 | 14 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -519 | 0
1469 | 3170110330500 | HUB 4P USB3.0 3XUSB-A 1XUSB-C 5GBPS NEGR | 1800114176 | 80 | 2024-10-16 |  | 4200582088 | 10 | 2024-10-21 | 2024-10-21 |  | 2024-11-12 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | STARTECH.COM LTD | HB30A3A1CFB |  | 0 | 0 |  | 7218¦JA2585_1001 | 22 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -527 | 0
1470 | 1065001380100 | FOTOTRANSISTOR NPN 70V 100MA T-1/D3MM R | 1800114177 | 10 | 2024-10-16 |  | 4200582718 | 290 | 2024-10-24 | 2024-10-24 |  | 2024-11-10 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | VISHAY | BPW85A |  | 0 | 0 |  | 7218¦JA2586_1001 | 17 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1471 | 1229500300006 | CBL EQ SFP+10GBE AWG30 3M | 1800114199 | 10 | 2024-10-16 |  | 4200582287 | 10 | 2024-10-22 | 2024-10-29 |  | 2024-11-10 | 30 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | ENCORE REAL TIME ESPAÑA,S.A | OPTCORE | CAB-DAC30M-SFPP |  | 0 | 0 |  | 7218¦JA2585_1001 | 19 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1472 | 3210103550300 | CBL EQUI USB 2.0(M/M) 480MBPS TIP A L=3M | 1800114199 | 20 | 2024-10-16 |  | 4200586593 | 10 | 2024-11-20 | 2024-11-21 |  | 2024-12-04 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | MILEXIA IBÉRICA, S.A.U. | L-COM | CSMUAA-3M |  | 0 | 0 |  | 7218¦JA2585_1001 | 14 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -505 | 0
1473 | 1390704693802 | DISPLAY UNITS AIRBUS DU S/OF | 1800114244 | 10 | 2024-10-17 |  | 4200582413 | 10 | 2024-10-22 | 2024-10-24 |  | 2025-03-30 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ47701 |  | 1 | 1 |  | 7218¦JA2583_1001 | 159 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -389 | 0
1474 | 1209994210022 | ACC BACKSHELL #21 RECTO AL ZN/CO NEGRO | 1800114432 | 10 | 2024-10-21 |  | 4200585421 | 10 | 2024-11-13 | 2024-11-13 |  | 2024-11-18 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | GLENAIR, INC | MILITARY SPECS. | M85049/38-21Z |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -521 | 0
1475 | 1218000320303 | CNC ALIMENT P+N+T 6H 230V 16A IP44 AZ | 1800114432 | 20 | 2024-10-21 |  | 4200586251 | 20 | 2024-11-19 | 2024-11-20 |  | 2024-11-28 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MENNEKES ELECT. | 148A |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -511 | 0
1476 | 1237000122005 | BLOQ TERM 2P 26-12AWG AMR/VER ZPEA 2.5-2 | 1800114432 | 40 | 2024-10-21 |  | 4200584477 | 10 | 2024-11-06 | 2024-11-07 |  | 2024-11-10 | 110 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | WEIDMULLER, S.A. | WEIDMULLER | 1720950000 |  | 0 | 0 |  | 7218¦JA2582_1001 | 4 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1477 | 1237000122101 | BLOQ TERM 3P 26-12AWG ZDU 2.5-2/3AN ROHS | 1800114432 | 50 | 2024-10-21 |  | 4200584477 | 20 | 2024-11-06 | 2024-11-07 |  | 2024-11-10 | 40 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | WEIDMULLER, S.A. | WEIDMULLER | 1706010000 |  | 0 | 0 |  | 7218¦JA2582_1001 | 4 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1478 | 1237000262001 | BORNE D/POTENCIA 26AWG 500V GRIS ROHS | 1800114432 | 60 | 2024-10-21 |  | 4200591800 | 90 | 2024-12-30 | 2025-01-03 |  | 2025-01-24 | 110 | 8 | Liberado | 20 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | PHOENIX CONTACT | 3211480 |  | 0 | 0 |  | 7218¦JA2582_1001 | 25 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -454 | 0
1479 | 1237091470401 | PEINE CONEXION TRANSV 24A AMAR ZQV 2.5/2 | 1800114432 | 70 | 2024-10-21 |  | 4200584477 | 30 | 2024-11-06 | 2024-11-07 |  | 2024-11-10 | 110 | 8 | Liberado | 20 | 20 | 20 | 0 | 0 | 0 | X | 0.00 |  | WEIDMULLER, S.A. | WEIDMULLER | 1608860000 |  | 0 | 0 |  | 7218¦JA2582_1001 | 4 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1480 | 1237092052100 | TAPA FINAL 36.2X50.5X2.5MM BEIGE ZAP/TW7 | 1800114432 | 80 | 2024-10-21 |  | 4200584477 | 40 | 2024-11-06 | 2024-11-07 |  | 2024-11-10 | 40 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | WEIDMULLER, S.A. | WEIDMULLER | 1706110000 |  | 0 | 0 |  | 7218¦JA2582_1001 | 4 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1481 | 1237711415200 | TERM PUNTERA S=1,5MM2 L=14MM E-CU-PP NEG | 1800114432 | 90 | 2024-10-21 |  | 4200589329 | 20 | 2024-12-10 | 2024-12-13 |  | 2024-12-20 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | XB | TE-1.50 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -489 | 0
1482 | 1237714100000 | TERM AISL PUNTERA P/CBL 1MM2 ROJO | 1800114432 | 100 | 2024-10-21 |  | 4200584911 | 130 | 2024-11-08 | 2024-11-12 |  | 2024-11-29 | 40 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | RS | 458-702 |  | 1 | 1 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -510 | 0
1483 | 1705505480000 | PANEL FRONTAL 3U 84HP 426.4X128.4X2.5MM | 1800114432 | 110 | 2024-10-21 |  | 4200586187 | 200 | 2024-11-18 | 2024-11-21 |  | 2024-12-09 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 24563-096 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -500 | 0
1484 | 1706201190100 | MOD SOPORTE PU 19" 3U EQUIP P/SUBRACK | 1800114432 | 120 | 2024-10-21 |  | 4200586187 | 210 | 2024-11-18 | 2024-11-21 |  | 2024-12-09 | 45 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | CENVALSA, S.L. | CENVALSA | 991201500-24564100 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -500 | 0
1485 | 1706701900200 | RAIL GUIA DIN 43880 SOP SUJECCION P/19" | 1800114432 | 130 | 2024-10-21 |  | 4200586187 | 220 | 2024-11-18 | 2024-11-21 |  | 2024-12-09 | 60 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 24560-171 |  | 0 | 0 |  | 7218¦JA2582_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -500 | 0
1486 | 1000142801001 | RST PELMET AXI 2K80 1% 50PPM 2/5W 0204 R | 1800114433 | 10 | 2024-10-21 |  | 4200582734 | 250 | 2024-10-24 | 2024-11-04 | BORR | 2024-11-10 | 40 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 2.80 |  | TCX MICRO, S.L.U | VISHAY | MRS16000C2801FCT00 |  | 0 | 0 |  | 7218¦JA2583_1001 | 17 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -529 | 0
1487 | 1000142801001 | RST PELMET AXI 2K80 1% 50PPM 2/5W 0204 R | 1800114433 | 10 | 2024-10-21 |  | 4200589895 | 10 | 2024-12-12 | 2024-12-12 |  | 2025-02-13 | 40 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | VISHAY | MRS16000C2801FCT00 |  | 2 | 0 |  | 7218¦JA2583_1001 | 63 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -434 | 0
1488 | 1000242801001 | RST PELMET 2K80 1% 50PPM 3/5W 0207 ROHS | 1800114433 | 20 | 2024-10-21 |  | 4200582308 | 10 | 2024-10-22 | 2024-10-24 |  | 2024-11-04 | 40 | 8 | Liberado | 20 | 35 | 35 | 0 | 35 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | YAGEO | MF0207FTE52-2K8 |  | 0 | 0 |  | 7218¦JA2583_1001 | 13 | - |  | YES | 35 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -535 | 0
1489 | 1540913000001 | ARA ABA EXT P/M4 INOX DIN 6798A | 1800114433 | 30 | 2024-10-21 |  | 4200593022 | 10 | 2025-01-14 | 2025-01-15 |  | 2025-01-27 | 60 | 8 | Liberado | 400 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | INOX IBERICA, S.A. | DIN | DIN6798-A4,3-A2 |  | 0 | 0 |  | 7218¦JA2583_1001 | 13 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -451 | 0
1490 | 1264011783500 | SAI 80KW 3F 400V 5X8 C/ARMARIO/INT S/OF | 1800114612 | 10 | 2024-10-23 |  | 4200595863 | 10 | 2025-01-31 | 2025-02-05 |  | 2025-02-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. | SCHNEIDER ELECTRIC | GVSUPS80KHS/221213-12728957 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -419 | 0
1491 | 1264011783500 | SAI 80KW 3F 400V 5X8 C/ARMARIO/INT S/OF | 1800114612 | 10 | 2024-10-23 |  | 4200584758 | 10 | 2024-11-07 | 2024-11-08 | BORR | 2024-11-12 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 15105.56 |  | SCHNEIDER ELECTRIC IT SPAIN, S.L | SCHNEIDER ELECTRIC | GVSUPS80KHS/221213-12728957 |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -527 | 0
1492 | 1209994130024 | ACC BACKSHELL #13 RECTO AL ZN/CO NEGRO | 1800114613 | 10 | 2024-10-23 |  | 4200585421 | 20 | 2024-11-13 | 2024-11-13 |  | 2024-12-11 | 40 | 8 | Liberado | 30 | 30 | 30 | 0 | 0 | 0 | X | 0.00 |  | GLENAIR, INC | MILITARY SPECS. | M85049/38-13Z |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -498 | 0
1493 | 1237000122003 | BLOQ TERM 2P 26-12AWG DNRAIL G/Y PT2,5PE | 1800114613 | 20 | 2024-10-23 |  | 4200591800 | 10 | 2024-12-30 | 2025-01-03 |  | 2025-01-24 | 40 | 8 | Liberado | 20 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | PHOENIX CONTACT | 3209536 |  | 0 | 0 |  | 7218¦JA2582_1001 | 25 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -454 | 0
1494 | 1237090062101 | BORNA RAIL SIZE#22 DISENO#3 5A S/SELLAR | 1800114614 | 20 | 2024-10-23 |  | 4200585921 | 20 | 2024-11-15 | 2024-11-22 |  | 2025-02-10 | 30 | 8 | Liberado | 20 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | SOURIAU | SOURIAU | 8559N2202B |  | 0 | 0 |  | 7218¦JA2583_1001 | 87 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -437 | 0
1495 | 3050501221300 | MEMORY RAM SODIMM 16GB 3200MHZ 1.2V DDR4 | 1800114614 | 30 | 2024-10-23 |  | 4200584480 | 10 | 2024-11-06 | 2024-11-06 |  | 2024-11-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | CRUCIAL | CT16G4SFD832A |  | 0 | 0 |  | 7218¦JA2583_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -524 | 0
1496 | 3060303930200 | DISK SSD 250GB M.2 NVME PCIE G4X4 3D TLC | 1800114614 | 40 | 2024-10-23 |  | 4200584489 | 10 | 2024-11-06 | 2024-11-06 |  | 2024-11-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TD SYNNEX SPAIN, S.L.U. | KINGSTON | SNV2S/250G |  | 0 | 0 |  | 7218¦JA2583_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -524 | 0
1497 | 1237714400300 | TERM PUNTE AISL P/CBL 4MM2 E-CU-PP NARAN | 1800114615 | 10 | 2024-10-23 |  | 4200590467 | 10 | 2024-12-17 | 2024-12-17 |  | 2024-12-20 | 45 | 8 | Liberado | 50 | 100 | 100 | 0 | 0 | 0 | X | 0.00 |  | LUJISA, S.A. | XB | TE-4.00 |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -489 | 0
1498 | 1238514252800 | TERM PUNTERA P/CBL 2,5MM2 E-CU-PP GRIS | 1800114615 | 20 | 2024-10-23 |  | 4200589329 | 40 | 2024-12-10 | 2024-12-13 |  | 2024-12-20 | 40 | 8 | Liberado | 100 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | XB | TE-2.50 |  | 0 | 0 |  | 7218¦JA2585_1001 | 10 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -489 | 0
1499 | 1587080790700 | ETIQ ADH 27X12,5MM PLATA PE TRASNF TERMI | 1800114615 | 30 | 2024-10-23 |  | 4200582294 | 100 | 2024-10-22 | 2024-11-18 |  | 2024-11-10 | 40 | 8 | Liberado | 50 | 250 | 250 | 0 | 250 | 0 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | BRADY | M71EP-2-7593-SL |  | 0 | 0 |  | 7218¦JA2585_1001 | 19 | - |  | YES | 250 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1500 | 1705202000000 | CUBIERTA P/ MODULO SOPORTE 19" 3U | 1800114615 | 40 | 2024-10-23 |  | 4200589856 | 10 | 2024-12-12 | 2024-12-12 |  | 2025-01-15 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CENVALSA, S.L. | PENTAIR | 24564-100 |  | 0 | 0 |  | 7218¦JA2585_1001 | 34 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -463 | 0
1501 | 1706201190000 | KIT MOD DISTR POT SUBRACK 3U 84HP 115MM | 1800114615 | 50 | 2024-10-23 |  | 4200587542 | 80 | 2024-11-27 | 2024-11-27 |  | 2024-12-20 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 24563-100 |  | 1 | 0 |  | 7218¦JA2585_1001 | 23 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -489 | 0
1502 | 1209994085220 | ACC CNC CIR #8 .500-20UNF STRN RELIEF NI | 1800114616 | 10 | 2024-10-23 |  | 4200584635 | 420 | 2024-11-07 | 2024-12-29 |  | 2024-11-10 | 80 | 8 | Liberado | 25 | 25 | 25 | 0 | 25 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | M85049/52-1-8N |  | 0 | 0 |  | 7218¦JA2586_1001 | 3 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1503 | 1229511850000 | CBL EQ STEREO-3.5MM-H ACOD/2XRCA-M L=3M | 1800114617 | 10 | 2024-10-23 |  | 4200592966 | 80 | 2025-01-14 | 2025-01-17 |  | 2025-01-24 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | VAN DAMME | 103-326-704 |  | 0 | 0 |  | 7218¦JA2587_1001 | 10 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -454 | 0
1504 | 3190402380300 | MONITOR TACTIL LCD 22" 1920X1080 FULL HD | 1800114618 | 10 | 2024-10-23 |  | 4200583638 | 30 | 2024-10-30 | 2024-10-30 |  | 2024-11-13 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INGRAM MICRO, S.L.U. | ELO TOUCH SOLUTIONS | E351600 |  | 0 | 0 |  | 7218¦JA2588_1001 | 14 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -526 | 0
1505 | 1209994130022 | STRAIN RELIEF #13 AL/NI M85049/38-13N | 1800114769 | 10 | 2024-10-25 |  | 4200584417 | 10 | 2024-11-05 | 2024-11-06 |  | 2024-11-10 | 30 | 8 | Liberado | 9 | 9 | 9 | 0 | 9 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | SAE INC. | AS85049/38-13N |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 9 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1506 | 1214200430721 | CNC CIR 13-4 4H PLUG D38999/26ZC4SN | 1800114769 | 20 | 2024-10-25 |  | 4200584635 | 510 | 2024-11-07 | 2024-12-29 |  | 2024-11-10 | 45 | 8 | Liberado | 11 | 11 | 11 | 0 | 11 | 0 | X | 0.00 |  | Electro Enterprises New York | MILITARY SPECS. | D38999/26ZC4SN |  | 0 | 0 |  | 7218¦JA2582_1001 | 3 | - |  | YES | 11 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1507 | 1218095002000 | CLAVIJA STAR TOP 400V 50/60HZ 16A ROJO | 1800114769 | 30 | 2024-10-25 |  | 4200586251 | 40 | 2024-11-19 | 2024-11-20 |  | 2024-11-28 | 80 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MENNEKES ELECT. | 33 |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -511 | 0
1508 | 1222291900200 | CBL 2X1,50MM TRENZADO 500V ROJO/NEGRO | 1800114769 | 40 | 2024-10-25 |  | 4200591804 | 10 | 2024-12-30 | 2025-01-08 |  | 2025-01-10 | 30 | 8 | Liberado | 50 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | LUJISA, S.A. | GESCABLE | GESFIRE RF 90 AS+ |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -468 | 0
1509 | 1237092052300 | TAPA FINAL 36.2X50.5X2.5MM ZAP/TW7 OR | 1800114769 | 50 | 2024-10-25 |  | 4200584477 | 70 | 2024-11-06 | 2024-11-07 |  | 2024-11-10 | 40 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | WEIDMULLER, S.A. | WEIDMULLER | 1706130000 |  | 0 | 0 |  | 7218¦JA2582_1001 | 4 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -529 | 0
1510 | 3166035600000 | LIC SW SIMULADOR FMS A320 FFS | 1800114778 | 20 | 2024-10-25 |  | 4200589833 | 10 | 2024-12-12 | 2025-01-07 |  | 2025-01-07 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | Honeywell International SARL | HONEYWELL | PS4087600-907 |  | 0 | 0 |  | 7218¦JA2576_1001 | 26 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -471 | 0
1511 | 1706202120000 | SOPORTE CARRIL DIN 84HP 426MM GRIS ACERO | 1800114780 | 10 | 2024-10-25 |  | 4200586187 | 230 | 2024-11-18 | 2024-11-21 |  | 2024-12-09 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 24565-100 |  | 0 | 0 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -500 | 0
1512 | 1390704692600 | PANEL FFIOS 170X85X58.25MM | 1800114782 | 10 | 2024-10-25 | BORR | 4200583170 | 10 | 2024-10-28 | 2024-11-05 | BORR | 2024-12-23 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 7960.78 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40402 |  | 0 | 0 |  | 7218¦JA2588_1001 | 56 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -486 | 0
1513 | 1390704692700 | PANEL SEAT 71X85MM ALUM 6061T6 | 1800114782 | 20 | 2024-10-25 |  | 4200583170 | 20 | 2024-10-28 | 2024-11-05 |  | 2025-02-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40403 |  | 1 | 1 |  | 7218¦JA2588_1001 | 118 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -424 | 0
1514 | 1390704692800 | PANEL CONEXION AUDIO IOS 50X85MM ALUM | 1800114782 | 30 | 2024-10-25 | BORR | 4200583170 | 30 | 2024-10-28 | 2024-11-05 | BORR | 2024-12-23 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 1068.08 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40404 |  | 0 | 0 |  | 7218¦JA2588_1001 | 56 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -486 | 0
1515 | 1390704693000 | PANEL SEAT+AUDIO ALUM 6061T6 | 1800114782 | 40 | 2024-10-25 | BORR | 4200583170 | 40 | 2024-10-28 | 2024-11-05 | BORR | 2024-12-23 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 1733.42 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40406 |  | 0 | 0 |  | 7218¦JA2588_1001 | 56 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -486 | 0
1516 | 1390704693100 | PANEL BLANCO 50X85X2MM ALUM 6061T6 | 1800114782 | 50 | 2024-10-25 | BORR | 4200583170 | 50 | 2024-10-28 | 2024-11-05 | BORR | 2024-12-23 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 565.95 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40407 |  | 0 | 0 |  | 7218¦JA2588_1001 | 56 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 10 | 100% |  | -486 | 0
1517 | 1390705801095 | IOS AUDIO CONNECTION PANEL A320 | 1800114782 | 60 | 2024-10-25 |  | 4200583170 | 60 | 2024-10-28 | 2024-11-05 |  | 2025-02-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40408 |  | 1 | 1 |  | 7218¦JA2588_1001 | 118 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -424 | 0
1518 | 1390705801195 | USB PANEL A320 | 1800114782 | 70 | 2024-10-25 |  | 4200583170 | 70 | 2024-10-28 | 2024-11-05 |  | 2025-02-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40409 |  | 1 | 1 |  | 7218¦JA2588_1001 | 118 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -424 | 0
1519 | 1390705801295 | AUDIO AND SEAT PANEL A320 | 1800114782 | 80 | 2024-10-25 |  | 4200583170 | 80 | 2024-10-28 | 2024-11-05 |  | 2025-02-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40410 |  | 1 | 1 |  | 7218¦JA2588_1001 | 118 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -424 | 0
1520 | 1390705801395 | FFIOS PANEL A320 | 1800114782 | 90 | 2024-10-25 |  | 4200583170 | 90 | 2024-10-28 | 2024-11-05 |  | 2025-02-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40411 |  | 1 | 1 |  | 7218¦JA2588_1001 | 118 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -424 | 0
1521 | 1390705801495 | BLANCK PANEL A320 | 1800114782 | 100 | 2024-10-25 |  | 4200583170 | 100 | 2024-10-28 | 2024-11-05 |  | 2025-02-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ40412 |  | 1 | 1 |  | 7218¦JA2588_1001 | 118 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -424 | 0
1522 | 1229598230401 | CBL EQ HDMI 1.4-M/M HD PRO P/150 L=45.7M | 1800114783 | 10 | 2024-10-25 |  | 4200585481 | 10 | 2024-11-13 | 2024-11-13 |  | 2024-11-21 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. | EXTRON ELECTRONICS | 26-726-150 |  | 1 | 1 |  | 7218¦JA2588_1001 | 8 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -518 | 0
1523 | 1219000490700 | CAJA PORTACONTACTOS 4H 1,57MM RECEP | 1800115231 | 10 | 2024-11-04 |  | 4200588938 | 160 | 2024-12-05 | 2024-12-10 |  | 2024-12-17 | 30 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | TELKRON, S.A. | MOLEX | 0050291758 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -492 | 0
1524 | 1237092052800 | TAPA FINAL 2.2X39.6X68MM GRIS D-PTTB 2.5 | 1800115231 | 20 | 2024-11-04 |  | 4200585756 | 70 | 2024-11-14 | 2024-11-19 |  | 2024-11-25 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | LUJISA, S.A. | PHOENIX CONTACT | 3211634 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -514 | 0
1525 | 1237093219000 | TAPA FINAL 48.6X2.2X29.1MM PA GRS DST2,5 | 1800115231 | 30 | 2024-11-04 |  | 4200585736 | 80 | 2024-11-14 | 2024-11-14 |  | 2024-11-25 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | PHOENIX CONTACT | 3030417 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -514 | 0
1526 | 7854619050100 | CORREA MUÑECA TIERRA ESD BANANA/M 1.8M | 1800115232 | 10 | 2024-11-04 |  | 4200585517 | 10 | 2024-11-13 | 2024-11-14 |  | 2024-11-10 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | STARTECH.COM LTD | SWS100 |  | 0 | 0 |  | 7218¦JA2585_1001 | -3 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -529 | 0
1527 | 0915477020000 | PCB-400 HZ AC DIMMER BOARD | 1800115413 | 10 | 2024-11-07 |  | 4200584859 | 10 | 2024-11-08 | 2024-11-08 |  | 2024-12-09 | 50 | 8 | Liberado | 6 | 6 | 6 | 0 | 6 | 0 | X | 0.00 |  | LAB CIRCUITS SA | INDRA SISTEMAS S.A. | 0915477020000 |  | 0 | 0 |  | 7218¦JA2586_1001 | 31 | - |  | YES | 6 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -500 | 0
1528 | 0973585290100 | SOPORTE ESPEJO | 1800115609 | 10 | 2024-11-13 |  | 4600004162 | 80 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290100 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1529 | 1204894000006 | ACC P/CNC BACKSHELL SR R/A NIC SIZE 19 | 1800115630 | 10 | 2024-11-13 |  | 4200590263 | 130 | 2024-12-16 | 2024-12-18 |  | 2025-02-14 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CONECTORES Y CABLES VAHER, S.A. | AMPHENOL CORP | M85049/39-19N |  | 2 | 1 |  | 7218¦JA2582_1001 | 60 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -433 | 0
1530 | 1219090250000 | ACC CONTACTO H AWG18-24 D=1,57MM SERIE 1 | 1800115630 | 20 | 2024-11-13 |  | 4200594482 | 20 | 2025-01-24 | 2025-01-24 |  | 2025-02-04 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 0 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | RS | 236-3050 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -443 | 0
1531 | 3210104720000 | LATIGUILLO ETHERNET UTP CAT.6 RJ45 M/M, | 1800115631 | 10 | 2024-11-13 |  | 4200586361 | 10 | 2024-11-19 | 2024-11-19 |  | 2024-11-22 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-3M |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
1532 | 3210104720100 | LATIGUILLO ETHERNET UTP CAT.6 RJ45 M/M, | 1800115631 | 20 | 2024-11-13 |  | 4200586361 | 20 | 2024-11-19 | 2024-11-19 |  | 2024-11-22 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-5M |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
1533 | 3210104720300 | LATIGUILLO ETHERNET UTP CAT.6 RJ45 M/M, | 1800115631 | 30 | 2024-11-13 |  | 4200586361 | 30 | 2024-11-19 | 2024-11-19 |  | 2024-11-22 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-10M |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
1534 | 3210104721300 | LATIGUILLO ETHERNET UTP CAT6 RJ45 M/M L= | 1800115631 | 40 | 2024-11-13 |  | 4200586361 | 40 | 2024-11-19 | 2024-11-19 |  | 2024-11-22 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | CBT-CAT6-2M |  | 0 | 0 |  | 7218¦JA2585_1001 | 3 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -517 | 0
1535 | 1229593631000 | CBL EQUIP EXTENS USB 2.0 L=8M | 1800115632 | 10 | 2024-11-13 |  | 4200586683 | 10 | 2024-11-20 | 2024-11-21 |  | 2024-11-29 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ELECTRONIC EQUIPMENT TRADING SAU (E | LINDY | 42780 |  | 0 | 0 |  | 7218¦JA2588_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -510 | 0
1536 | 0973585290200 | CIERRE SUPERIOR | 1800115675 | 10 | 2024-11-15 |  | 4600004162 | 50 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290200 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1537 | 0973585290300 | SOPORTE PANTALLA BPS | 1800115675 | 20 | 2024-11-15 |  | 4600004162 | 60 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290300 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1538 | 0973585290400 | CIERRE POST SUP + ANILLOS ADAPT | 1800115675 | 30 | 2024-11-15 |  | 4600004162 | 70 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290400 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1539 | 0973585290500 | CERRAMIENTO INFERIOR | 1800115676 | 10 | 2024-11-15 |  | 4600004162 | 20 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290500 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1540 | 0973585290600 | PANEL POSTERIOR | 1800115676 | 20 | 2024-11-15 |  | 4600004162 | 30 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290600 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1541 | 0973585290700 | ESTRUCTURA PROY BANDEJA PROY SOPORT MASC | 1800115676 | 30 | 2024-11-15 |  | 4600004162 | 40 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290700 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1542 | 0973585290800 | BPS MATIZADA | 1800115677 | 10 | 2024-11-15 |  | 4600004162 | 10 | 2024-11-19 | 2024-11-20 |  | 2025-12-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585290800 |  | 0 | 0 |  | 7218¦JA2578_1001 | 391 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -129 | 0
1543 | 1124390028000 | ACC CUERPO 1NO+1NC C/BLOQ P/INT FINAL | 1800115921 | 10 | 2024-11-21 |  | 4200587699 | 20 | 2024-11-28 | 2024-11-28 |  | 2024-12-05 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | LUJISA, S.A. | LOVATO ELECTRIC S.P.A. | KXCBS11 |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -504 | 0
1544 | 1124390028100 | ACC PALANC RODIL ADJ D19X5MM P/INT FINAL | 1800115921 | 20 | 2024-11-21 |  | 4200587700 | 10 | 2024-11-28 | 2024-11-28 |  | 2024-12-09 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | LOVATO ELECTRIC S.P.A. | KXAF1 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -500 | 0
1545 | 1218000324400 | CNC IEC C13 3P/H+T 250V LSZH C/BLOQUEO | 1800115921 | 30 | 2024-11-21 |  | 4200590003 | 140 | 2024-12-13 | 2025-01-08 |  | 2025-01-24 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 0 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | IEC LOCK | PA130100BK |  | 1 | 0 |  | 7218¦JA2582_1001 | 42 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -454 | 0
1546 | 1229500280015 | CBL EQ CEE7/7 ACOD-M/IECC13 RECT-H L=2M | 1800115921 | 40 | 2024-11-21 |  | 4200588386 | 300 | 2024-12-03 | 2025-09-30 |  | 2024-12-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | STARTECH.COM LTD | PXT101EUR |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -499 | 0
1547 | 1234090019000 | FIJACION CABLE VELCRO/SOPORTE 400MM | 1800115921 | 50 | 2024-11-21 |  | 4200587320 | 10 | 2024-11-26 | 2024-11-28 |  | 2025-01-31 | 60 | 8 | Liberado | 10 | 10 | 12 | 0 | 10 | 2 | X | 0.00 |  | RITTAL, S.A | RITTAL | 5502.155 |  | 1 | 0 |  | 7218¦JA2582_1001 | 66 | - |  | YES | 12 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -447 | 0
1548 | 1246701149001 | MOD CONTROL REMOTO 120X120X19MM VRV SKY | 1800115921 | 60 | 2024-11-21 |  | 4200587505 | 10 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | BRC1E53A |  | 1 | 1 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0
1549 | 1246701149100 | MOD CONTROL REMOTO MANDO-CBL C/BLUETOOTH | 1800115921 | 70 | 2024-11-21 |  | 4200587505 | 20 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 2 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | BRC1H52W | X | 1 | 1 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0 |  | X
1550 | 1246790030000 | KIT CONTROL ON/OFF REMOTO PARO FORZADO | 1800115921 | 80 | 2024-11-21 |  | 4200587505 | 30 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 2 | 2 | 4 | 0 | 2 | 2 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | EKRORO |  | 1 | 1 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0
1551 | 1501215010001 | TOR ALO CRUC M5X10 INOX DIN7985/ISO7045 | 1800115922 | 10 | 2024-11-21 |  | 4200594703 | 30 | 2025-01-27 | 2025-01-27 |  | 2025-02-07 | 60 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN7985-M5X10-A2-70-H |  | 0 | 0 |  | 7218¦JA2583_1001 | 11 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -440 | 0
1552 | 1709906180000 | TUERCA ENJAULAD M6 P/ESP 0,8-2,5MM 50PCS | 1800115922 | 20 | 2024-11-21 |  | 4200596342 | 10 | 2025-02-04 | 2025-02-06 |  | 2025-02-12 | 40 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | RITTAL, S.A | RITTAL | 2094.200 |  | 0 | 0 |  | 7218¦JA2583_1001 | 8 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -435 | 0
1553 | 1216500240400 | CNC AUDIO 2H 1.5-4MM2 QUICKLOCK SPEAKON | 1800115923 | 10 | 2024-11-21 |  | 4200598539 | 10 | 2025-02-18 | 2025-02-24 |  | 2025-03-12 | 85 | 8 | Liberado | 2 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | AMALFI TRADING, INC | NEUTRIK | NL2FX |  | 0 | 0 |  | 7218¦JA2584_1001 | 22 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -407 | 0
1554 | 1250200530300 | AMPLIF AUDIO 4CH 4X75W/4R 4X50W/8R 300W | 1800115923 | 20 | 2024-11-21 |  | 4200588053 | 10 | 2024-11-29 | 2024-11-29 |  | 2024-12-30 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | BEHRINGER SPEZIELLE | EPQ304 |  | 1 | 1 |  | 7218¦JA2584_1001 | 31 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -479 | 0
1555 | 1263011021400 | F.A. VE=230VAC VS=15VDC 1.6A 25W TIPO-C | 1800115923 | 30 | 2024-11-21 |  | 4200594157 | 10 | 2025-01-22 | 2025-01-27 |  | 2024-11-30 | 40 | 8 | Liberado | 1 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | ALPHA ELETTRONICA | SW25-415-60 |  | 0 | 0 |  | 7218¦JA2584_1001 | -53 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -509 | 0
1556 | 1263011021400 | F.A. VE=230VAC VS=15VDC 1.6A 25W TIPO-C | 1800115923 | 30 | 2024-11-21 |  | 4200587632 | 10 | 2024-11-27 | 2024-11-28 | BORR | 2025-01-03 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 47.50 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | ALPHA ELETTRONICA | SW25-415-60 |  | 0 | 0 |  | 7218¦JA2584_1001 | 37 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 11 | 100% |  | -475 | 0
1557 | 1229500280014 | CBL EQ USB 2.0-C M/M RECT PVC NEGRO L=4M | 1800115924 | 10 | 2024-11-21 |  | 4200588386 | 310 | 2024-12-03 | 2025-09-30 |  | 2024-12-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TELKRON, S.A. | STARTECH.COM LTD | USB2C5C4M |  | 0 | 0 |  | 7218¦JA2585_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -499 | 0
1558 | 1229591600803 | CBL EQ PC CAT6A F/UTP RJ45 LSZH VER L=3M | 1800115924 | 20 | 2024-11-21 |  | 4200590815 | 10 | 2024-12-18 | 2024-12-18 |  | 2024-12-31 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | LAT-CAT6AF-VD-3 |  | 0 | 0 |  | 7218¦JA2585_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -478 | 0
1559 | 1229591600903 | CBL EQ PC CAT6A F/UTP RJ45 LSZH NE L=10M | 1800115924 | 30 | 2024-11-21 |  | 4200590815 | 20 | 2024-12-18 | 2024-12-18 |  | 2024-12-31 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | CUBITEL,S.L | CUBITEL | LAT-CAT6AF-NG-10 |  | 0 | 0 |  | 7218¦JA2585_1001 | 13 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -478 | 0
1560 | 3190402940300 | MONITOR IPS 22.5" 1920X1080 HDMI/DP/USB | 1800115925 | 10 | 2024-11-21 |  | 4200588806 | 10 | 2024-12-05 | 2024-12-05 |  | 2025-01-14 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | DELL COMPUTER, S.A. | DELL COMPUTER | P2225H |  | 1 | 1 |  | 7218¦JA2588_1001 | 40 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -464 | 0
1561 | 1246701141300 | UDAD EXT A/C 1F 220-240V R32/675 DAG125A | 1800115974 | 10 | 2024-11-24 |  | 4200587505 | 40 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 2 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | RZAG125NV1 | X | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0 |  | X
1562 | 1246701141400 | UDAD INT A/C 12.1/13.5KW R32 DAG125A | 1800115974 | 20 | 2024-11-24 |  | 4200587505 | 50 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 2 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | FDA125A | X | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0 |  | X
1563 | 1246701141500 | UDAD EXT A/C 3F 15.9A R32 DA200A | 1800115974 | 30 | 2024-11-24 |  | 4200587505 | 60 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | RZA200D |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0
1564 | 1246701141600 | UDAD INT A/C 19/22.4KW R32 DA200A | 1800115974 | 40 | 2024-11-24 |  | 4200587505 | 70 | 2024-11-27 | 2024-11-27 |  | 2024-12-06 | 40 | 8 | Liberado | 1 | 1 | 2 | 0 | 1 | 1 | X | 0.00 |  | YNTEGRA SERV.INTEGRALES, S.L. | DAIKIN | FDA200A |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0
1565 | 1216500321701 | CNC JACK 6.35MM 3H RECPT RECT PANEL SOLD | 1800115975 | 10 | 2024-11-24 |  | 4200587560 | 50 | 2024-11-27 | 2024-12-03 |  | 2024-12-06 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | LUMBERG CONNECT GMBH | KLB 3 |  | 0 | 0 |  | 7218¦JA2584_1001 | 9 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -503 | 0
1566 | 1220112502800 | CBL FLEX 1X0.05MM2 600V ETFE GRI SPEC55A | 1800116190 | 10 | 2024-11-26 |  | 4200592835 | 40 | 2025-01-14 | 2025-01-14 |  | 2025-01-31 | 40 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | TE CONNECTIVITY | 55A9002-30-8 |  | 0 | 0 |  | 7218¦JA2582_1001 | 17 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -447 | 0
1567 | 1351500460000 | MOD ETHERNET GIGABIT 2P NUC LID | 1800116191 | 10 | 2024-11-26 |  | 4200590025 | 10 | 2024-12-13 | 2024-12-13 |  | 2025-01-10 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | ELECTRONIC PRODUCT SOLUTIONS | GR-LID-1971 |  | 0 | 0 |  | 7218¦JA2583_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -468 | 0
1568 | 1390700480200 | BRAKE PRESSURE INDICATOR | 1800116698 | 10 | 2024-12-05 |  | 4200589302 | 10 | 2024-12-10 | 2024-12-11 |  | 2025-01-15 | 86 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | EUROPAVIA ESPAÑA S.A. | THALES | 64882-206-1 |  | 0 | 0 |  | 7218¦JA2582_1001 | 36 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -463 | 0
1569 | 1209990010000 | PIN PARA CONECTOR SUB-D M 20-24AWG | 1800116882 | 10 | 2024-12-10 |  | 4200590885 | 170 | 2024-12-18 | 2024-12-19 |  | 2025-01-24 | 52 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | AMPHENOL CORP | 17-RRD1M11-400 |  | 2 | 1 |  | 7218¦JA2582_1001 | 37 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -454 | 0
1570 | 1210300938000 | CNC HOUSING RECEPT 9H 3,68MM CRIMP NYLON | 1800116882 | 20 | 2024-12-10 |  | 4200592303 | 100 | 2025-01-08 | 2025-01-08 |  | 2025-01-20 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | TELKRON, S.A. | MOLEX | 03-06-1092 |  | 0 | 0 |  | 7218¦JA2582_1001 | 12 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -458 | 0
1571 | 1219990010100 | PIN H CNC SUB-D AWG20-24 | 1800116882 | 30 | 2024-12-10 |  | 4200590885 | 210 | 2024-12-18 | 2024-12-19 |  | 2025-01-24 | 66 | 8 | Liberado | 200 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | MOUSER ELECTRONICS, INC. | AMPHENOL CORP | 17-RRD1F 11-400 |  | 1 | 0 |  | 7218¦JA2582_1001 | 37 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -454 | 0
1572 | 1141009210100 | LUMINARIA LED 15BLANC+1ROJO 10-3VDC F-4M | 1800116883 | 10 | 2024-12-10 |  | 4200590489 | 30 | 2024-12-17 | 2024-12-17 |  | 2024-12-20 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | FRENSCH GMBH | 6267 |  | 0 | 0 |  | 7218¦JA2583_1001 | 3 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -489 | 0
1573 | 1229508280005 | CBL EQ UTP RJ45-M/M 50FT NEGRO CAT6 LSZH | 1800116884 | 10 | 2024-12-10 |  | 4200594997 | 20 | 2025-01-28 | 2025-01-31 |  | 2025-02-28 | 55 | 8 | Liberado | 8 | 8 | 8 | 0 | 8 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6K-50-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 31 | - |  | YES | 8 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -419 | 0
1574 | 1390700590501 | SISTEMA EGPWS MKVA 115VAC P/A320/330/340 | 1800116903 | 10 | 2024-12-11 |  | 4200589833 | 20 | 2024-12-12 | 2025-01-07 |  | 2025-01-07 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | Honeywell International SARL | HONEYWELL | 69000942-151 |  | 0 | 0 |  | 7218¦JA2576_1001 | 26 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -471 | 0
1575 | 3210503440000 | EXTENSOR USB 2.0/CAT5 100MT | 1800117120 | 10 | 2024-12-13 |  | 4200591593 | 10 | 2024-12-24 | 2024-12-24 |  | 2025-02-28 | 40 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | CHARMEX INTERNACIONAL S.A. | GEFEN INC | EXT-USB2.0-LR |  | 3 | 0 |  | 7218¦JA2587_1001 | 66 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -419 | 0
1576 | 0972881203200 | NUC PLATE SUPPORT | 1800117351 | 10 | 2024-12-18 |  | 4200594989 | 10 | 2025-01-28 | 2025-01-29 |  | 2025-03-14 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | PUNZOMET S.L. | INDRA SISTEMAS S.A. | 0972881203200 |  | 0 | 0 |  | 7218¦JA2583_1001 | 45 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -405 | 0
1577 | 7884000010000 | EXTINTOR CO2 2KG 34B 3,01L 116X485MM | 1800117501 | 10 | 2024-12-19 |  | 4200592939 | 10 | 2025-01-14 | 2025-01-14 |  | 2025-02-11 | 30 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | IBERCOIN INGENIEROS, S.L. | EXTINTORES FAEX, S.L. | CO2-2 AF |  | 1 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 12 | 0% |  | -436 | 0
1578 | 1229508280003 | CBL EQ UTP RJ45-M/M 20FT NEGRO CAT6 LSZH | 1800117638 | 10 | 2025-01-08 |  | 4200592966 | 30 | 2025-01-14 | 2025-01-17 |  | 2025-01-31 | 45 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6K-20-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
1579 | 1229508280004 | CBL EQ UTP RJ45-M/M 35FT NEGRO CAT6 LSZH | 1800117638 | 20 | 2025-01-08 |  | 4200592966 | 40 | 2025-01-14 | 2025-01-17 |  | 2025-01-31 | 30 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6K-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 17 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
1580 | 1229508280303 | CBL EQ UTP RJ45-M/M 20FT BLANC CAT6 LSZH | 1800117638 | 30 | 2025-01-08 |  | 4200592966 | 50 | 2025-01-14 | 2025-01-17 |  | 2025-01-31 | 75 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6W-20-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 17 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
1581 | 1229508280304 | CBL EQ UTP RJ45-M/M 35FT BLANC CAT6 LSZH | 1800117638 | 40 | 2025-01-08 |  | 4200592966 | 60 | 2025-01-14 | 2025-01-17 |  | 2025-01-31 | 105 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6W-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 17 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
1582 | 1229508280703 | CBL EQ UTP RJ45-M/M 20FT NARAN CAT6 LSZH | 1800117638 | 50 | 2025-01-08 |  | 4200592966 | 70 | 2025-01-14 | 2025-01-17 |  | 2025-01-31 | 105 | 8 | Liberado | 7 | 7 | 7 | 0 | 7 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6O-20-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 17 | - |  | YES | 7 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -447 | 0
1583 | 1390704694600 | PANEL PUERTA CRT | 1800117645 | 10 | 2025-01-08 |  | 4200593050 | 10 | 2025-01-15 | 2025-01-17 |  | 2025-03-09 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-PNL27802 |  | 1 | 1 |  | 7218¦JA2583_1001 | 53 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -410 | 0
1584 | 1230123802000.LO | TUBO SILICONA TRANSLUC DI=0,8 GROS=0,4MM | 1800117646 | 10 | 2025-01-08 |  | 4200594689 | 10 | 2025-01-27 |  | BORR | 2025-02-20 | 40 | 8 |  | 100 | 300 | 0 | 300 | 0 | 0 |  | 363.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MEREFSA | TSTR600080040 |  | 0 | 0 |  | 7218¦JA2582_1001 | 24 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 1 | 100% |  | -427 | 0
1585 | 1230123802000.LO | TUBO SILICONA TRANSLUC DI=0,8 GROS=0,4MM | 1800117646 | 10 | 2025-01-08 |  | 4200596822 | 10 | 2025-02-07 | 2025-02-10 |  | 2025-03-07 | 40 | 8 | Liberado | 100 | 300 | 300 | 0 | 0 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | MEREFSA | TSTR600080040 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 300 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -412 | 0
1586 | 3190403160000 | MONITOR 27" LCD IPS QHD 2560X1440 240HZ | 1800118608 | 10 | 2025-01-27 |  | 4200595584 | 10 | 2025-01-30 | 2025-01-30 |  | 2025-02-26 | 40 | 8 | Liberado | 2 | 2 | 4 | 0 | 0 | 2 | X | 0.00 |  | DELL COMPUTER, S.A. | DELL COMPUTER | AW2723DF |  | 1 | 1 |  | 7218¦JA2588_1001 | 27 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -421 | 0
1587 | 1202091000002 | CARCASA P/CNC SUB-D #15 METALICA ROHS | 1800118661 | 10 | 2025-01-27 |  | 4200595475 | 80 | 2025-01-30 | 2025-01-31 |  | 2025-02-15 | 80 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL AEROSPACE | 8655MH1501LF |  | 0 | 0 |  | 7218¦JA2582_1001 | 16 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 1 | 0% |  | -432 | 0
1588 | 1222700240801.LO | CBL PARES TWIST 4X2 CAT5E UTP AWG24 PVC | 1800119186 | 30 | 2025-02-06 |  | 4200597215 | 60 | 2025-02-11 | 2025-02-12 |  | 2025-02-20 | 40 | 8 | Liberado | 4.5 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | ARISTON | NI 1002 |  | 0 | 0 |  | 7218¦JA2590_1001 | 9 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -427 | 0
1589 | 1589908780000 | TAPON OBTURADOR 14.5MM POLIAMIDA-6.6 NEG | 1800119425 | 10 | 2025-02-10 |  | 4200599844 | 10 | 2025-02-26 | 2025-02-26 |  | 2025-03-04 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | TR FASTENINGS | RP0000383456 |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -415 | 0
1590 | 1220115701000 | CBL FLEX 1X70MM2 H07Z1-K 450/700V NEG R | 1800120450 | 10 | 2025-02-24 |  | 4200601578 | 10 | 2025-03-10 | 2025-03-11 |  | 2025-03-15 | 85 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | LUJISA, S.A. | MIGUELEZ | 84109-NEGRO |  | 0 | 0 |  | 7218¦JA2582_1001 | 5 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -404 | 0
1591 | 1220115702600 | CBL FLEX 1X70MM2 450/750V AZUL H07ZK 90C | 1800120450 | 20 | 2025-02-24 |  | 4200601560 | 10 | 2025-03-09 | 2025-03-09 |  | 2025-11-24 | 85 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 578.00 |  | Technipol Suministros, S.L. | LAPP KABEL | 4727021 |  | 2 | 0 |  | 7218¦JA2582_1001 | 260 | - | [5 empty] | 1 |  | 0% | 4200601560 |  |  |  | 2 | 100% |  | -150 | 0
1592 | 1237790900000 | TERM REDONDO REFORZ 70 D=8 | 1800120450 | 30 | 2025-02-24 |  | 4200600909 | 180 | 2025-03-05 | 2025-04-11 |  | 2025-03-15 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CEMBRE | A14-M8 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -404 | 0
1593 | 1237790902100 | TERM REDONDO CRIMP 70MM2 D=10 | 1800120450 | 40 | 2025-02-24 |  | 4200600909 | 190 | 2025-03-05 | 2025-04-11 |  | 2025-03-15 | 30 | 8 | Liberado | 50 | 50 | 50 | 0 | 0 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CEMBRE | A14-M10 |  | 0 | 0 |  | 7218¦JA2582_1001 | 10 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -404 | 0
1594 | 1229599576000 | CBL EQ P/MOD SERV INTERFACE KVM | 1800120452 | 10 | 2025-02-24 |  | 4200600284 | 20 | 2025-02-28 | 2025-02-28 |  | 2025-03-15 | 135 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | ICOMPPLUS ELECTRONICS S.L | DELL COMPUTER | DMPUIQ-VMCHS-G01 |  | 0 | 0 |  | 7218¦JA2585_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -404 | 0
1595 | 3170408510000 | MOD ETH I350-T4 4P 10/100/1000MBPS 1GB N | 1800120452 | 20 | 2025-02-24 |  | 4200601405 | 10 | 2025-03-07 | 2025-03-07 |  | 2025-03-28 | 40 | 8 | Liberado | 14 | 14 | 14 | 0 | 0 | 0 | X | 0.00 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | W8X25AA |  | 0 | 0 |  | 7218¦JA2585_1001 | 21 | - |  | YES | 14 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -391 | 0
1596 | 3170302221301 | ROUTER INALAM AX3000 3GBPS WIFI6 DUAL | 1800120548 | 10 | 2025-02-25 |  | 4200601510 | 10 | 2025-03-07 | 2025-03-09 |  | 2025-03-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | TP-LINK TECHNOLOGIES | ARCHER AX58 |  | 2 | 2 |  | 7218¦JA2582_1001 | 20 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -392 | 0
1597 | 0973585293900 | THEODOLITE SUPPORT A320 | 1800120551 | 10 | 2025-02-25 |  | 4200600615 | 10 | 2025-03-03 | 2025-03-04 |  | 2025-04-15 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | TALLERES XUQUER, SL | INDRA SISTEMAS S.A. | 0973585293900 |  | 0 | 0 |  | 7218¦JA2590_1001 | 43 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 2 | 0% |  | -373 | 0
1598 | 0973585296700 | OPTICAL FILTER #1 | 1800120813 | 10 | 2025-03-03 |  | 4200602935 | 10 | 2025-03-18 | 2025-03-18 |  | 2025-07-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | PROTELECT TRANSFORMADOS,S.A.L. | INDRA SISTEMAS S.A. | 0973585296700 |  | 0 | 0 |  | 7218¦JA2590_1001 | 132 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -269 | 0
1599 | 0973585296800 | OPTICAL FILTER #2 | 1800120813 | 20 | 2025-03-03 |  | 4200602935 | 20 | 2025-03-18 | 2025-03-18 |  | 2025-07-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | PROTELECT TRANSFORMADOS,S.A.L. | INDRA SISTEMAS S.A. | 0973585296800 |  | 0 | 0 |  | 7218¦JA2590_1001 | 132 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -269 | 0
1600 | 0973585296900 | OPTICAL FILTER #3 | 1800120813 | 30 | 2025-03-03 |  | 4200602935 | 30 | 2025-03-18 | 2025-03-18 |  | 2025-07-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | PROTELECT TRANSFORMADOS,S.A.L. | INDRA SISTEMAS S.A. | 0973585296900 |  | 0 | 0 |  | 7218¦JA2590_1001 | 132 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -269 | 0
1601 | 1229508280004 | CBL EQ UTP RJ45-M/M 35FT NEGRO CAT6 LSZH | 1800120814 | 10 | 2025-03-03 |  | 4200602335 | 20 | 2025-03-13 | 2025-05-21 |  | 2025-03-27 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6K-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 14 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -392 | 0
1602 | 1229508280008 | CBL EQ UTP RJ45-M/M 15FT NEGRO CAT6 LSZH | 1800120814 | 20 | 2025-03-03 |  | 4200602355 | 10 | 2025-03-13 | 2025-03-14 |  | 2025-03-20 | 50 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6K-15-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 7 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -399 | 0
1603 | 1229508280202 | CBL EQ UTP RJ45-M/M 10FT VERDE CAT6 LSZH | 1800120814 | 30 | 2025-03-03 |  | 4200602335 | 30 | 2025-03-13 | 2025-05-21 |  | 2025-03-27 | 55 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | PACTECH | MM-C6N-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 14 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -392 | 0
1604 | 1229508280302 | CBL EQ UTP RJ45-M/M 10FT BLANC CAT6 LSZH | 1800120814 | 40 | 2025-03-03 |  | 4200601981 | 10 | 2025-03-11 | 2025-03-13 |  | 2025-03-20 | 45 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6W-10-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -399 | 0
1605 | 1229508280303 | CBL EQ UTP RJ45-M/M 20FT BLANC CAT6 LSZH | 1800120814 | 50 | 2025-03-03 |  | 4200603611 | 10 | 2025-03-21 | 2025-04-11 | BORR | 2025-04-15 | 75 | 8 |  | 3 | 3 | 0 | 3 | 0 | 0 |  | 90.00 |  | CARTRONIC MEMORY, S.A. | PACTECH | MM-C6W-20-28LSZH-F |  | 1 | 1 |  | 7218¦JA2585_1001 | 25 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 3 | 100% |  | -373 | 0
1606 | 1229508280303 | CBL EQ UTP RJ45-M/M 20FT BLANC CAT6 LSZH | 1800120814 | 50 | 2025-03-03 |  | 4200615654 | 20 | 2025-06-13 | 2025-06-13 |  | 2025-06-30 | 75 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6W-20-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 17 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -297 | 0
1607 | 1229508280304 | CBL EQ UTP RJ45-M/M 35FT BLANC CAT6 LSZH | 1800120814 | 60 | 2025-03-03 |  | 4200601981 | 20 | 2025-03-11 | 2025-03-13 |  | 2025-03-20 | 105 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6W-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -399 | 0
1608 | 1229508280504 | CBL EQ UTP RJ45-M/M 35FT AMAR CAT6 LSZH | 1800120814 | 70 | 2025-03-03 |  | 4200601981 | 30 | 2025-03-11 | 2025-03-13 |  | 2025-03-20 | 60 | 8 | Liberado | 4 | 4 | 4 | 0 | 4 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6Y-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 4 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -399 | 0
1609 | 1229508280704 | CBL EQ UTP RJ45-M/M 35FT NARAN CAT6 LSZH | 1800120814 | 80 | 2025-03-03 |  | 4200601981 | 40 | 2025-03-11 | 2025-03-13 |  | 2025-03-20 | 105 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PACTECH | MM-C6O-35-28LSZH-F |  | 0 | 0 |  | 7218¦JA2585_1001 | 9 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -399 | 0
1610 | 3210506270100 | ADAPT ETH USB-C-M/RJ45-H BLANC CBL=145MM | 1800120814 | 90 | 2025-03-03 |  | 4200601677 | 10 | 2025-03-10 | 2025-03-10 |  | 2025-03-20 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | STARTECH.COM LTD | US1GC30W |  | 0 | 0 |  | 7218¦JA2585_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -399 | 0
1611 | 7855500040000 | ESCALERA EMERGENCIA NYLON NEGRO L25FT | 1800120814 | 100 | 2025-03-03 |  | 4200602943 | 10 | 2025-03-18 | 2025-03-19 |  | 2025-03-28 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 0 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | ISOP LLC | 741718808327 |  | 0 | 0 |  | 7218¦JA2585_1001 | 10 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -391 | 0
1612 | 0973564310200 | SMK BOX CAJA CONEXIONES | 1800121209 | 10 | 2025-03-06 | BORR | 4200604020 | 10 | 2025-03-25 | 2025-03-26 | BORR | 2025-06-06 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 603.60 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0973564310200 |  | 0 | 0 |  | 7218¦JA2583_1001 | 73 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 3 | 100% |  | -321 | 0
1613 | 0973564320200 | SMK PLACA CONEXIONES | 1800121209 | 20 | 2025-03-06 | BORR | 4200604020 | 20 | 2025-03-25 | 2025-03-26 | BORR | 2025-06-06 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 302.80 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0973564320200 |  | 0 | 0 |  | 7218¦JA2583_1001 | 73 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 3 | 100% |  | -321 | 0
1614 | 0973580310200 | CARRIL DIN SMKBOX#1 | 1800121209 | 30 | 2025-03-06 | BORR | 4200604013 | 10 | 2025-03-25 | 2025-03-26 | BORR | 2025-07-11 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 69.70 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0973580310200 |  | 0 | 0 |  | 7218¦JA2583_1001 | 108 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 3 | 100% |  | -286 | 0
1615 | 0973581310200 | CARRIL DIN SMKBOX#2 | 1800121209 | 40 | 2025-03-06 | BORR | 4200604013 | 20 | 2025-03-25 | 2025-03-26 | BORR | 2025-07-11 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 67.20 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0973581310200 |  | 0 | 0 |  | 7218¦JA2583_1001 | 108 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 3 | 100% |  | -286 | 0
1616 | 1243602470000 | COMPRESOR EKOM DK50 2V/50S/M C/ACC S/OF | 1800121210 | 10 | 2025-03-06 |  | 4200602560 | 10 | 2025-03-14 | 2025-07-23 |  | 2025-04-11 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | HIDROHENARES, S.L. | HIDROHENARES | COMPRESOR EKOM DK50 2V/50S/M/100119 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -377 | 0
1617 | 7275500320000 | MANOMETRO 0-10BAR D40MM 1/8" POSTERIOR | 1800121210 | 20 | 2025-03-06 |  | 4200602560 | 20 | 2025-03-14 | 2025-07-23 |  | 2025-04-11 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | HIDROHENARES, S.L. | HIDROHENARES | M-40-010 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -377 | 0
1618 | 1705505480000 | PANEL FRONTAL 3U 84HP 426.4X128.4X2.5MM | 1800121211 | 30 | 2025-03-06 |  | 4200603733 | 40 | 2025-03-21 | 2025-03-25 |  | 2025-04-21 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 24563-096 |  | 0 | 0 |  | 7218¦JA2582_1001 | 31 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -367 | 0
1619 | 3170411820100 | MOD POE INYECTOR 2P RJ45 100-240V 1A 30W | 1800121211 | 40 | 2025-03-06 |  | 4200601669 | 10 | 2025-03-10 | 2025-03-10 |  | 2025-03-21 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ESPRINET IBERICA, S.L.U. | TP-LINK TECHNOLOGIES | TL-POE160S |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -398 | 0
1620 | 1231024321001 | TUBO TERMORETRACTIL D=3.2MM PVC NEGRO | 1800121212 | 10 | 2025-03-06 |  | 4200603155 | 10 | 2025-03-19 | 2025-03-25 |  | 2025-03-25 | 60 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AUDIOBUS, S.L. | AUDIOBUS S.L | ZZ4400 |  | 0 | 0 |  | 7218¦JA2590_1001 | 6 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -394 | 0
1621 | 1214301130022 | CNC CIR 19-11S/H RCPT RECT AL ZN/NI R-N | 1800122179 | 10 | 2025-03-23 |  | 4200604898 | 470 | 2025-03-31 | 2025-04-07 |  | 2025-04-09 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZF11SN |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
1622 | 1214301130022 | CNC CIR 19-11S/H RCPT RECT AL ZN/NI R-N | 1800122179 | 10 | 2025-03-23 |  | 4200605021 | 10 | 2025-03-31 |  | BORR | 2025-04-09 | 40 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 46.08 |  | SUMINISTROS CONECTORES PROF.,SA. | MILITARY SPECS. | D38999/20ZF11SN |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 3 | 100% |  | -379 | 0
1623 | 1220115702003 | CBL FLEX 1X70MM2 750V H07Z1-K AM/VE ROHS | 1800122179 | 20 | 2025-03-23 |  | 4200604135 | 60 | 2025-03-25 | 2025-04-09 |  | 2025-04-09 | 40 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | MIGUELEZ | 82040100700-A/V |  | 0 | 0 |  | 7218¦JA2582_1001 | 15 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
1624 | 1501216016001 | TOR ALO CRUC M6X16 INOX DIN7985/ISO7045 | 1800122179 | 30 | 2025-03-23 |  | 4200605018 | 110 | 2025-03-31 | 2025-04-03 |  | 2025-04-28 | 60 | 8 | Liberado | 100 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN7985-M6X16-A2-70-H |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -360 | 0
1625 | 1531215000001 | TUERCA EXA SEG C/ARA PLST M5 INOX DIN985 | 1800122179 | 40 | 2025-03-23 |  | 4200605018 | 120 | 2025-03-31 | 2025-04-03 |  | 2025-04-28 | 40 | 8 | Liberado | 100 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN985-M5-A2 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -360 | 0
1626 | 1540116000001 | ARA PL P/M6 INOX DIN125A/ISO7089 | 1800122179 | 50 | 2025-03-23 |  | 4200605018 | 130 | 2025-03-31 | 2025-04-03 |  | 2025-04-28 | 60 | 8 | Liberado | 100 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN125-A6,4-A2 |  | 0 | 0 |  | 7218¦JA2582_1001 | 28 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -360 | 0
1627 | 1510436013001 | TOR ALO CRUZ 0.164-32UNC-2AX0.500 CRES P | 1800122200 | 10 | 2025-03-23 |  | 4200607162 | 20 | 2025-04-11 | 2025-04-11 |  | 2025-04-22 | 60 | 8 | Liberado | 2 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | EUROPEAN AGENCY MENK | MILITARY STANDARDS | MS51957-45 |  | 0 | 0 |  | 7218¦JA2583_1001 | 11 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -366 | 0
1628 | 1229598250100 | CBL EQ DP 1.4-M/M 8K DP PRO P/150 L45.7M | 1800122201 | 10 | 2025-03-23 |  | 4200604155 | 20 | 2025-03-25 | 2025-03-28 |  | 2025-04-09 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | PENTATEL COMUNICACIONES, S.L. | EXTRON ELECTRONICS | 26-727-150 |  | 0 | 0 |  | 7218¦JA2585_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
1629 | 1263011300800 | F.A. VE=230V VS=12V 1.5A JACK-2.1MM ROHS | 1800122201 | 20 | 2025-03-23 |  | 4200604017 | 10 | 2025-03-25 | 2025-03-25 |  | 2025-04-09 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | PT18-1812-UN |  | 0 | 0 |  | 7218¦JA2585_1001 | 15 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
1630 | 1282001480200 | SENSOR TEMP 1U RACK 2XRJ11 | 1800122201 | 30 | 2025-03-23 |  | 4200604017 | 20 | 2025-03-25 | 2025-03-25 |  | 2025-04-09 | 30 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | CARTRONIC MEMORY, S.A. | HW GROUP | 600329 |  | 0 | 0 |  | 7218¦JA2585_1001 | 15 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
1631 | 1285000449000 | BASE STD SUPERFICIE P/DET NFX PC/ABS BL | 1800122201 | 40 | 2025-03-23 |  | 4200604072 | 10 | 2025-03-25 | 2025-03-25 |  | 2025-04-09 | 40 | 8 | Liberado | 2 | 2 | 2 | 0 | 2 | 0 | X | 0.00 |  | BY DEMES, S.L. | NOTIFIER | B501AP |  | 0 | 0 |  | 7218¦JA2585_1001 | 15 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -379 | 0
1632 | 1229599576000 | CBL EQ P/MOD SERV INTERFACE KVM | 1800122202 | 10 | 2025-03-23 |  | 4200603970 | 10 | 2025-03-25 | 2025-03-26 |  | 2025-05-16 | 135 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | DELL COMPUTER, S.A. | DELL COMPUTER | DMPUIQ-VMCHS-G01 |  | 1 | 1 |  | 7218¦JA2585_1001 | 52 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 3 | 0% |  | -342 | 0
1633 | 1390701502100 | PANEL 22VU ETOPS AUTOMATICO IAE | 1800122962 | 10 | 2025-04-03 |  | 4200605815 | 10 | 2025-04-04 | 2025-04-09 |  | 2025-06-23 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ50204-01 |  | 0 | 0 |  | 7218¦JA2583_1001 | 80 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -304 | 0
1634 | 0973585295900 | PLACA PUNTEROS 60 | 1800123068 | 10 | 2025-04-07 |  | 4200606884 | 10 | 2025-04-10 | 2025-04-10 |  | 2025-06-16 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MONTAJES CEBIS SL | INDRA SISTEMAS S.A. | 0973585295900 |  | 0 | 0 |  | 7218¦JA2590_1001 | 67 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -311 | 0
1635 | 0973585296100 | PLACA PUNTEROS 50 | 1800123068 | 20 | 2025-04-07 |  | 4200606884 | 20 | 2025-04-10 | 2025-04-10 |  | 2025-06-16 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | MONTAJES CEBIS SL | INDRA SISTEMAS S.A. | 0973585296100 |  | 0 | 0 |  | 7218¦JA2590_1001 | 67 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -311 | 0
1636 | 1500311008001 | TOR CIL ALLEN M3X8 INOX DIN912/ISO4762 | 1800123069 | 10 | 2025-04-07 |  | 4200607688 | 30 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 30 | 8 | Liberado | 2 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN912-M3X8-A2-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1637 | 1500313016001 | TOR CIL ALLEN M4X16 INOX DIN912/ISO4762 | 1800123069 | 20 | 2025-04-07 |  | 4200607688 | 40 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 40 | 8 | Liberado | 4 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | ISO | ISO4762-M4X16-A2-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1638 | 1500315016001 | TORNILLO ALLEN M5X16 INOX DIN912 | 1800123069 | 30 | 2025-04-07 |  | 4200607688 | 50 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 30 | 8 | Liberado | 12 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN912-M5X16-A2-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1639 | 1501311012002 | TORNILLO AV ALLEN M3X12 A4-70 DIN7991 | 1800123069 | 40 | 2025-04-07 |  | 4200607688 | 230 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 40 | 8 | Liberado | 4 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN7991-M3X12-A4-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1640 | 1501313008001 | TOR AV ALLEN M4X8 INOX DIN7991 | 1800123069 | 50 | 2025-04-07 |  | 4200607688 | 240 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 40 | 8 | Liberado | 3 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN7991-M4X8-A2-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1641 | 1521016999001.LO | VARILLA ROSC M6X1000MM INOX DIN975 | 1800123069 | 60 | 2025-04-07 |  | 4200607688 | 250 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 40 | 8 | Liberado | 1 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN975-M6X1000-A2 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1642 | 1530116000002 | TUERCA EXA M6 INOX DIN934/ISO4032 | 1800123069 | 70 | 2025-04-07 |  | 4200607688 | 270 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 40 | 8 | Liberado | 8 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN934-M6-A4-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1643 | 1530120000002 | TUERCA EXA M12 INOX DIN934/ISO4032 | 1800123069 | 80 | 2025-04-07 |  | 4200607688 | 280 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 70 | 8 | Liberado | 8 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN934-M12-A4-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1644 | 1540116000003 | ARA PLANA P/M6 INOX ISO7089/DIN125A | 1800123069 | 90 | 2025-04-07 |  | 4200608348 | 30 | 2025-04-25 | 2025-04-25 | BORR | 2025-07-14 | 60 | 8 | Liberado | 8 | 100 | 0 | 100 | 0 | 0 |  | 350.00 |  | TCX MICRO, S.L.U | DIN | DIN125-A6-A4-80 |  | 0 | 0 |  | 7218¦JA2590_1001 | 80 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 4 | 100% |  | -283 | 0
1645 | 1540116000003 | ARA PLANA P/M6 INOX ISO7089/DIN125A | 1800123069 | 90 | 2025-04-07 |  | 4200608334 | 20 | 2025-04-25 | 2025-04-25 |  | 2025-04-30 | 60 | 8 | Liberado | 8 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | ABACO SUYTEC, S.A.U. | DIN | DIN125-A6-A4-80 |  | 0 | 0 |  | 7218¦JA2590_1001 | 5 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -358 | 0
1646 | 1540211000011 | ARA GROWER P/M3 INOX OX NE DIN127B | 1800123069 | 100 | 2025-04-07 |  | 4200607688 | 370 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 60 | 8 | Liberado | 4 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN127-B3-A2 OX NEGRO |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1647 | 1540216000102 | ARA GROWER P/M6 INOX A4 DIN127 | 1800123069 | 110 | 2025-04-07 |  | 4200607688 | 380 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 60 | 8 | Liberado | 8 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN127-M6-A4-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1648 | 1540220000102 | ARA GROWER M12 DIN127 INOX A4-70 | 1800123069 | 120 | 2025-04-07 |  | 4200607688 | 390 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 105 | 8 | Liberado | 8 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN127-M12-INOX-A4-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1649 | 1541320000002 | ARA PLANA M12 A4-70 DIN 9021 | 1800123069 | 130 | 2025-04-07 |  | 4200607688 | 420 | 2025-04-21 | 2025-04-23 |  | 2025-05-05 | 45 | 8 | Liberado | 8 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN9021-M12-A4-70 |  | 0 | 0 |  | 7218¦JA2590_1001 | 14 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -353 | 0
1650 | 1390700725500 | GEAR BOX A320 | 1800123318 | 10 | 2025-04-10 |  | 4200610958 | 10 | 2025-05-15 | 2025-05-15 |  | 2025-05-19 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | AMF MADRID SL | AIRBUS INDUSTRIE | D3231007000100 |  | 0 | 0 |  | 7218¦JA2583_1001 | 4 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -339 | 0
1651 | 1232525308000 | CINT ADH ESPUM ACR VHB 4930P 30MM 33M BL | 1800123672 | 10 | 2025-04-23 |  | 4200610619 | 30 | 2025-05-13 | 2025-05-14 |  | 2025-07-11 | 40 | 8 | Liberado | 3 | 3 | 3 | 0 | 3 | 0 | X | 0.00 |  | FERRETERIA FERAYU SL | 3M | 4930P/30MM |  | 1 | 1 |  | 7218¦JA2578_1001 | 59 | - |  | YES | 3 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -286 | 0
1652 | 1221415352500 | CBL APANT 4G35MM2 600V XLPE RC4Z1-K VERD | 1800123673 | 10 | 2025-04-23 |  | 4200608709 | 70 | 2025-04-29 | 2025-11-04 |  | 2025-05-10 | 40 | 8 | Liberado | 15 | 15 | 15 | 0 | 15 | 0 | X | 0.00 |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | CERVI | 31814205 |  | 0 | 0 |  | 7218¦JA2582_1001 | 11 | - |  | YES | 15 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -348 | 0
1653 | 1231024570900 | TAPA TERMO 4:1 POLEO 5,72-1,27MM L=30MM | 1800123673 | 20 | 2025-04-23 |  | 4200609570 | 60 | 2025-05-06 | 2025-05-09 |  | 2025-05-15 | 60 | 8 | Liberado | 500 | 500 | 500 | 0 | 500 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | FARNELL ELECTR | 134-764 |  | 0 | 0 |  | 7218¦JA2582_1001 | 9 | - |  | YES | 500 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -343 | 0
1654 | 1237700120400 | TERMINAL AISL REDON AWG12-10 3.7MM AMAR | 1800123673 | 30 | 2025-04-23 |  | 4200609226 | 10 | 2025-05-05 | 2025-05-05 |  | 2025-08-08 | 110 | 8 | Liberado | 50 | 50 | 50 | 0 | 50 | 0 | X | 0.00 |  | OMNIAELECTRONICS, S.L. | KS TERMINALS | RNYD5-3.7 |  | 1 | 0 |  | 7218¦JA2582_1001 | 95 | - |  | YES | 50 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -258 | 0
1655 | 7883000120600 | PUNTO TOMA TIERRA BROCHE 25X35MM | 1800123673 | 40 | 2025-04-23 |  | 4200610017 | 10 | 2025-05-08 | 2025-05-08 |  | 2025-06-10 | 40 | 8 | Liberado | 6 | 100 | 200 | 0 | 100 | 100 | X | 0.00 |  | EUROASICA,S.A. | EUROASICA S.A | CON-9765 |  | 2 | 0 |  | 7218¦JA2582_1001 | 33 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -317 | 0
1656 | 1202090240000 | PIN CNC SUB-D M 20-24AWG (ROLLO 400UD) | 1800123674 | 10 | 2025-04-23 |  | 4200609797 | 10 | 2025-05-07 | 2025-05-09 |  | 2025-05-10 | 56 | 8 | Liberado | 100 | 400 | 400 | 0 | 400 | 0 | X | 0.00 |  | SUMINISTROS CONECTORES PROF.,SA. | AMPHENOL CORP | 17RRD1M11400 |  | 0 | 0 |  | 7218¦JA2583_1001 | 3 | - |  | YES | 400 |  |  | 0 | X | 100% |  |  |  |  | 4 | 0% |  | -348 | 0
1657 | 1060330100001 | LED AMARILLO 8X3MM 2V IP67 | 1800124012 | 10 | 2025-05-06 |  | 4200611470 | 10 | 2025-05-19 | 2025-05-19 |  | 2026-01-07 | 40 | 8 | Liberado | 10 | 10 | 20 | 0 | 10 | 10 | X | 0.00 |  | FARNELL COMPONENTS, S.L. | APEM | Q8P1CXXY02E |  | 1 | 0 |  | 7218¦JA2583_1001 | 233 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -106 | 0
1658 | 0973588300100 | CB INTLCK OPEN SUPPORT | 1800124162 | 10 | 2025-05-06 |  | 4200614815 | 30 | 2025-06-09 | 2025-06-09 |  | 2025-10-14 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | MARCOA, S.L. | INDRA SISTEMAS S.A. | 0973588300100 |  | 1 | 0 |  | 7218¦JA2583_1001 | 127 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -191 | 0
1659 | 0973588300200 | CB INTLCK CLOSED SUPPORT PLATE | 1800124162 | 20 | 2025-05-06 |  | 4200615832 | 10 | 2025-06-16 | 2025-06-30 |  | 2025-11-08 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0973588300200 |  | 2 | 1 |  | 7218¦JA2583_1001 | 145 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -166 | 0
1660 | 1500311008003 | TORNILLO ALLEN M3x8 DIN 912/ISO4762 | 1800125058 | 10 | 2025-05-21 |  | 4200613304 | 70 | 2025-05-29 | 2025-06-02 |  | 2025-06-30 | 65 | 8 | Liberado | 4 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN912-M3X8-A4-80 |  | 1 | 1 |  | 7218¦JA2590_1001 | 32 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -297 | 0
1661 | 1500313008003 | TOR ALLEN M4X8 INOX DIN912 | 1800125058 | 20 | 2025-05-21 |  | 4200613852 | 10 | 2025-06-03 | 2025-06-03 |  | 2025-07-01 | 60 | 8 | Liberado | 4 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN912-M4X8-A4-80 |  | 0 | 0 |  | 7218¦JA2590_1001 | 28 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -296 | 0
1662 | 1500313010003 | TOR ALLEN M4X10 AC INOX A4-80 DIN912 | 1800125058 | 30 | 2025-05-21 |  | 4200613304 | 100 | 2025-05-29 | 2025-06-02 |  | 2025-06-30 | 50 | 8 | Liberado | 8 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN912-M4X10-A4-80 |  | 1 | 1 |  | 7218¦JA2590_1001 | 32 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -297 | 0
1663 | 1540213000015 | ARA GROWER P/M4 PAV DIN127 | 1800125058 | 50 | 2025-05-21 |  | 4200613304 | 620 | 2025-05-29 | 2025-06-02 |  | 2025-05-30 | 60 | 8 | Liberado | 8 | 1000 | 1000 | 0 | 1000 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN127-M4-PAVONADA |  | 0 | 0 |  | 7218¦JA2590_1001 | 1 | - |  | YES | 1000 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -328 | 0
1664 | 1705500920200 | PANEL CIEGO 3U RAL 7035 | 1800125059 | 10 | 2025-05-21 |  | 4200613768 | 20 | 2025-06-02 | 2025-06-10 |  | 2025-06-30 | 35 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 30118-302 |  | 0 | 0 |  | 7218¦JA2583_1001 | 28 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -297 | 0
1665 | 0972880000000 | IDENTIFICATION LABEL | 1800125070 | 10 | 2025-05-21 |  | 4200616259 | 50 | 2025-06-18 | 2025-06-18 |  | 2025-11-21 | 30 | 8 | Liberado | 10 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | MARKABLE SOLUTIONS, S.L. | INDRA SISTEMAS S.A. | 0972880000000 |  | 2 | 0 |  | 7218¦JA2583_1001 | 156 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -153 | 0
1666 | 0972888472500 | AVIONICS PLATE | 1800125070 | 20 | 2025-05-21 |  | 4200615824 | 20 | 2025-06-16 | 2025-06-18 |  | 2026-01-30 | 90 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INDUSTRIAS BALMES, S.A. | INDRA SISTEMAS S.A. | 0972888472500 |  | 4 | 2 |  | 7218¦JA2583_1001 | 228 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -83 | 0
1667 | 0973585295800 | TELA INFERIOR MYLAR | 1800125129 | 10 | 2025-05-23 |  | 4200615314 | 20 | 2025-06-12 | 2025-06-27 |  | 2025-06-30 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ANTONIO RAMIREZ, S.L. | INDRA SISTEMAS S.A. | 0973585295800 |  | 2 | 0 |  | 7218¦JA2590_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -297 | 0
1668 | 0973585296000 | TELA SUPERIOR MYLAR | 1800125129 | 20 | 45800 |  | 4200615314 | 10 | 2025-06-12 | 2025-06-27 |  | 2025-06-30 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ANTONIO RAMIREZ, S.L. | INDRA SISTEMAS S.A. | 0973585296000 |  | 2 | 0 |  | 7218¦JA2590_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -297 | 0
1669 | 1000146811030 | RST PELMET 6K81 1% 1/8W RLR05C6811FR | 1800125130 | 10 | 45800 |  | 4200613274 | 350 | 2025-05-29 | 2025-05-29 |  | 2025-06-09 | 150 | 8 | Liberado | 20 | 20 | 20 | 0 | 20 | 0 | X | 0.00 |  | TCX MICRO, S.L.U | MILITARY SPECS. | RLR05C6811FR |  | 1 | 0 |  | 7218¦JA2583_1001 | 11 | - |  | YES | 20 |  |  | 0 | X | 100% |  |  |  |  | 5 | 0% |  | -318 | 0
1670 | 0973585294200 | TELA DERECHA MYLAR | 1800125602 | 10 | 45811 |  | 4200615314 | 40 | 2025-06-12 | 2025-06-27 |  | 2025-06-30 | 0 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ANTONIO RAMIREZ, S.L. | INDRA SISTEMAS S.A. | 0973585294200 |  | 1 | 0 |  | 7218¦JA2590_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -297 | 0
1671 | 0973585296400 | TELA IZQUIERDA MYLAR | 1800125602 | 20 | 2025-06-03 |  | 4200615314 | 30 | 2025-06-12 | 2025-06-27 |  | 2025-06-30 | 0 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | ANTONIO RAMIREZ, S.L. | INDRA SISTEMAS S.A. | 0973585296400 |  | 1 | 0 |  | 7218¦JA2590_1001 | 18 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -297 | 0
1672 | 1221415352500 | CBL APANT 4G35MM2 600V XLPE RC4Z1-K VERD | 1800125603 | 10 | 2025-06-03 |  | 4200618266 | 30 | 2025-07-03 | 2025-12-11 |  | 2025-07-09 | 40 | 8 | Liberado | 25 | 25 | 25 | 0 | 25 | 0 | X | 0.00 |  | CERVI, S.L. | CERVI | 31814205 |  | 0 | 0 |  | 7218¦JA2582_1001 | 6 | - |  | YES | 25 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -288 | 0
1673 | 2820120500141 | PLANCHA E=5MM NEOPRENO NEGRO 40-50 SH | 1800125603 | 20 | 45811 |  | 4200616342 | 10 | 2025-06-18 | 2025-06-19 |  | 2025-06-25 | 30 | 8 | Liberado | 1 | 10 | 10 | 0 | 10 | 0 | X | 0.00 |  | Technipol Suministros, S.L. | OTROS FABRICANTES | NEOPRENO NEGRO/E=5MM 40-50 SH |  | 0 | 0 |  | 7218¦JA2582_1001 | 7 | - |  | YES | 10 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -302 | 0
1674 | 3210506760000 | DONGLE SENTINEL HL MAX-MICRO S/CONDUCTOR | 1800126496 | 10 | 45833 |  | 4200617886 | 10 | 2025-07-01 | 2025-07-03 |  | 2025-07-08 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | THALES AVS FRANCE SAS | GEMALTO NV | 942-001422-001 |  | 0 | 0 |  | 7218¦JA2583_1001 | 7 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 6 | 0% |  | -289 | 0
1675 | 1501215014001 | TOR ALOM CRUC M5X14 INOX DIN7985 | 1800127076 | 10 | 45847 |  | 4200620834 | 10 | 2025-07-22 | 2025-07-22 |  | 2025-07-30 | 60 | 8 | Liberado | 2 | 200 | 200 | 0 | 200 | 0 | X | 0.00 |  | ALMACENES DELCA, S.A. | DIN | DIN7985-M5X14-A2-70 |  | 0 | 0 |  | 7218¦JA2583_1001 | 8 | - |  | YES | 200 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -267 | 0
1676 | 1538013015001 | TUR INSERT ANTI-ROT M4 L=15MM INOX | 1800127076 | 20 | 45847 |  | 4200623166 | 10 | 2025-08-08 | 2025-08-11 |  | 2025-09-30 | 100 | 8 | Liberado | 6 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | AMF MADRID SL | SIMAF | 4 TFB 40 X |  | 1 | 1 |  | 7218¦JA2583_1001 | 53 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
1677 | 1538015011001 | TUR INSERT AV M5 L=11.5MM INOX AISI-303 | 1800127076 | 30 | 45847 |  | 4200623166 | 20 | 2025-08-08 | 2025-08-11 |  | 2025-09-30 | 60 | 8 | Liberado | 2 | 100 | 100 | 0 | 100 | 0 | X | 0.00 |  | AMF MADRID SL | SERBLOC | 5 TF 30 X |  | 1 | 1 |  | 7218¦JA2583_1001 | 53 | - |  | YES | 100 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -205 | 0
1678 | 7883000582700 | ALFOMBRA SEGURIDAD RKP 1890X750MM CBL=2/ | 1800127761 | 10 | 2025-07-24 |  | 4200621836 | 10 | 2025-07-30 | 2025-07-30 |  | 2025-08-25 | 50 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SAFEWORK, S.L. | SAFEWORK | RKP TBC 9/1890X750MM |  | 2 | 2 |  | 7218¦JA2583_1001 | 26 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 7 | 0% |  | -241 | 0
1679 | 1750101350000 | TUBERIA FLEX DE=90MM DS=98MM -10/60C PVC | 1800128117 | 10 | 45873 |  | 4200625496 | 10 | 2025-09-03 | 2025-09-05 |  | 2025-09-23 | 60 | 8 | Liberado | 30 | 30 | 30 | 0 | 30 | 0 | X | 0.00 |  | FERRETERIA FERAYU SL | URARTU | 122090 |  | 0 | 0 |  | 7218¦JA2582_1001 | 20 | - |  | YES | 30 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -212 | 0
1680 | 0973588330200 | DOOR INTERNAL FRAME | 1800128532 | 10 | 45889 |  | 4200629548 | 50 | 2025-10-02 | 2025-10-15 |  | 2025-11-20 | 40 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 289.60 |  | PREFIMETAL, S.A. | INDRA SISTEMAS S.A. | 0973588330200 |  | 0 | 0 |  | 7218¦JA2582_1001 | 49 | - | [5 empty] | 1 |  | 0% | 4200629548 |  |  |  | 8 | 100% |  | -154 | 0
1681 | 0973588330300 | DOOR EXTERNAL FRAME | 1800128532 | 20 | 45889 |  | 4200629548 | 60 | 2025-10-02 | 2025-10-15 |  | 2025-11-20 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | PREFIMETAL, S.A. | INDRA SISTEMAS S.A. | 0973588330300 |  | 0 | 0 |  | 7218¦JA2582_1001 | 49 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 8 | 0% |  | -154 | 0
1682 | 1390701500700 | MOD MCDU SEQ27901 C/DISPLAY | 1800128840 | 10 | 45898 |  | 4200625222 | 10 | 2025-09-02 | 2025-09-02 |  | 2026-04-18 | 245 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 9315.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ27901 |  | 1 | 1 |  | 7218¦JA2591_1001 | 228 | - | [5 empty] | 0 |  | 0% | 4200625222 |  |  |  | 8 | 100% |  | -5 | 0
1683 | 1390704693802 | DISPLAY UNITS AIRBUS DU S/OF | 1800128840 | 20 | 45898 |  | 4200625222 | 20 | 2025-09-02 | 2025-09-02 |  | 2026-04-18 | 125 | 8 | Liberado | 2 | 2 | 0 | 2 | 0 | 0 |  | 12092.26 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-SEQ47701 |  | 1 | 1 |  | 7218¦JA2591_1001 | 228 | - | [5 empty] | 0 |  | 0% | 4200625222 |  |  |  | 8 | 100% |  | -5 | 0
1684 | 1705502500000 | PANEL FRONTAL 19" 1U ALUMINIO 3MM 43,6X3 | 1800128869 | 10 | 45902 |  | 4200626547 | 20 | 2025-09-11 | 2025-09-19 |  | 2025-10-02 | 35 | 8 | Liberado | 5 | 5 | 5 | 0 | 5 | 0 | X | 0.00 |  | CENVALSA, S.L. | SCHROFF | 30118-948 |  | 0 | 0 |  | 7218¦JA2593_1001 | 21 | - |  | YES | 5 |  |  | 0 | X | 100% |  |  |  |  | 9 | 0% |  | -203 | 0
1685 | 1250101570000 | ALTAVOZ SUBWOOFER 170W 20-200HZ SUB/HPF | 1800129554 | 10 | 45919 | BORR | 4200630060 | 10 | 2025-10-06 | 2025-10-08 | BORR | 2025-11-24 | 85 | 8 |  | 1 | 1 | 0 | 1 | 0 | 0 |  | 1292.86 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PRESONUS AUDIO | TEMBLOR T10 |  | 1 | 0 |  | 7218¦JA2583_1001 | 49 | - | [5 empty] | 0 |  | 0% |  |  |  |  | 9 | 100% |  | -150 | 0
1686 | 7883000582700 | ALFOMBRA SEGURIDAD RKP 1890X750MM CBL=2/ | 1800130856 | 10 | 2025-10-16 |  | 4200639845 | 10 | 2025-12-05 | 2025-12-10 |  | 2026-01-05 | 50 | 8 | Liberado | 2 | 2 | 2 | 0 | 0 | 0 | X | 0.00 |  | SAFEWORK, S.L. | SAFEWORK | RKP TBC 9/1890X750MM |  | 0 | 0 |  | 7218¦JA2583_1001 | 31 | - |  | YES | 2 |  |  | 0 | X | 100% |  |  |  |  | 10 | 0% |  | -108 | 0
1687 | 3210402620000 | ALTAVOZ SUBWOOFER 130W ERIS PRO SUB 10 | 1800131893 | 10 | 2025-11-06 |  | 4200636792 | 10 | 2025-11-18 | 2025-11-18 |  | 2025-11-27 | 40 | 8 | Liberado | 1 | 1 | 1 | 0 | 1 | 0 | X | 0.00 |  | INFORMATICA CALCULO Y TECNICA, S.A. | PRESONUS | 2777504132 |  | 0 | 0 |  | 7218¦JA2583_1001 | 9 | - |  | YES | 1 |  |  | 0 | X | 100% |  |  |  |  | 11 | 0% |  | -147 | 0
1688 | 0918530000000 | CANIF-DIO32_TIPO11B | 1800134174 | 10 | 46013 |  |  | 0 |  |  |  |  | 50 | 8 |  | 15 | 0 | 0 | 0 | 0 | 0 |  | 0.00 | [5 empty] | 0 | 0 |  | 7218¦JA2581_1001 | #VALUE! | - | [5 empty] | 0 |  | 0% |  |  |  |  | 12 | 100% |  | #VALUE! | #VALUE! | #VALUE! | X
1689 | 0918630000000 | CANIF-DIO32 TIPO11A | 1800134189 | 10 | 2025-12-22 |  |  | 0 |  |  |  |  | 55 | 8 |  | 15 | 0 | 0 | 0 | 0 | 0 |  | 0.00 | [5 empty] | 0 | 0 |  | 7218¦JA2581_1001 | #VALUE! | - | [5 empty] | 0 |  | 0% |  |  |  |  | 12 | 100% |  | #VALUE! | #VALUE! | #VALUE! | X
1690 | 1390705900595 | MOD ALTERNATE SWITCH | 1800134189 | 20 | 2025-12-22 |  | 4200645497 | 10 | 2026-01-19 | 2026-01-19 |  | 2026-05-16 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 875.00 |  | SUMINISTROS, FRESADOS Y GRABADOS | GRABYSUR | GR-ABS26022 |  | 0 | 0 |  | 7218¦JA2581_1001 | 117 | - | [5 empty] | 0 |  | 0% | 4200645497 |  |  |  | 12 | 100% |  | 23 | 0
1691 | 0918625900400 | I/F CAN 21A-21S1 | 1800134280 | 10 | 2026-01-09 | BLOQ |  | 0 |  |  |  |  | 0 | 3 |  | 10 | 0 | 0 | 0 | 0 | 0 |  | 0.00 | [5 empty] | 0 | 0 |  | 7218¦JA2581_1001 | #VALUE! | - | [5 empty] | 0 |  | 0% |  |  | 1 |  | 1 | 100% |  | #VALUE! | #VALUE! | #VALUE! | X
1692 | 3010201822302 | WS Z4 RACK G5 2X 675W T1000 RCTO S/OF | 1800134780 | 10 | 2026-01-19 |  | 4200646214 | 10 | 2026-01-22 | 2026-01-27 |  | 2026-03-19 | 40 | 8 | Liberado | 3 | 1 | 0 | 1 | 0 | 0 |  | 3756.31 |  | HP PRINTING AND COMPUTING SOLUTIONS | HEWLETT PACKARD | 52258775/7178862 | X | 0 | 0 |  | 7218¦JA2581_1001 | 56 | - | [5 empty] | 0 |  | 0% | 4200646214 |  |  |  | 1 | 100% |  | -35 | 0 |  | X
Formulas:
OTD Qty = IF(AND([Received]="X",[Delivery Date]<=AJ2),[Ctd. Recepcionada],"")

## Lista de Compra (banco Pruebas) (hidden)
Solped FMS | INDRA CODE | Recodificado | DESCRIPTION | PANEL | DATE | NSN | P/N MFR | MFR | QTY | DEVICE | GPI I&T | GPI PRD | PRIORIDAD | SYSTEM/EQUIPMENT | TYPE | RESPONSABLE I&T | Comentario | Orden FMS | Contraseña FMS | Orden FTD | Contraseña FTD | Orden Repuestos | Contraseña Repuestos | Orden DBF | Contraseña DBF | Orden SAS | Contraseña SAS | Solped FMS
1800105189/20 | 1229508280002 |  | CBL EQ UTP RJ45-M/M 10FT NEGRO CAT6 LSZH |  | 2024-03-06 |  | MM-C6K-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/20
1800105189/30 | 1229508280102 |  | CBL EQ UTP RJ45-M/M 10FT AZUL CAT6 LSZH |  | 2024-03-06 |  | MM-C6B-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/30
1800105189/40 | 1229508280202 |  | CBL EQ UTP RJ45-M/M 10FT VERDE CAT6 LSZH |  | 2024-03-06 |  | MM-C6N-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/40
1800105189/50 | 1229508280302 |  | CBL EQ UTP RJ45-M/M 10FT BLANC CAT6 LSZH |  | 2024-03-06 |  | MM-C6W-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/50
1800105189/60 | 1229508280402 |  | CBL EQ UTP RJ45-M/M 10FT ROJO CAT6 LSZH |  | 2024-03-06 |  | MM-C6R-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/60
1800105189/70 | 1229508280502 |  | CBL EQ UTP RJ45-M/M 10FT AMAR CAT6 LSZH |  | 2024-03-06 |  | MM-C6Y-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/70
1800105189/80 | 1229508280602 |  | CBL EQ UTP RJ45-M/M 10FT MORAD CAT6 LSZH |  | 2024-03-06 |  | MM-C6C-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/80
1800105189/90 | 1229508280702 |  | CBL EQ UTP RJ45-M/M 10FT NARAN CAT6 LSZH |  | 2024-03-06 |  | MM-C6O-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/90
1800105189/130 | 1229598281100 |  | CBL EQ RJ45-M/M CAT7 S/FTP LSZH AZL 10FT |  | 2024-03-06 |  | MM-S7B-10-28LSZH-F | PACTECH | 20 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE ETHERNET | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/130
1800105189/120 | 1229593631000 |  | CBL EQUIP EXTENS USB 2.0 L=8M |  | 2024-03-06 |  | 42780 | LINDY | 10 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | EXTENSOR USB | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/120
1800105189/210 | 3210106240000 |  | CBL EQUIP USB 2.0 A 1M/4H C/HUB 12M |  | 2024-03-06 |  | 42783 | LINDY | 10 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | EXTENSOR USB | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/210
1800105189/230 | 3210574070700 |  | CBL DVI-D DUAL LINK 15M CNC= M/M CBL=AWG |  | 2024-03-06 |  | HE46 | CABLEMATIC | 10 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE VIDEO | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/230
1800105189/200 | 3170110370000 |  | SWITCH PROSAFE 24P 10/100/1000BASE-T RJ4 |  | 2024-03-06 |  | GS724T-400EUS | NETGEAR | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | SWITCH LAN | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/200
1800105189/190 | 3170101514700 |  | SWICHT 28 PORT 10-GB PRO 4 SFP+ |  | 2024-03-06 |  | XS728T-100NES | NETGEAR | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | SWITCH LAN | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/190
1800105189/220 | 3210107070200 |  | CBL EQ TWINAX DAC SFP+/SFP+ 10G PVC L=1M |  | 2024-03-06 |  | SFPCMM1M | STARTECH | 2 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE SFP+ | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/220
1800105582/20 | 3060399700000 | 3030700470000 | SIST NAS 12BAHIAS NUCLEOS 3,3GHZ 300W OF |  | 2024-03-06 |  | TS-1283XU-RP-E2124-8G | QNAP SYSTEMS | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | QNAP | dpenag | Identificado alternativo | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105582/20
1800105207/10 | 3060301930700 |  | DISCO DURO SSD 1TB SATA3 2.5" 870QVO |  | 2024-03-06 |  | MZ-77Q1T0BW | SAMSUNG | 12 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | DISCO DURO | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105207/10
1800105582/10 | 3060303259000 | 1706700040700 | KIT GUIA RAIL P/ TSX79/TSECX80U |  | 2024-03-06 |  | RAIL-A01-35 | QNAP SYSTEMS | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | RAIL MONTAJE | dpenag | Lanzar de nuevo con código 1706700040700 | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105582/10
1800105189/140 | 1229599001001 |  | CBL EQ ALIM C13X2(H) C14(M) 250V NG 2,5M |  | 2024-03-06 |  | 818-8909 | RS PRO | 12 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE POTENCIA | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/140
1800105189/110 | 1229590010001 |  | CBL EQ ALIMEN IEC320.C13/C14 1M |  | 2024-03-06 |  | IECC13C14-1 | CUBITEL | 3 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE POTENCIA | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/110
1800105189/10 | 1229502480000 |  | CBL EQ ALIMENT 10A 250V C13 CEE 7/7 L=2. |  | 2024-03-06 |  | 626-6616 | DECELECT | 11 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE POTENCIA | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/10
1800105189/150 | 1351709000500 |  | MOD INTERFAZ AUDIO USB 44.1HZ-192KHZ 30P |  | 2024-03-06 |  | FIREFACE UFX II | RME INTELLIGENR AUDI | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | MOD. INTERFAZ AUDIO | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/150
1800105189/160 | 1701501350200 |  | RACK NETSHELTER SX 1991X600X1070MM 42U |  | 2024-03-06 |  | AR3100 | APC | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | RACK | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/160
1800105189/170 | 1701501522000 |  | RACK 19" 34U 1567X553X500MM RAL7021 |  | 2024-03-06 |  | 28230-029 | SCHROFF | 1 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | RACK | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/170
1800105189/100 | 1229524400300 |  | CBL EQ DISPLAYPORT1.2-M/M 4K NEGRO L=15M |  | 2024-03-06 |  | 236-9089 | RS PRO | 15 | ENTORNO | S23D02_P1283 |  | 1 | ENTORNO DE DESARROLLO | CABLE VIDEO | dpenag |  | 60002983 | 7218¦2GP313_1016 | [8 empty] | 1800105189/100
1101726043/1 | 1390702400000 |  | PANTALLA CONTROL ADF CDF-552 S/OF |  |  |  | 400-047552-9005 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/2 | 1390702400000 |  | PANTALLA CONTROL ADF CDF-552 S/OF |  |  |  | 400-047552-9005 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/6 | 1390702400000 |  | PANTALLA CONTROL ADF CDF-552 S/OF |  |  |  | 400-047552-9005 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/3 | 1390702400100 |  | PANEL CONTROL AUDIO DIGITAL ACP-53 S/OF |  |  |  | ACP53-003 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/4 | 1390702400100 |  | PANEL CONTROL AUDIO DIGITAL ACP-53 S/OF |  |  |  | ACP53-003 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/5 | 1390702400100 |  | PANEL CONTROL AUDIO DIGITAL ACP-53 S/OF |  |  |  | ACP53-003 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/7 | 1390702400200 |  | TAPA LEYENDA PLACA-FRONTAL S/OF |  |  |  | 55-06-000 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/8 | 1390702400200 |  | TAPA LEYENDA PLACA-FRONTAL S/OF |  |  |  | 55-06-000 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/9 | 1390702400200 |  | TAPA LEYENDA PLACA-FRONTAL S/OF |  |  |  | 55-06-000 | COBHAM |  | ELEMENTO CRÍTICO
1101720693/3 | 1309000613000 |  | AUTO PILOT CONTROL PANEL |  |  |  | FP682-22 | ESTERLINE |  | ELEMENTO CRÍTICO
1101720693/4 | 1309000613000 |  | AUTO PILOT CONTROL PANEL |  |  |  | FP682-22 | ESTERLINE |  | ELEMENTO CRÍTICO
1101720693/5 | 1309000613000 |  | AUTO PILOT CONTROL PANEL |  |  |  | FP682-22 | ESTERLINE |  | ELEMENTO CRÍTICO
1101695398/1 | 1390704800100 |  | GENERADOR MAP DIGI RN7 C/UMTS3G EURONAV7 |  |  |  | 257.015-004 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695419/1 | 1390704800100 |  | GENERADOR MAP DIGI RN7 C/UMTS3G EURONAV7 |  |  |  | 257.015-004 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695398/2 | 1390704809100 |  | BANDEJA MONT 1/4 ATR HNR-7.0 VERT P/RN7 |  |  |  | 255.001-001 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695419/2 | 1390704809100 |  | BANDEJA MONT 1/4 ATR HNR-7.0 VERT P/RN7 |  |  |  | 255.001-001 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695398/3 | 1390704809000 |  | KIT CONECTOR P/GENERADOR MAP DIGI RN7 |  |  |  | 255.007-041 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695419/3 | 1390704809000 |  | KIT CONECTOR P/GENERADOR MAP DIGI RN7 |  |  |  | 255.007-041 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695398/4 | 1390704809700 |  | UDAD CNTRL CLN8-1.0 NVIS B RN7 EURONAV7 |  |  |  | 257.007-023 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695419/4 | 1390704809700 |  | UDAD CNTRL CLN8-1.0 NVIS B RN7 EURONAV7 |  |  |  | 257.007-023 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695398/5 | 1390704809800 |  | KIT CNC CLN8-1.0+CLN8ERS-1.0 EURONAV7 |  |  |  | 255.007-043 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695419/5 | 1390704809800 |  | KIT CNC CLN8-1.0+CLN8ERS-1.0 EURONAV7 |  |  |  | 255.007-043 | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695398/6 | 1390704809900 |  | DISCO FLASH 512GB C/ARINC708 EURONAV7 |  |  |  | 257.031-179M | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101695419/6 | 1390704809900 |  | DISCO FLASH 512GB C/ARINC708 EURONAV7 |  |  |  | 257.031-179M | EUROAVIONICS GMBH & CO |  | ELEMENTO CRÍTICO
1101726043/3 | 1390702400100 |  | PANEL CONTROL AUDIO DIGITAL ACP-53 S/OF |  |  |  | ACP53-003 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/4 | 1390702400100 |  | PANEL CONTROL AUDIO DIGITAL ACP-53 S/OF |  |  |  | ACP53-003 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/5 | 1390702400100 |  | PANEL CONTROL AUDIO DIGITAL ACP-53 S/OF |  |  |  | ACP53-003 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/7 | 1390702400200 |  | TAPA LEYENDA PLACA-FRONTAL S/OF |  |  |  | 55-06-000 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/8 | 1390702400200 |  | TAPA LEYENDA PLACA-FRONTAL S/OF |  |  |  | 55-06-000 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/9 | 1390702400200 |  | TAPA LEYENDA PLACA-FRONTAL S/OF |  |  |  | 55-06-000 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/1 | 1390702400000 |  | PANTALLA CONTROL ADF CDF-552 S/OF |  |  |  | 400-047552-9005 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/2 | 1390702400000 |  | PANTALLA CONTROL ADF CDF-552 S/OF |  |  |  | 400-047552-9005 | COBHAM |  | ELEMENTO CRÍTICO
1101726043/6 | 1390702400000 |  | PANTALLA CONTROL ADF CDF-552 S/OF |  |  |  | 400-047552-9005 | COBHAM |  | ELEMENTO CRÍTICO
1101720693/1 | 1303000350000 |  | CPI 28V COCKPIT CTRL PANEL W/NIGHT VISIO |  |  |  | 503-22-28NV | TECHTEST LIMITED |  | ELEMENTO CRÍTICO
1101720693/2 | 1303000350000 |  | CPI 28V COCKPIT CTRL PANEL W/NIGHT VISIO |  |  |  | 503-22-28NV | TECHTEST LIMITED |  | ELEMENTO CRÍTICO
1101718321/1 | 1390705630201 |  | HANDCONTROLLER MX SERIES S/OF |  |  |  | 42228-22 | L-3 WESCAM |  | ELEMENTO CRÍTICO
1101718321/2 | 1390705630201 |  | HANDCONTROLLER MX SERIES S/OF |  |  |  | 42228-22 | L-3 WESCAM |  | ELEMENTO CRÍTICO

## Extended Orders Report
Material | Material Description | Solped | Solped Line | Date Sol. | Warning Sol | No. PO | PO Line | PO Date | Release PO Date | Warning PO | Delivery Date | Planned Lead Time | Tmpo.tratamiento EM | Status | Ctd. Solicitada | Ctd. pedido | Ctd. Recepcionada | Ctd. por recepcionar | Ctd. Aceptada | Ctd. Rechazada | Received | Valor por entregar | Valor ctd. aceptada | Supplier | OEM | P/N OEM | Concluída | Número modificaciones en fecha entrega | Número modificaciones fecha estadística | Es material RUF(Si='X',No='') | Elemento PEP | Lead Time | Lead Time Impact | Revised Date | OTD | OTD Qty | Late | Late Qty | Extended dealine Orders | OTIF | OTIF (%) | Pending Orders to be received | Pending to be issued | SOLPED BLOQ | PO BLOQ | Month | Backorder Rate | Today | Delivery Date-Today | On-going Deliveries | On-going Deliveries (Qty) | Warning Units (neededvsordered) | Solped pos | Device | LT | Posición GPI | OP
| JOSÉ MARÍA CHAVERO | 1101869421 | 1 | 2025-05-15 |  | 4300346317 | 10 | 2025-05-20 | 2025-05-21 |  | 2025-07-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | TINDAI FORMACION, PREVENCION Y |  |  |  | 0 | 0 |  | 7218¦JA2594_1001
| ADEC. LUMINARIAS BANCO ST.01 | 1101876885 | 1 | 2025-06-04 |  | 4300348534 | 10 | 2025-06-25 | 2025-06-26 |  | 2025-10-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001
| INSTALACION SIMULADOR A320 | 1101881742 | 1 | 2025-06-17 |  | 4300348535 | 30 | 2025-06-25 | 2025-07-01 |  | 2025-07-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | TALLERES SANTIAGO DATO, S.L.U. |  |  |  | 1 | 1 |  | 7218¦JA2594_1001
| INSTAL. CONDUCTOS PINGÜINO SF.03 | 1101885147 | 1 | 2025-06-26 |  | 4300349565 | 10 | 2025-07-11 | 2025-07-14 |  | 2025-10-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦S24B05_S1075
| MOQUETA A320 FFS | 1101890088 | 1 | 2025-07-10 |  | 4300349810 | 10 | 2025-07-17 | 2025-07-18 |  | 2025-11-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ANTONIO RAMIREZ DECORACION SL |  |  |  | 0 | 0 |  | 7218¦S24B05_S1076
| TRABAJOS DE CORTE DE MAYLAR - COSLADA | 1101893680 | 1 | 2025-07-21 |  | 4300350504 | 10 | 2025-07-30 | 2025-07-30 |  | 2025-08-13 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ISC Instalaciones y Servicios de |  |  |  | 0 | 0 |  | 7218¦S24B05_P10253
| FABRICACION PIEZAS | 1101893987 | 1 | 2025-07-22 |  | 4300350909 | 10 | 2025-08-07 | 2025-08-07 |  | 2025-09-14 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ESTRUCTURAS COSAN,S.L. |  |  |  | 0 | 0 |  | 7218¦JA2594_1001
| MONTAJE REJIBAND SF.03 | 1101898253 | 1 | 2025-08-05 |  | 4300351264 | 10 | 2025-08-18 | 2025-08-19 |  | 2025-12-31 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | VEOLIA SERVICIOS LECAM, S.A.U. |  |  |  | 0 | 0 |  | 7218¦S24B05_GAR03
| INSTALACION SIMULADOR H175 | 1101904455 | 1 | 2025-09-03 |  | 4300352010 | 20 | 2025-09-05 | 2025-09-17 |  | 2025-10-15 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | ISC Instalaciones y Servicios de |  |  |  | 1 | 1 |  | 7218¦JA2593_1001
| PROGRAMACIÓN CENTRALITA DE INCENDIOS | 1101920430 | 1 | 2025-10-15 |  | 4300354754 | 10 | 2025-10-23 | 2025-11-18 |  | 2025-11-30 | 0 | 0 | Liberado | 1 | 1 | 0 | 0 | 0 | 0 |  | 0.00 |  | IBERCOIN INGENIEROS, S.L. |  |  |  | 2 | 2 |  | 7218¦S24B05_S1076
1239024433900 | MANG AUTOSOLD AWG22 C/TERMIN M83519/2-8 | 1800108784 | 90 | 2024-06-14 |  | 4200571556 | 170 | 2024-07-19 | 2024-07-24 |  | 2024-07-26 | 30 | 8 | Liberado | 500 | 500 | 0 | 500 | 0 | 0 |  | 500.00 |  | TTI INC. | TE CONNECTIVITY | S02-08-R |  | 0 | 0 |  | 7218¦JA2581_1001
1229590140400 | CBL EQ CAT6A LSZH RJ45-M/RJ45-M L=0.5M | 1800108947 | 80 | 2024-06-19 |  | 4200580892 | 10 | 2024-10-11 | 2024-10-15 |  | 2024-10-18 | 105 | 8 | Liberado | 6 | 6 | 0 | 6 | 0 | 0 |  | 31.20 |  | GITEC CONTROL, S.L. | OMRON CORPORATION | XS6W-6LSZH8SS50CM-Y |  | 0 | 0 |  | 7218¦JA2586_1001
1209994000109 | ACC CARCASA P/CNC SUB-D ZINC | 1800110417 | 90 | 2024-07-17 |  | 4200583052 | 730 | 2024-10-25 | 2025-02-08 |  | 2025-01-17 | 80 | 8 | Liberado | 50 | 100 | 0 | 100 | 0 | 0 |  | 1650.00 |  | TTI INC. | TE CONNECTIVITY | 1-2308346-6 |  | 0 | 0 |  | 7218¦JA2581_1001
1263011094800 | FA 85-264VAC 12(12-16)VDC 2.5A 30W C-DIN | 1800110423 | 180 | 2024-07-17 |  | 4200571846 | 10 | 2024-07-23 | 2024-07-23 |  | 2024-08-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 58.46 |  | AMIDATA, S.A. | TRACO POWER | TBL 030-112 |  | 0 | 0 |  | 7218¦JA2584_1001
1390705220902 | MS TUNING | 1800112332 | 40 | 2024-09-04 |  | 4600003976 | 170 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 7216.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA90 |  | 1 | 1 |  | 7218¦JA2612_1001
1390705220903 | CLS TUNING | 1800112332 | 50 | 2024-09-04 |  | 4600003976 | 180 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 13825.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA130 |  | 2 | 1 |  | 7218¦JA2612_1001
1390705220905 | TRAVEL & SUBS.TUNING MS | 1800112332 | 70 | 2024-09-04 |  | 4600003976 | 200 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 4520.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA150 |  | 2 | 2 |  | 7218¦JA2612_1001
1390705220907 | TRAVEL & SUBS.TUNING CLS | 1800112332 | 90 | 2024-09-04 |  | 4600003976 | 220 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 5895.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA170 |  | 2 | 2 |  | 7218¦JA2612_1001
1239024433900 | MANG AUTOSOLD AWG22 C/TERMIN M83519/2-8 | 1800108784 | 90 | 2024-06-14 |  | 4200571556 | 170 | 2024-07-19 | 2024-07-24 |  | 2024-07-26 | 30 | 8 | Liberado | 500 | 500 | 0 | 500 | 0 | 0 |  | 500.00 |  | TTI INC. | TE CONNECTIVITY | S02-08-R |  | 0 | 0 |  | 7218¦JA2581_1001
0970785241600 | CHASSIS 24VU | 1800108820 | 50 | 2024-06-16 |  | 4200570671 | 20 | 2024-07-15 | 2026-01-22 |  | 2026-01-24 | 90 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 182.95 |  | JOYFE,S.L. | INDRA SISTEMAS S.A. | 0970785241600 |  | 4 | 4 |  | 7218¦JA2583_1001
1229590140400 | CBL EQ CAT6A LSZH RJ45-M/RJ45-M L=0.5M | 1800108947 | 80 | 2024-06-19 |  | 4200580892 | 10 | 2024-10-11 | 2024-10-15 |  | 2024-10-18 | 105 | 8 | Liberado | 6 | 6 | 0 | 6 | 0 | 0 |  | 31.20 |  | GITEC CONTROL, S.L. | OMRON CORPORATION | XS6W-6LSZH8SS50CM-Y |  | 0 | 0 |  | 7218¦JA2586_1001
1209994000109 | ACC CARCASA P/CNC SUB-D ZINC | 1800110417 | 90 | 2024-07-17 |  | 4200583052 | 730 | 2024-10-25 | 2025-02-08 |  | 2025-01-17 | 80 | 8 | Liberado | 50 | 100 | 0 | 100 | 0 | 0 |  | 1650.00 |  | TTI INC. | TE CONNECTIVITY | 1-2308346-6 |  | 0 | 0 |  | 7218¦JA2581_1001
1263011094800 | FA 85-264VAC 12(12-16)VDC 2.5A 30W C-DIN | 1800110423 | 180 | 2024-07-17 |  | 4200571846 | 10 | 2024-07-23 | 2024-07-23 |  | 2024-08-19 | 30 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 58.46 |  | AMIDATA, S.A. | TRACO POWER | TBL 030-112 |  | 0 | 0 |  | 7218¦JA2584_1001
1390705220902 | MS TUNING | 1800112332 | 40 | 2024-09-04 |  | 4600003976 | 170 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 7216.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA90 |  | 1 | 1 |  | 7218¦JA2612_1001
1390705220903 | CLS TUNING | 1800112332 | 50 | 2024-09-04 |  | 4600003976 | 180 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 13825.00 |  | MOOG, B.V. | MOOG | DM-NL-TUNING-NC/LINEA130 |  | 2 | 1 |  | 7218¦JA2612_1001
1390705220905 | TRAVEL & SUBS.TUNING MS | 1800112332 | 70 | 2024-09-04 |  | 4600003976 | 200 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 4520.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA150 |  | 2 | 2 |  | 7218¦JA2612_1001
1390705220907 | TRAVEL & SUBS.TUNING CLS | 1800112332 | 90 | 2024-09-04 |  | 4600003976 | 220 | 2024-06-21 | 2024-09-11 |  | 2025-03-31 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 5895.00 |  | MOOG, B.V. | MOOG | DM-NL-TRAV-SUBSIST/LINEA170 |  | 2 | 2 |  | 7218¦JA2612_1001
1237090092100 | BORNA RAIL 10P #20 7,5A TYP11 | 1800112395 | 10 | 2024-09-05 |  | 4200581619 | 10 | 2024-10-16 | 2025-04-07 |  | 2025-01-03 | 30 | 8 | Liberado | 6 | 50 | 50 | 50 | 0 | 50 |  | 837.00 |  | SOURIAU | SOURIAU | 8559N2011B |  | 0 | 0 |  | 7218¦JA2581_1001
1209500900300 | CNC HEADER 1X9M 2,54MM PCB RECT LAT/AU | 1800113277 | 60 | 2024-10-02 |  | 4200582207 | 230 | 2024-10-21 | 2025-04-30 |  | 2024-11-04 | 85 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 22.60 |  | FARNELL COMPONENTS, S.L. | MOLEX | 70543-0008 |  | 1 | 1 |  | 7218¦JA2583_1001
1209501002300 | CNC HEADER 1X10M 2,54MM PCB RECT LAT/SN | 1800113277 | 70 | 2024-10-02 |  | 4200582207 | 240 | 2024-10-21 | 2025-04-30 |  | 2024-11-04 | 85 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 23.40 |  | FARNELL COMPONENTS, S.L. | MOLEX | 70543-0044 |  | 1 | 1 |  | 7218¦JA2583_1001
1390700725500 | GEAR BOX A320 | 1800113827 | 40 | 2024-10-10 |  | 4600004293 | 10 | 2025-01-20 | 2025-01-21 |  | 2025-01-29 | 40 | 8 | Liberado | 1 | 1 | 0 | 1 | 0 | 0 |  | 1470.00 |  | TOULOUSE AIR SPARES | AIRBUS INDUSTRIE | D3231007000100 |  | 0 | 0 |  | 7218¦JA2583_1001
1220115702600 | CBL FLEX 1X70MM2 450/750V AZUL H07ZK 90C | 1800120450 | 20 | 2025-02-24 |  | 4200601560 | 10 | 2025-03-09 | 2025-03-09 |  | 2025-11-24 | 85 | 8 | Liberado | 20 | 20 | 0 | 20 | 0 | 0 |  | 578.00 |  | Technipol Suministros, S.L. | LAPP KABEL | 4727021 |  | 2 | 0 |  | 7218¦JA2582_1001
0973588330200 | DOOR INTERNAL FRAME | 1800128532 | 10 | 2025-08-20 |  | 4200629548 | 50 | 2025-10-02 | 2025-10-15 |  | 2025-11-20 | 40 | 8 | Liberado | 1 | 1 | 1 | 1 | 0 | 1 |  | 289.60 |  | PREFIMETAL, S.A. | INDRA SISTEMAS S.A. | 0973588330200 |  | 0 | 0 |  | 7218¦JA2582_1001

## Pending to be issued
Material | Material Description | Solped | Solped Line | Date Sol. | Warning Sol | No. PO | PO Line | PO Date | Release PO Date | Warning PO | Delivery Date | Planned Lead Time | Tmpo.tratamiento EM | Status | Ctd. Solicitada | Ctd. pedido | Ctd. Recepcionada | Ctd. por recepcionar | Ctd. Aceptada | Ctd. Rechazada | Received | Valor por entregar | Valor ctd. aceptada | Supplier | OEM | P/N OEM | Concluída | Número modificaciones en fecha entrega | Número modificaciones fecha estadística | Es material RUF(Si='X',No='') | Elemento PEP | Lead Time | Lead Time Impact | Revised Date | OTD | OTD Qty | Late | Late Qty | Extended dealine Orders | OTIF | OTIF (%) | Pending Orders to be received | Pending to be issued | SOLPED BLOQ | PO BLOQ | Month | Backorder Rate | Today | Delivery Date-Today | On-going Deliveries | On-going Deliveries (Qty) | Warning Units (neededvsordered) | Solped pos | Device | LT | Posición GPI | OP

## Process Overview
SUPPLIERS - ORDERS STATUS |  |  | SUPPLIERS - KPIs | [10 empty] | SUPPLIERS - PROCESS OVERVIEW (QTY ITEMS) | [8 empty] | KPI- POs pending to be issued | [13 empty] | Faltantes OPs
[14 empty] | Etiquetas de fila | Qty Ordered | Qty to be received | Qty Received | Qty Received and Accepted | [5 empty] | Etiquetas de columna
Suppliers | Suma de Ctd. Solicitada | Suma de Ctd. Aceptada | Etiquetas de fila | No. PO / No.Lines | OTIF (%) | Backorder Rate (%) | No. Extended dealine Orders | No. On-going Deliveries | [5 empty] | (AEMSA)ALMACENES ELECTRICOS MADRILE | 6589 | 0 | 6589 | 6220 | [5 empty] | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 3 | 4 | Total general | Suma de Ctd. pedido | Suma de Ctd. Aceptada
(AEMSA)ALMACENES ELECTRICOS MADRILE | 60 | 0 | (AEMSA)ALMACENES ELECTRICOS MADRILE | 61 | 100% | 0% | 0 | 0 | [5 empty] | CENVALSA, S.L. | 80 | 0 | 80 | 80 |  |  |  |  | Pending to be issued | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36689 | 996
ABACO SUYTEC, S.A.U. | 580 | 0 | CENVALSA, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | CONECTORES Y CABLES VAHER, S.A. | 6426 | 1 | 6462 | 6425
AMIDATA, S.A. | 34119 | 0 | CONECTORES Y CABLES VAHER, S.A. | 23 | 95.65% | 4.348% | 0 | 0 | [5 empty] | DELL COMPUTER, S.A. | 1 | 0 | 1 | 0
CONECTORES Y CABLES VAHER, S.A. | 94 | 94 | DELL COMPUTER, S.A. | 1 | 100% | 0% | 0 | 0 | [5 empty] | ELECTRONIC EQUIPMENT TRADING SAU (E | 1 | 0 | 1 | 1 |  |  |  |  | No.POs pending to be issued
DELL COMPUTER, S.A. | 1 | 0 | ELECTRONIC EQUIPMENT TRADING SAU (E | 1 | 100% | 0% | 0 | 0 | [5 empty] | ESPRINET IBERICA, S.L.U. | 4 | 0 | 4 | 4 |  |  |  |  | 0
Electro Enterprises New York | 300 | 300 | ESPRINET IBERICA, S.L.U. | 2 | 100% | 0% | 0 | 0 | [5 empty] | FARNELL COMPONENTS, S.L. | 1003 | 1000 | 5 | 3
ELECTRONIC EQUIPMENT TRADING SAU (E | 1 | 1 | FARNELL COMPONENTS, S.L. | 5 | 60% | 40% | 0 | 0 | [5 empty] | ICOMPPLUS ELECTRONICS S.L | 6701 | 1918 | 4783 | 4783
FELIPE DE MARCO, S.A. | 14 | 0 | ICOMPPLUS ELECTRONICS S.L | 66 | 33.33% | 66.67% | 0 | 0 | [5 empty] | INDUSTRIAS BALMES, S.A. | 9 | 0 | 11 | 9
GRUPO ELECTRO-STOCKS,S.L.U | 32 | 0 | INDUSTRIAS BALMES, S.A. | 8 | 100% | 0% | 0 | 0 | [5 empty] | INFORMATICA CALCULO Y TECNICA, S.A. | 6 | 0 | 6 | 6
ICOMPPLUS ELECTRONICS S.L | 121 | 30 | INFORMATICA CALCULO Y TECNICA, S.A. | 6 | 100% | 0% | 0 | 0 | [5 empty] | JOYFE,S.L. | 14 | 1 | 14 | 13
INFORMATICA CALCULO Y TECNICA, S.A. | 5 | 5 | JOYFE,S.L. | 9 | 88.89% | 11.11% | 1 | 0 | [5 empty] | LUJISA, S.A. | 613 | 0 | 613 | 413
INGRAM MICRO, S.L.U. | 1 | 0 | LUJISA, S.A. | 6 | 100% | 0% | 0 | 0 | [5 empty] | MARKABLE SOLUTIONS, S.L. | 2000 | 0 | 2000 | 2000
MILEXIA IBÉRICA, S.A.U. | 1 | 0 | MARKABLE SOLUTIONS, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | MILEXIA IBÉRICA, S.A.U. | 9 | 1 | 8 | 8
PENTATEL COMUNICACIONES, S.L. | 5 | 0 | MILEXIA IBÉRICA, S.A.U. | 3 | 66.67% | 33.33% | 0 | 0 | No.POs / No. Lines | OTIF (%) | Backorder Rate (%) | No. Extended Deadline Orders | No. On-going Deliveries | MOOG, B.V. | 1 | 1 | 0 | 0 | Qty Ordered | Qty to be received | Qty Received | Qty Accepted
REBOUND ELECTRONICS (UK) LTD | 2 | 2 | MOOG, B.V. | 1 | 0% | 100% | 0 | 0 | 967 | 91.42% | 8.583% | 13 | #VALUE! | OMNIAELECTRONICS, S.L. | 100 | 0 | 100 | 100 | 88069.2 | 4579.2 | 85197 | 37807
SUMINISTROS CONECTORES PROF.,SA. | 56 | 56 | OMNIAELECTRONICS, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | PENTATEL COMUNICACIONES, S.L. | 5 | 0 | 0 | 0
SUMINISTROS, FRESADOS Y GRABADOS | 7 | 0 | PENTATEL COMUNICACIONES, S.L. | 5 | 100% | 0% | 0 | 0 | [5 empty] | REBOUND ELECTRONICS (UK) LTD | 2 | 0 | 2 | 2
TALLERES SANTIAGO DATO, S.L.U. | 4 | 0 | REBOUND ELECTRONICS (UK) LTD | 1 | 100% | 0% | 0 | 0 | [5 empty] | SARVER S.L. | 78 | 0 | 78 | 0
TALLERES XUQUER, SL | 2 | 0 | SARVER S.L. | 44 | 97.73% | 2.273% | 0 | 0 | [5 empty] | SUMINISTROS CONECTORES PROF.,SA. | 11754 | 320 | 11435 | 5601
TD SYNNEX SPAIN, S.L.U. | 12 | 0 | SUMINISTROS CONECTORES PROF.,SA. | 80 | 93.75% | 6.25% | 0 | 0 | [5 empty] | SUMINISTROS, FRESADOS Y GRABADOS | 69 | 0 | 69 | 62
Technipol Suministros, S.L. | 190 | 411 | SUMINISTROS, FRESADOS Y GRABADOS | 9 | 100% | 0% | 0 | 0 | [5 empty] | TALLERES XUQUER, SL | 3 | 0 | 2 | 1
TTI, INC. | 28 | 28 | TALLERES XUQUER, SL | 3 | 100% | 0% | 0 | 0 | [5 empty] | TD SYNNEX SPAIN, S.L.U. | 12 | 0 | 12 | 0
VEOLIA SERVICIOS LECAM, S.A.U. | 4 | 0 | TD SYNNEX SPAIN, S.L.U. | 7 | 100% | 0% | 0 | 0 | [5 empty] | Technipol Suministros, S.L. | 868.2 | 457.2 | 1091 | 411
VESTUARIO Y PROTECCION LABORAL JOYS | 7 | 0 | Technipol Suministros, S.L. | 9 | 88.89% | 11.11% | 0 | 0 | [5 empty] | TELKRON, S.A. | 1121 | 0 | 1121 | 1121
ALTER TECHNOLOGY-TÜV NORD | 1 | 0 | TELKRON, S.A. | 5 | 100% | 0% | 0 | 0 | [5 empty] | TEMPEL, S.A. | 1 | 0 | 1 | 1
HILTI ESPAÑOLA, S.A. | 6 | 0 | TEMPEL, S.A. | 1 | 100% | 0% | 0 | 0 | [5 empty] | GRUPO ELECTRO-STOCKS,S.L.U | 32 | 0 | 32 | 0
ACOM SISTEMAS, S.L. | 1 | 0 | GRUPO ELECTRO-STOCKS,S.L.U | 4 | 75% | 25% | 0 | 0 | [5 empty] | ABACO SUYTEC, S.A.U. | 1125 | 0 | 1125 | 0
AUXITEL, S.L. | 11 | 0 | ABACO SUYTEC, S.A.U. | 56 | 98.21% | 1.786% | 0 | 0 | [5 empty] | INGRAM MICRO, S.L.U. | 1 | 0 | 1 | 0
FERRETERIA FERAYU SL | 3 | 0 | INGRAM MICRO, S.L.U. | 1 | 100% | 0% | 0 | 0 | [5 empty] | DICOMAT, S.L. | 1250 | 0 | 2250 | 1250
SOUND OF NUMBERS SL | 1 | 1 | DICOMAT, S.L. | 3 | 100% | 0% | 0 | 0 | [5 empty] | GITEC CONTROL, S.L. | 162 | 6 | 162 | 156
FUNDACION JUAN XXIII-RONCALLI DISC. | 46 | 0 | GITEC CONTROL, S.L. | 5 | 80% | 20% | 1 | 0 | [5 empty] | Electro Enterprises New York | 900 | 0 | 900 | 350
SARVER S.L. | 58 | 0 | Electro Enterprises New York | 5 | 100% | 0% | 0 | 0 | [5 empty] | AUXITEL, S.L. | 16 | 0 | 5 | 5
YNTEGRA SERV.INTEGRALES, S.L. | 2 | 0 | AUXITEL, S.L. | 12 | 100% | 0% | 0 | 0 | [5 empty] | ARROW IBERIA ELECTRONICA SLU | 977 | 0 | 977 | 977
TCX MICRO, S.L.U | 11 | 50 | ARROW IBERIA ELECTRONICA SLU | 1 | 100% | 0% | 0 | 0 | [5 empty] | MAX TECHNOLOGIES INC | 24 | 6 | 18 | 18
ISC Instalaciones y Servicios de | 4 | 0 | MAX TECHNOLOGIES INC | 6 | 66.67% | 33.33% | 0 | 0 | [5 empty] | VESTUARIO Y PROTECCION LABORAL JOYS | 7 | 0 | 7 | 0
RDT INGENIEROS MADRID, S.L. | 1 | 0 | VESTUARIO Y PROTECCION LABORAL JOYS | 7 | 100% | 0% | 0 | 0 | [5 empty] | SOURIAU | 1252 | 0 | 1252 | 1252
CONSUEGRA SOC. COOP. LTD. | 1 | 0 | SOURIAU | 5 | 100% | 0% | 0 | 0 | [5 empty] | AMIDATA, S.A. | 34125 | 1 | 34124 | 6
APLICACIONES DE SIMULACION | 2 | 0 | AMIDATA, S.A. | 361 | 99.72% | 0.277% | 0 | 0 | [5 empty] | TTI, INC. | 28 | 0 | 48 | 28
ESTRUCTURAS COSAN,S.L. | 2 | 0 | TTI, INC. | 4 | 100% | 0% | 0 | 0 | [5 empty] | CERVI, S.L. | 200 | 0 | 200 | 200
LAYHER IBERICA, S.L. | 17 | 17 | CERVI, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | PEI GENESISUK LTD | 1280 | 200 | 1080 | 1080
TINDAI FORMACION, PREVENCION Y | 1 | 0 | PEI GENESISUK LTD | 7 | 85.71% | 14.29% | 0 | 0 | [5 empty] | QNV, S.L. | 1 | 0 | 1 | 1
ANTONIO RAMIREZ DECORACION SL | 1 | 0 | QNV, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | E-T-A APARELLAJE ELECTRICO S.L.U. | 869 | 0 | 869 | 869
SOLUCIONES SICNOVA, S.L. | 1 | 1 | E-T-A APARELLAJE ELECTRICO S.L.U. | 21 | 100% | 0% | 0 | 0 | [5 empty] | TALLERES SANTIAGO DATO, S.L.U. | 4 | 0 | 0 | 0
| 8 | 0 | TALLERES SANTIAGO DATO, S.L.U. | 4 | 75% | 25% | 1 | 0 | [5 empty] | VEOLIA SERVICIOS LECAM, S.A.U. | 4 | 0 | 0 | 0
IBERCOIN INGENIEROS, S.L. | 1 | 0 | VEOLIA SERVICIOS LECAM, S.A.U. | 4 | 0% | 100% | 3 | 1 | [5 empty] | FELIPE DE MARCO, S.A. | 14 | 0 | 14 | 0
Total general | 35825 | 996 | FELIPE DE MARCO, S.A. | 10 | 100% | 0% | 0 | 0 | [5 empty] | BARCITRONIC S.A. | 3 | 0 | 3 | 3
|  |  | BARCITRONIC S.A. | 1 | 100% | 0% | 0 | 0 | [5 empty] | ALTER TECHNOLOGY-TÜV NORD | 1 | 0 | 0 | 0
|  |  | ALTER TECHNOLOGY-TÜV NORD | 1 | 0% | 100% | 0 | 1 | [5 empty] | HILTI ESPAÑOLA, S.A. | 34 | 0 | 33 | 0
|  |  | HILTI ESPAÑOLA, S.A. | 6 | 100% | 0% | 0 | 0 | [5 empty] | CHARMEX INTERNACIONAL S.A. | 5 | 0 | 5 | 5
|  |  | CHARMEX INTERNACIONAL S.A. | 1 | 100% | 0% | 0 | 0 | [5 empty] | ELATE,S.A. | 25 | 0 | 25 | 25
|  |  | ELATE,S.A. | 1 | 100% | 0% | 0 | 0 | [5 empty] | SIMTEK, INC | 1 | 0 | 1 | 1
|  |  | SIMTEK, INC | 1 | 100% | 0% | 0 | 0 | [5 empty] | OMRON ELECTRONICS IBERIA S.A.U. | 6 | 6 | 0 | 0
|  |  | OMRON ELECTRONICS IBERIA S.A.U. | 1 | 0% | 100% | 0 | 0 | [5 empty] | ACOM SISTEMAS, S.L. | 1 | 0 | 0 | 0
|  |  | ACOM SISTEMAS, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | FERRETERIA FERAYU SL | 3 | 0 | 3 | 0
|  |  | FERRETERIA FERAYU SL | 1 | 100% | 0% | 0 | 0 | [5 empty] | SOUND OF NUMBERS SL | 1 | 0 | 1 | 1
|  |  | SOUND OF NUMBERS SL | 1 | 100% | 0% | 0 | 0 | [5 empty] | CONSUEGRA SOC. COOP. LTD. | 1 | 0 | 1 | 0
|  |  | CONSUEGRA SOC. COOP. LTD. | 1 | 100% | 0% | 0 | 0 | [5 empty] | FUNDACION JUAN XXIII-RONCALLI DISC. | 46 | 0 | 46 | 0
|  |  | FUNDACION JUAN XXIII-RONCALLI DISC. | 13 | 100% | 0% | 0 | 0 | [5 empty] | YNTEGRA SERV.INTEGRALES, S.L. | 2 | 0 | 0 | 0
|  |  | YNTEGRA SERV.INTEGRALES, S.L. | 2 | 100% | 0% | 0 | 0 | [5 empty] | TCX MICRO, S.L.U | 773 | 0 | 773 | 763
|  |  | TCX MICRO, S.L.U | 15 | 100% | 0% | 0 | 0 | [5 empty] | ISC Instalaciones y Servicios de | 4 | 0 | 0 | 0
|  |  | ISC Instalaciones y Servicios de | 4 | 50% | 50% | 2 | 0 | [5 empty] | RDT INGENIEROS MADRID, S.L. | 1 | 0 | 0 | 0
|  |  | RDT INGENIEROS MADRID, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | APLICACIONES DE SIMULACION | 2 | 0 | 0 | 0
|  |  | APLICACIONES DE SIMULACION | 2 | 100% | 0% | 0 | 0 | [5 empty] | ESTRUCTURAS COSAN,S.L. | 2 | 0 | 0 | 0
|  |  | ESTRUCTURAS COSAN,S.L. | 2 | 50% | 50% | 1 | 0 | [5 empty] | LAYHER IBERICA, S.L. | 17 | 0 | 17 | 17
|  |  | LAYHER IBERICA, S.L. | 4 | 100% | 0% | 0 | 0 | [5 empty] | ARRAY ELECTRONICA PROFESIONAL, S.A. | 100 | 0 | 100 | 100
|  |  | ARRAY ELECTRONICA PROFESIONAL, S.A. | 1 | 100% | 0% | 0 | 0 | [5 empty] | TINDAI FORMACION, PREVENCION Y | 1 | 0 | 0 | 0
|  |  | TINDAI FORMACION, PREVENCION Y | 1 | 0% | 100% | 1 | 0 | [5 empty] | INGE VIDEO, S.A. | 14 | 0 | 14 | 14
|  |  | INGE VIDEO, S.A. | 2 | 100% | 0% | 0 | 0 | [5 empty] | ANTONIO RAMIREZ DECORACION SL | 1 | 0 | 0 | 0
|  |  | ANTONIO RAMIREZ DECORACION SL | 1 | 0% | 100% | 1 | 0 | [5 empty] | SOLUCIONES SICNOVA, S.L. | 1 | 0 | 1 | 1
|  |  | SOLUCIONES SICNOVA, S.L. | 1 | 100% | 0% | 0 | 0 | [5 empty] | TTI INC. | 6786 | 661 | 6125 | 2925
|  |  | TTI INC. | 18 | 83.33% | 16.67% | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0
|  |  |  | 3 | 0% | 100% | 0 | #VALUE! | [5 empty] | MOUSER ELECTRONICS, INC. | 496 | 0 | 496 | 496
|  |  | MOUSER ELECTRONICS, INC. | 3 | 100% | 0% | 0 | 0 | [5 empty] | IBERCOIN INGENIEROS, S.L. | 1 | 0 | 0 | 0
|  |  | IBERCOIN INGENIEROS, S.L. | 1 | 0% | 100% | 1 | 0 | [5 empty] | Total general | 88069.2 | 4579.2 | 85197 | 37807
|  |  | Total general | 967 | 91.42% | 8.583% | 13 | #VALUE!
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Lead Time
PENDING ITEMS - LEAD TIME IMPACT
Count of PO Line | Column Label
Etiquetas de fila | - | Total
(AEMSA)ALMACENES ELECTRICOS MADRILE | 51 | 51
ABACO SUYTEC, S.A.U. | 56 | 56
AMIDATA, S.A. | 360 | 360
CONECTORES Y CABLES VAHER, S.A. | 15 | 15
Electro Enterprises New York | 2 | 2
ICOMPPLUS ELECTRONICS S.L | 38 | 38
INFORMATICA CALCULO Y TECNICA, S.A. | 5 | 5
REBOUND ELECTRONICS (UK) LTD | 1 | 1 |  |  |  |  | Etiquetas de fila | Cuenta de No. PO
SUMINISTROS CONECTORES PROF.,SA. | 30 | 30 |  |  |  |  | (AEMSA)ALMACENES ELECTRICOS MADRILE | 51
Technipol Suministros, S.L. | 8 | 8 |  |  |  |  | AMIDATA, S.A. | 360
TTI, INC. | 4 | 4 |  |  |  |  | CONECTORES Y CABLES VAHER, S.A. | 15
Total | 570 | 570 |  |  |  |  | DELL COMPUTER, S.A. | 1
[7 empty] | Electro Enterprises New York | 2
[7 empty] | ELECTRONIC EQUIPMENT TRADING SAU (E | 1
|  |  | VERY HIGH | HIGH | MEDIUM | LOW | GRUPO ELECTRO-STOCKS,S.L.U | 4
|  |  | #REF! | #REF! | #REF! | #REF! | ICOMPPLUS ELECTRONICS S.L | 38
[7 empty] | INFORMATICA CALCULO Y TECNICA, S.A. | 5
[7 empty] | INGRAM MICRO, S.L.U. | 1 | VERY HIGH | HIGH | MEDIUM | LOW
[7 empty] | MILEXIA IBÉRICA, S.A.U. | 1 | #REF! | #REF! | #REF! | 0
[7 empty] | REBOUND ELECTRONICS (UK) LTD | 1
[7 empty] | SUMINISTROS CONECTORES PROF.,SA. | 30
[7 empty] | SUMINISTROS, FRESADOS Y GRABADOS | 7
[7 empty] | TALLERES XUQUER, SL | 2
[7 empty] | TD SYNNEX SPAIN, S.L.U. | 7
[7 empty] | Technipol Suministros, S.L. | 8
[7 empty] | TTI, INC. | 4
[7 empty] | VESTUARIO Y PROTECCION LABORAL JOYS | 7
[7 empty] | ABACO SUYTEC, S.A.U. | 56
[7 empty] | PENTATEL COMUNICACIONES, S.L. | 5
[7 empty] | TALLERES SANTIAGO DATO, S.L.U. | 4
[7 empty] | VEOLIA SERVICIOS LECAM, S.A.U. | 4
[7 empty] | FELIPE DE MARCO, S.A. | 10
[7 empty] | ALTER TECHNOLOGY-TÜV NORD | 1
[7 empty] | HILTI ESPAÑOLA, S.A. | 6
[7 empty] | ACOM SISTEMAS, S.L. | 1
[7 empty] | AUXITEL, S.L. | 11
[7 empty] | FERRETERIA FERAYU SL | 1
[7 empty] | SOUND OF NUMBERS SL | 1
[7 empty] | FUNDACION JUAN XXIII-RONCALLI DISC. | 13
[7 empty] | SARVER S.L. | 44
[7 empty] | YNTEGRA SERV.INTEGRALES, S.L. | 2
[7 empty] | TCX MICRO, S.L.U | 6
[7 empty] | ISC Instalaciones y Servicios de | 4
[7 empty] | RDT INGENIEROS MADRID, S.L. | 1
[7 empty] | CONSUEGRA SOC. COOP. LTD. | 1
[7 empty] | APLICACIONES DE SIMULACION | 2
[7 empty] | ESTRUCTURAS COSAN,S.L. | 2
[7 empty] | LAYHER IBERICA, S.L. | 4
[7 empty] | TINDAI FORMACION, PREVENCION Y | 1
[7 empty] | ANTONIO RAMIREZ DECORACION SL | 1
[7 empty] | SOLUCIONES SICNOVA, S.L. | 1
3
[7 empty] | IBERCOIN INGENIEROS, S.L. | 1
[7 empty] | Total general | 731
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.

## High LD Table Analysis
Item | OEM P/N | OEM | Initial Supplier | Supplier Initial Proposal Delivery Date | Current Delivery Time | Mitigation Action | Status | Lead time Impact
PRIORITY 1
PRIORITY 2
PRIORITY 3

## Criticidades Producción
Item | Description | PO | Pos. | OEM P/N | OEM | Initial Supplier | Supplier Initial Proposal Delivery Date | Current Delivery Time | Fecha máxima necesidad | Mitigation Action | Status | Lead time Impact
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW
[11 empty] | WIP | LOW